Public Sector

Asset Investment Program

2008–09

Presented by

John Lenders, M.P.

Treasurer of the State of Victoria

for the information of Honourable Members

Budget Information Paper No. 1

Table of Contents

Introduction	1

Coverage	1

Assets	1

Document structure	2

Chapter 1: Public sector asset investment program 2008-09	3

Asset management and delivery	4

General government sector asset investment	9

Public non-financial corporations asset investment	12

Project descriptions from Table 1.4	16

Chapter 2: General government asset investment program 2008-09	23

Department of Education and Early Childhood Development	23

Department of Human Services	40

Department of Innovation, Industry and Regional Development	48

Department of Justice	52

Department of Planning and Community Development	57

Department of Premier and Cabinet	59

Department of Primary Industries	61

Department of Sustainability and Environment	62

Department of Transport	66

Department of Treasury and Finance	73

Parliament	74

Country Fire Authority	75

Metropolitan Fire and Emergency Services Board	77

Chapter 3: Major public non-financial corporations asset investment program 2008-09	79

Barwon Region Water Corporation	79

Central Gippsland Regional Water Corporation	88

Central Highlands Region Water Corporation	99

Coliban Region Water Corporation	102

East Gippsland Region Water Corporation	107

First Mildura Irrigation Trust	110

Gippsland and Southern Rural Water Corporation	111

Goulburn-Murray Rural Water Corporation	113

Goulburn Valley Region Water Corporation	117

Grampians Wimmera-Mallee Rural Water Corporation	123

Lower Murray Urban and Rural Water Corporation	127

North East Region Water Corporation	129

Office of Housing	132

South Gippsland Region Water Corporation	134

Wannon Regional Water Corporation	136

Western Region Water Corporation	140

Westernport Region Water Corporation	144

## Table of Contents (continued)

Appendix A: Contact addresses and telephone numbers	147

General government sector	147

Public non-financial corporations	149

Appendix B: Location index	151

Style conventions	157

Introduction

# Coverage

The 2008-09 Public Sector Asset Investment Program Budget Information Paper No. 1 (BIP1) is compiled in association with the annual Budget Papers to inform Parliament and the community about Victoria’s capital asset program. The general government sector asset investment projects published in this paper support the outputs detailed in Service Delivery, Budget Paper No. 3, 2008-09.

BIP1 presents:

- detailed listings of major asset investment in 2008-09 for the general government sector and for major public non-financial corporations (PNFCs);

- summary information for a number of significant corporations that provide goods and services in a commercial market place; and

- major public sector asset investment projects being delivered under Partnerships Victoria during 2008-09.

BIP1 captures projects with a total estimated investment (TEI) equal to or in excess of $240 000 and reflects machinery-of-government changes announced as part of the 2008-09 Budget.

Projects not included are those with a planned capital expenditure in 2008-09 of less than $72 000 and projects that do not deliver benefits beyond 12 months.

# Assets

Victoria’s economic outlook means that Victoria can sustain and improve the historic levels of infrastructure investment. As Victoria’s population continues to grow, investment in infrastructure remains one of the State’s key priorities. Asset investment projects result in the production, enhancement and acquisition of non-current physical assets, typically infrastructure assets. Infrastructure assets provide services used to support or produce outputs in the form of final services or products.

The State’s asset portfolio includes road and railway networks, information technology systems, schools and hospitals, as well as water storage and distribution infrastructure, correctional centres, courts, cultural assets such as historic museum collections, and environmental assets such as public reserves, parks and public open spaces.

# Document structure

The projects contained in the publication are listed together with their location under entity headings. Details of TEI are provided, including investment activity reflected in the 2008-09 Budget, together with projected asset investment expenditures on individual projects for 2008-09 and beyond.

For each entity, the asset investments are listed as either:

- ‘Existing’– projects that have received government approval and were being delivered as at 30 June 2008; or

- ‘New’– projects approved and announced to commence by government as part of the 2008-09 Budget Update or the 2008-09 Budget.

BIP1 is prepared by the Department of Treasury and Finance with input from the entities concerned. It should be noted that project details as listed reflect the intentions and priorities at the time of compilation. However, since asset investments are rarely static, it can be expected that some re-scheduling and re-programming will occur during the course of the year.

Chapter 1: Public sector asset investment program 2008-09

The Government is committed to investing in vital infrastructure projects to meet the needs of the growing Victorian population over the coming decades. Projects such as schools, roads, hospitals, public transport and securing future water supplies continue to form a key part of the Government’s infrastructure program. The investment in new technology is also critical to Victoria’s future prosperity. Investment in information and communication technologies remains an important focus of the Government’s agenda. This investment is provided through both the general government sector (e.g. government departments) and public non-financial corporations which are located in the broader public sector (e.g. urban and regional water authorities).

Victoria’s economic outlook means that Victoria can sustain and improve the Government’s historic levels of investment in infrastructure. Since 1999, the Victorian Government has invested over $21 billion to deliver the biggest infrastructure program in Victoria’s history. As announced in the 2008-09 Budget, the Government will invest a further $17 billion over the next four years to maintain a strong commitment to infrastructure investment.

While investment in Victoria’s infrastructure needs will continue, the current level of expenditure is particularly high to meet specific needs. As demonstrated in this information paper, it also reflects the Government’s commitment to supporting regional areas. Chart 1.1 shows the distribution across the state of the asset investment projects that have been included in Budget Information Paper 1 (BIP1), with 56 per cent of total projects being delivered in regional Victoria and a further 27 per cent supporting service delivery across the State.

Part of this chapter delivers on an election commitment (Table 1.4) to highlight key infrastructure projects of strategic importance to the state. There is also commentary provided on the state of these projects.

Chart 1.1: Distribution of the 2008-09 BIP1 asset investment projects by area – Percentage of total BIP1 asset investment projects

Source: Department of Treasury and Finance

# Asset management and delivery

Asset investment decision making is guided by Government policy on economic and social development, and financial and environmental management. The Government’s vision is articulated in key strategic planning documents including Growing Victoria Together and Melbourne 2030. Commitments on asset investment are informed by community consultation, existing legislation, policy and contractual commitments, and the provision of advice from departments on service delivery needs, demand drivers, service standards and whole-of-life asset plans.

The Government has also established several planning and governance processes to support the planning and delivery of public sector assets. These include the Asset Management Framework, the Gateway Initiative and Partnerships Victoria. Partnerships Victoria aims to create long term service contracts between the Government and private businesses to deliver public infrastructure and related services. The Partnerships Victoria approach achieves value for money by stimulating innovation through competitive bidding, by appropriate transfer of risk and by facilitating whole-of-life cost considerations.

Sustaining the capital stock to effectively support services is being achieved by investment in renewing and replacing assets at consistent levels to achieve longer-term service delivery needs.

## Asset investment program

BIP1 has traditionally provided details on the government’s asset investment program from the perspective of individual projects. The subsequent chapters of BIP1 have provided listings of projects that meet specific criteria (as outlined in the Introduction) with details on the total estimated investment (TEI) provided for each project together with expenditure to date, estimated expenditure for the current financial year and any remaining future year expenditure. While this format is continued in Chapters 2 and 3, to provide a better comparison with the financial estimates published as part of the 2008-09 Budget and included in Budget Paper No. 4 – Statement of Finances, Table 1.1 provides details on the aggregate purchases for the general government and public non-financial corporation (PNFC) sectors.

Table 1.1: Purchases of non-financial assets – by sector

($ million)

|  | Estimated Expenditure 2007-08 | Estimated Expenditure 2008-09 | Estimated Expenditure 2009-10 to 2011-12 |
| --- | --- | --- | --- |
| General government |  |  |  |
| Education and Early Childhood Development | 620.5 | 705.0 | 913.5 |
| Human Services | 670.4 | 643.2 | 1 007.9 |
| Innovation, Industry and Regional Development | 219.7 | 166.2 | 367.6 |
| Justice | 169.0 | 281.9 | 710.7 |
| Planning and Community Development | 18.8 | 47.9 | 73.6 |
| Premier and Cabinet | 101.8 | 39.2 | 73.4 |
| Primary Industries | 15.9 | 63.2 | 148.7 |
| Sustainability and Environment | 118.6 | 130.6 | 153.7 |
| Transport | 922.0 | 936.8 | 2 196.3 |
| Treasury and Finance | 8.7 | 126.4 | 768.3 |
| Parliament | 11.2 | 8.1 | 11.2 |
| Regulatory bodies and other part budget funded agencies | 117.0 | 135.3 | 342.0 |
| Not allocated to departments (a) | .. | ( 445.9) | 3 879.6 |
| Sub-Total General government | 2 993.6 | 2 837.9 | 10 646.4 |
| Public non-financial corporations |  |  |  |
| Barwon Region Water Corporation | 61.4 | 111.6 | 251.8 |
| Central Gippsland Regional Water Corporation | 135.8 | 59.3 | 60.1 |
| Central Highlands Region Water Corporation | 199.6 | 54.4 | 81.7 |
| City West Water Ltd | 67.2 | 85.1 | 334.2 |
| Coliban Region Water Corporation | 93.6 | 71.5 | 141.1 |
| Director of Housing (PNFC) | 325.5 | 351.4 | 836.2 |
| East Gippsland Region Water Corporation | 21.8 | 29.7 | 25.9 |
| First Mildura Irrigation Trust | 1.3 | .. | 0.3 |
| Gippsland and Southern Rural Water Corporation | 18.8 | 21.7 | 72.9 |
| Goulburn Murray Rural Water Corporation | 103.2 | 60.8 | 111.1 |
| Goulburn Valley Region Water Corporation | 28.3 | 37.5 | 85.3 |
| Grampians Wimmera Mallee Water Corporation | 262.9 | 293.0 | 79.3 |
| Lower Murray Urban and Rural Water Corporation | 35.9 | 26.8 | 20.9 |
| Melbourne Water Corporation | 347.1 | 1 743.4 | 4 689.4 |
| North East Region Water Corporation | 24.3 | 28.9 | 41.3 |
| Port of Melbourne Corporation | 266.7 | 494.0 | 553.1 |

Table 1.1: Purchases of non-financial assets – by sector (continued)

($ million)

|  | Estimated Expenditure 2007-08 | Estimated Expenditure 2008-09 | Estimated Expenditure 2009-10 to 2011-12 |
| --- | --- | --- | --- |
| South East Water Ltd | 109.4 | 121.0 | 420.4 |
| South Gippsland Region Water Corporation | 11.3 | 12.0 | 15.3 |
| V/Line Passenger Corporation | 39.2 | 28.7 | 67.4 |
| Victorian Rail Track | 466.7 | 792.5 | 1 346.3 |
| Wannon Region Water Corporation | 23.7 | 40.6 | 48.0 |
| Western Region Water Corporation | 38.1 | 29.9 | 99.9 |
| Westernport Region Water Corporation | 5.3 | 2.9 | 7.6 |
| Yarra Valley Water Ltd | 187.7 | 236.0 | 832.5 |
| Other (b) | 328.3 | 312.7 | 1 681.8 |
| Sub-Total Public non-financial corporations | 3 203.1 | 5 045.5 | 11 903.8 |
| Total purchases of non-financial assets | 6 196.7 | 7 883.4 | 22 550.2 |

Source: Department of Treasury and Finance

Notes:

(a)	Amount available to be allocated to specific departments and projects in future budgets. This includes an allowance for departmental underspending in 2008-09 which may be subject to carryover in 2009-10.

(b)	Includes PNFCs with smaller asset investment programs, those where separate disclosure compromises competitive neutrality and commercial in confidence issues; and asset contingencies included in the estimates mainly related to general government equity contributions to PNFCs.

Using the more usual presentation for BIP1, the TEI of the asset investment program included in this publication is $20 billion, with $14.2 billion worth of projects in the general government sector and the remainder being provided through the public non-financial corporations listed in Chapter 3. Asset investments summarised in Table 1.2 use the same categorisation of projects for those in Chapters 2 and 3 where the individual projects are categorised as either:

- ‘Existing’ – projects that have received government approval and are currently being delivered as at 6 May 2008; or

- ‘New’ – projects approved and announced to commence by government as part of the 2007-08 Budget Update or the 2008-09 Budget.

Table 1.2: Infrastructure investment by TEI – Summary

($ million)

| Sector | Total Estimated Investment | Expenditure to 30.06.2008 (a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| --- | --- | --- | --- | --- |
| General government |  |  |  |  |
| Existing projects | 11 549.2 | 4 800.9 | 3 040.2 | 3 708.7 |
| New projects | 2 652.4 | 24.5 | 765.0 | 1 863.1 |
| Public non-financial corporations |  |  |  |  |
| Existing projects | 5 498.0 | 1 661.9 | 945.5 | 2 890.6 |
| New projects | 402.9 | 10.7 | 186.2 | 206.3 |
| Total existing projects | 17 047.2 | 6 462.8 | 3 985.7 | 6 599.3 |
| Total new projects | 3 055.3 | 35.2 | 951.2 | 2 069.4 |
| Total projects | 20 102.5 | 6 497.9 | 4 936.9 | 8 668.8 |

Source: Department of Treasury and Finance

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments and agencies as at May 2008.

## Sources of funding

Asset investment can require significant and long term funding commitments given the scale of the projects. Asset investment in both the general government and PNFC sectors is funded from a combination of sources including:

- Victorian Government appropriations or grants, cash surpluses from operating activities and borrowings;

- Commonwealth Government funding; and/or

- own source revenue.

The total estimated investment for the individual projects reported in BIP1 reflects the total value of all of these sources of funding.

## Partnerships Victoria

A number of asset investment projects are also procured through Partnerships Victoria arrangements. The choice between public and private provisions of infrastructure and associated services is based on an assessment of value for money and satisfaction of the public interest. This framework ensures that investment decisions are based on merit and outcomes are judged on the public benefits obtained.

The existing Partnerships Victoria projects represent a total estimated capital expenditure of approximately $5.5 billion, of which the following have been commissioned and are operational:

- Melbourne County Court;

- Wodonga Wastewater Treatment Plant;

- Campaspe Wastewater Treatment Plant;

- Casey Community Hospital;

- Mobile Data network;

- Correctional facilities;

- Southern Cross Station redevelopment;

- Emergency Alerting System;

- Royal Melbourne Showgrounds redevelopment;

- Metropolitan Mobile Radio;

- Royal Women’s Hospital redevelopment; and

- EastLink.

A further four contracted projects are still in the construction phase. These projects are:

- Melbourne Convention Centre development;

- Ballarat North Water reclamation;

- Barwon Water – Biosolids Management; and

- Royal Children’s Hospital redevelopment.

In addition, the procurement process is underway for the Biosciences Research Centre, the Wonthaggi Desalination project, and 11 schools as follows:

- Point Cook North P-9 School;

- Taylors Hill Primary School;

- Derrimut Primary School;

- Cranbourne North East Primary School;

- Mernda Central Primary School;

- Lyndhurst Primary School;

- Cranbourne East P-12 School;

- Kororoit Creek Primary School;

- Truganina South Primary School;

- Craigieburn West Primary School; and

- Casey Central Secondary College.

The procurement process for the Ararat prison project is expected to commence during 2008-09.

# General government sector asset investment

The Victorian Government manages an extensive range of public physical assets, which are estimated to be valued at $69.6 billion at 30 June 2009. Table 1.3 shows projected investment in 2008-09, by department. The table covers both new projects announced in the 2008-09 Budget and projects previously underway. Details on individual projects can be found in Chapter 2.

Table 1.3: General government asset investment program 2008-09 – Summary

($ million)

| Department | Total Estimated Investment |  | Expenditure to 30.06.2008 (a) |  |  | Estimated Expenditure 2008-09 | Remaining Expenditure |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Education and Early Childhood Development |  |  |  |  |  |  |  |
| Existing projects | 669.5 |  | 315.6 |  |  | 287.6 | 66.3 |
| New projects | 426.3 |  | .. |  |  | 203.0 | 223.3 |
| Human Services |  |  |  |  |  |  |  |
| Existing projects | 1 473.0 |  | 843.3 |  |  | 380.5 | 249.2 |
| New projects | 490.3 |  | 15.3 |  |  | 99.9 | 375.1 |
| Innovation, Industry and Regional Development |  |  |  |  |  |  |  |
| Existing projects | 213.3 |  | 83.5 |  |  | 78.4 | 51.4 |
| New projects | 103.1 |  | .. |  |  | 42.7 | 60.4 |
| Justice |  |  |  |  |  |  |  |
| Existing projects | 421.8 |  | 218.1 |  |  | 124.7 | 79.1 |
| New projects | 451.9 |  | 2.5 |  |  | 119.4 | 330.0 |
| Planning and Community Development |  |  |  |  |  |  |  |
| Existing projects | 505.0 |  | 169.0 |  |  | 194.0 | 142.1 |
| New projects | 70.5 |  | .. |  |  | 18.9 | 51.6 |
| Premier and Cabinet |  |  |  |  |  |  |  |
| Existing projects | 183.7 |  | 150.5 |  |  | 32.3 | 1.0 |
| New projects | 11.2 |  | .. |  |  | 7.2 | 4.0 |
| Primary Industries |  |  |  |  |  |  |  |
| Existing projects | 225.8 |  | 1.4 |  |  | 46.8 | 177.8 |
| New projects | 13.9 |  | 1.1 |  |  | 2.8 | 10.1 |
| Sustainability and Environment |  |  |  |  |  |  |  |
| Existing projects | 1 873.6 |  | 1 038.0 |  |  | 257.2 | 578.5 |
| New projects | 96.1 |  | 4.5 |  |  | 45.4 | 46.2 |
| Transport |  |  |  |  |  |  |  |
| Existing projects | 5 769.0 |  | 1 869.9 |  |  | 1 571.2 | 2 327.9 |
| New projects | 907.5 |  | 0.9 |  |  | 184.5 | 722.1 |
| Treasury and Finance |  |  |  |  |  |  |  |
| Existing projects | 18.2 |  | 5.1 |  |  | 11.0 | 2.2 |
| New projects | .. |  | .. |  |  | .. | .. |
| Parliament |  |  |  |  |  |  |  |
| Existing projects | 14.1 |  | 6.6 |  |  | 5.2 | 2.3 |
| New projects | 3.8 |  | .. |  |  | 0.9 | 2.9 |
| Country Fire Authority |  |  |  |  |  |  |  |
| Existing projects | 122.0 |  | 68.7 |  |  | 28.7 | 24.5 |
| New projects | 30.0 |  | 0.2 |  |  | 13.3 | 16.5 |
| Metropolitan Fire and Emergency Services Board |  |  |  |  |  |  |  |
| Existing projects | 60.2 |  | 31.2 |  |  | 22.6 | 6.4 |
| New projects | 47.8 |  | .. |  |  | 27.0 | 20.9 |
| Total existing projects | 11 549.2 |  | 4 800.9 |  |  | 3 040.2 | 3 708.7 |
| Total new projects | 2 652.4 |  | 24.5 |  |  | 765.0 | 1 863.1 |
| Total projects | 14 201.6 |  | 4 825.4 |  |  | 3 805.2 | 5 571.8 |

Source: Department of Treasury and Finance

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments and agencies as at May 2008.

## Types of investments

Infrastructure can be improved either through acquiring additional assets or through renewal or replacement of existing assets.

Chapter 2 presents new projects in the general government sector for 2008-09 by investment type. Chart 1.2 shows, for each service sector, investments to replenish and rejuvenate the asset stock along with investments to further expand and enhance the asset stock. These investments are being made consistent with government priorities and align with Growing Victoria Together, Sustaining Our Assets and Melbourne 2030.

Of the total general government asset investment projects included in BIP1 for 2008-09, around 44.5 per cent is for renewal or replacement projects and the remainder is for additional and enhanced infrastructure.

Chart 1.2: Infrastructure types (renewal or additional) announced in 2008-09

Source: Department of Treasury and Finance

## 2008-09 Asset Investment Initiatives

The 2008-09 Budget focused on the pressures placed on Victorian resources and infrastructure from population growth. The Budget was framed around delivering the infrastructure Victoria will need over the coming decades.

Major asset investments announced in the 2008-09 Budget were presented in Chapter 1, Service and Budget Initiatives and in Appendix A, Output, Asset Investment and Revenue Initiatives of 2008-09 Budget Paper No. 3, Service Delivery.

The 2008-09 Budget saw the announcement of new asset investments with a TEI of $4.4 billion, including $1.1 billion announced as part of the 2007-08 Budget Update.

Major infrastructure investments included in the 2008-09 Budget were as follows:

### Road and Rail

- $663 million TEI in new and upgraded roads in Melbourne’s growing outer suburbs and in regional areas. A further $529 million TEI was provided for rail infrastructure, to improve the capacity and reliability of the metropolitan train network, regional passenger rail services, and improve the rail freight network.

### Hospitals and Health Care Facilities

- $491 million in hospitals, health care facilities and medical equipment, including $137 million for major projects such as the Warrnambool Hospital redevelopment and the expansion of the Sunshine Hospital.

### Schools

- $592 million for the second tranche of the Government’s $1.9 billion Victorian Schools Plan for new, refurbished and modernised schools and other projects.

### Police and Justice

- $476 million TEI to improve the facilities available to Victoria’s police and the justice system, including upgrades to police stations and the construction of a new 350 bed prison at Ararat.

The broad and diverse capital program demonstrates the Government’s commitment to deliver world-class infrastructure to enhance social, economic, environmental and cultural outcomes across the State.

The Government has committed to a total asset investment in infrastructure over the next four years to 2011-2012 of $17.1 billion to support service delivery to the public. The actual expenditure and delivery of assets from these investments occurs over a number of years and is reflected in the project listings provided in this document.

# Public non-financial corporations asset investment

Asset investment in the PNFC sector includes investment in the regional and rural water authorities, public housing, port infrastructure and public transportation.

The total physical assets that PNFCs are accountable for managing increased from $38.7 billion as at 30 June 2006 to $40.2 billion at 30 June 2007. PNFCs are required to obtain the Treasurer’s approval for all projects with a TEI greater than $5 million. In seeking the Treasurer’s approval, PNFCs are required to submit a detailed business case of the proposal to the Department of Treasury and Finance for evaluation and review.

The growth in capital stock for the sector, excluding revaluation movements, has largely been funded through equity, namely additional contributed capital from the Victorian Government (including capital grants received from the Commonwealth Government), operating surpluses and accumulated funds and borrowings. Contributions from the private sector, for example from developers providing assets free of charge to entities in the water sector, also adds to the asset base of the sector.

The government has already announced significant infrastructure investments for the PNFC sector, including $4.9 billion to diversify and secure water supplies for the long term. Key components of the Government’s plan include:

- the first stage of the $1 billion Food Bowl Modernisation project upgrading major irrigation infrastructure in northern Victoria will create water savings of the long term average of 225 billion litres a year to be shared equally by irrigators, the environment and Melbourne by 2012. The State Government is contributing $600 million, Melbourne Water Corporation $300 million and $100 million from Goulburn-Murray Water. The first water savings will be available from 2010 for Melbourne;

- the $750 million Sugarloaf interconnector which will link the Goulburn River to the Melbourne system and transfer a share of the water savings obtained through the Food Bowl Modernisation Project to Melbourne from 2010. Melbourne Water Corporation will finance the delivery of this project; and

- the Wonthaggi Desalination project at an estimated capital cost of $3.1 billion is expected to be delivered under the Government’s Partnerships Victoria framework.

Other initiatives for the PNFC sector included in the 2008-09 Budget include:

- $256 million for the purchase of another eight metropolitan trains, stabling and associated operating costs to address the growing demand on the metropolitan rail network. This procurement is in addition to the purchase of ten metropolitan trains announced in the 2007-08 Budget. This initiative is funded from the Meeting Our Transport Challenges reserve; and

- $272.9 million for the delivery of works to address congestion on the metropolitan train network, including upgrades to Craigieburn and Laverton stations and associated track and the Dandenong rail corridor – Westall rail upgrade.

Historically, BIP1 has only included details on asset investment information on a project-by-project for the regional and rural water authorities and the Office of Housing, and this has continued with this publication in Chapter 3. It is anticipated that data from PNFCs (such as the metropolitan water corporations) will be included in future publications.

## Key Infrastructure Projects

Modern, efficient infrastructure is vitally important to the Government’s commitment of promoting sustainable growth across the whole state. Infrastructure is a key driver of economic growth and is essential to support the delivery of high quality services. Since 1999 the Government has been delivering the largest asset investment program in Victoria’s history. In 2008-09, the net infrastructure investment program of the general government sector alone is estimated to be $3.9 billion and to average $4.3 billion over the forward estimates.

With record levels of infrastructure investment to be delivered, the Government is also committed to increasing transparency and accountability for its major infrastructure projects. As such, for the first time in BIP1, and consistent with its election commitment to promote further openness and transparency in infrastructure projects, as stated in the policy document Keeping Victoria’s Finances Strong, Table 1.4 provides a consolidated report on key infrastructure projects being delivered across the State. This is regardless of whether the individual projects are being delivered by the general government sector, the PNFC sector, or through Partnerships Victoria arrangements.

The key infrastructure projects identified in this report are large, in that they have a TEI greater than $100 million. Their strategic significance to the State is demonstrated by listing the projects according to the five components of the Government’s Growing Victoria Together vision. Each asset project, not all of which have been listed in subsequent chapters, contributes to the accomplishment of two or more of the Growing Victoria Together goals.

The rail, road and other construction projects listed under Thriving Economy have a role to play in the support of industry and the linking of all Victorians. The commitment by the Government to Quality Education and Health is demonstrated by the 10-year plan to either renew or rebuild every Victorian School and to replace the Royal Children’s Hospital. In order to protect the environment for future generations and to efficiently use our natural resources, projects such as the Wonthaggi Desalination project and the Wimmera Mallee Pipeline project support the Government’s vision for a Healthy Environment. To deliver on its commitment to Caring Communities and a Vibrant Democracy, projects such as Building Confidence in Corrections and the Rectangular Sports Stadium will contribute to the building of friendly, confident and safe communities that respect the state’s rich cultural and social diversity.

A description of the projects listed in Table 1.4 can be found after Table 1.4.

Table 1.4: Key strategic infrastructure projects

($ million)

|  | Total Estimated Investment | Expenditure to 30.06.08 (a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| --- | --- | --- | --- | --- |
| Thriving Economy |  |  |  |  |
| Accessible Public Transport in Victoria | 129 | 48 | 42 | 39 |
| Calder Highway Improvements (b) | 395 | 367 | 18 | 10 |
| Channel Deepening project (c) | 969 | .. | .. | .. |
| Dynon Port Rail Link (d) | 125 | 91 | 34 | .. |
| Geelong Ring Road | 507 | 291 | 91 | 125 |
| Melbourne Convention Centre (e) | 367 | .. | .. | .. |
| Melbourne Wholesale Market (f) | 218 | .. | 42 | 176 |
| Metropolitan Train Safety Communications System | 135 | 11 | 48 | 75 |
| New Ticketing Solution – Technology and Installation | 460 | 180 | 150 | 131 |
| Purchase of Additional Rolling Stock (Suburban and V'Locity) | 666 | 88 | 147 | 431 |
| Transit Cities – Revitalise Central Dandenong | 243 | 75 | 60 | 109 |
| Western Bypass – Deer Park | 331 | 233 | 95 | 3 |
| Westgate Monash Freeway Improvement project | 1 100 | 150 | 360 | 590 |
|  | 5 645 | 1 534 | 1 087 | 1 689 |
| Quality Health and Education |  |  |  |  |
| Royal Children's Hospital (e) | 847 | .. | .. | .. |
| Victorian Schools Plan - School and School-ICT projects | 964 | 208 | 456 | 300 |
|  | 1 811 | 208 | 456 | 300 |
| Healthy Environment |  |  |  |  |
| Eastern Treatment Plant – Tertiary Treatment | 322 | 11 | 4 | 308 |
| Food Bowl Modernisation project | 1000 | 82 | 84 | 834 |
| Goldfields Superpipe - Ballarat Interconnect | 179 | 130 | 25 | 24 |
| Melbourne Main Sewer replacement | 221 | 17 | 38 | 167 |
| Northern Sewerage project | 650 | 138 | 135 | 378 |
| Sugarloaf Pipeline | 750 | 42 | 366 | 343 |
| Wonthaggi Desalination project (e) | 3 100 | .. | .. | .. |
|  | 6 223 | 420 | 651 | 2 053 |

Table 1.4: Key strategic infrastructure projects (continued)

($ million)

|  | Total Estimated Investment | Expenditure to 30.06.08 (a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| --- | --- | --- | --- | --- |
| Caring Communities and Vibrant Democracy |  |  |  |  |
| Building Confidence in Corrections | 317 | .. | 78 | 238 |
| Melbourne Recital Centre and Melbourne Theatre Company Theatre | 128 | 117 | 11 | .. |
| Rectangular Sports Stadium | 211 | 80 | 106 | 25 |
|  | 656 | 197 | 195 | 263 |
| Total Key Infrastructure Projects | 14 335 | 2 359 | 2 389 | 4 305 |

Source: Department of Treasury and Finance

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	This is the total project cost and includes completed stages.

(c)	Note that in December 2007 the Government committed $150 million to the Channel Deepening Project (CDP) and associated infrastructure works, with the remaining cost to be funded by port users through port charges. Government also committed $7.5 million to the CDP in 2004-05, as detailed in the Premier's Economic Statement of April 2004.

(d)	Total Estimated Investment of $125 million excludes $13.6 million from the Port of Melbourne Corporation.

(e) 	Project being delivered under Partnerships Victoria.

(f)	This figure excludes any Treasury Corporation of Victoria funding for this project.

# Project descriptions from Table 1.4

#### Thriving Economy

##### Accessible Public Transport in Victoria

This long term strategy focuses on delivering accessible bus, train, tram and taxi services throughout Victoria. This initiative contributes towards improving access to all public transport modes by making it easier for all Victorians to move around and participate in their community.

##### Calder Highway Improvements

Improvements to the Calder Highway aim to improve travel times between Bendigo and Melbourne and improve the safety for road travellers. This initiative contributes to major blackspots identified on the road network and improves connectivity between metropolitan Melbourne and regional Victoria.

##### Channel Deepening project

Dredging of Port Phillip Bay shipping channels and associated works seeks to provide vessels calling at the Port of Melbourne with 14 metre draught access at all tides. This initiative contributes towards enhancing port efficiency as well as that of export and import industries, and is scheduled for completion in the summer of 2009-10.

##### Dynon Port Rail Link

The construction of an uninterrupted rail link into the Port of Melbourne, including a new overpass along Footscray Road is expected to improve the capacity and efficiency of container movements into and out of the Port of Melbourne. This initiative contributes to improving travel times and freight connections and is expected to be completed in 2009.

##### Geelong Ring Road

The construction of a 23 kilometre freeway-standard road along Geelong's western outskirts to enable drivers to avoid 29 sets of traffic lights and improve the travel time from 25-60 minutes down to less than 15 minutes. This initiative contributes to growing  and linking Victoria by enhancing the performance of road networks to improve travel time and safety.

##### Melbourne Convention Centre

The construction of a new Convention Centre integrated with the existing Exhibition Centre aims to create the largest combined exhibition and convention centre in Australia.

The new Convention Centre seeks to provide economic benefits to Victoria by increasing the State’s capability to attract large international conferences and exhibitions.

The Convention Centre is on track to open in 2009.

##### Melbourne Wholesale Market

The relocation and development of the new Melbourne Wholesale Market will replace the existing Footscray Road infrastructure which is reaching the end of its design life. The new market provides opportunities for Victoria’s fruit and vegetable production, distribution and retail industry to become more efficient. The project also makes available the current site for the implementation of the Port of Melbourne strategy with the relocation occurring in line with the strategy’s development requirements.

##### Metropolitan Train Safety Communications System

Upgrading the existing Metrol rail management systems with state-of-the-art technology will allow for better coordination of the movement of trains on the network, increase the number of trains that can safely run on the system and provide more reliable up-to-the-minute timetable information for passengers.

##### New Ticketing Solution – Technology and Installation

Introduction of a high technology plastic smartcard that stores value aims to make travelling by train, tram and bus simpler for passengers.

##### Purchase of Additional Rolling Stock (Suburban and V’Locity)

Purchase of additional train rolling stock and V’Locity passenger trains seeks to improve rail load carrying capacity, passenger comfort and travel time between regional centres and Melbourne.

##### Transit Cities – Revitalise Central Dandenong

This project includes various improvements to position central Dandenong as an economic hub. Improvements include the development of a metropolitan village on the old saleyards site, development of the Lonsdale Street Boulevard and the development of the George Street bridge. This project will facilitate private sector investment leading to more jobs and economic growth for the region.

##### Western Bypass – Deer Park

The construction of a new 9.3 kilometre four lane freeway bypass from Sunshine West to Caroline Springs aims to improve traffic flow.  This initiative develops high quality transport links to facilitate more efficient freight movement and improves safety and amenity in key growth areas.

##### Westgate Monash Freeway Improvement project

This project represents a major upgrade of City Link's Southern Link and two adjoining state-managed roads to improve traffic flow along the 75 kilometre west-east corridor that carries essential freight and thousands of commuters daily. These improvements tackle congestion and improve travel times through enhanced transport links for motorists and Victoria’s growing freight task.

#### Quality Health and Education

##### Royal Children’s Hospital

Replacement of the existing Royal Children's Hospital with a new state-of-the-art 340 bed children’s hospital, with a capacity to treat an extra 35 000 patients a year. The new energy efficient hospital will be completed in 2011 and will provide improved world-class health facilities for Victorian children and their families. The net present cost of the project is approximately seven per cent below the public sector comparator, which is a key indicator that the project delivers value for money for the state. The winning bidder's proposal also offers other significant value for money benefits, such as enhanced amenity, additional space within the building, and world class design.

Further information on this project can be found in the Royal Children's Hospital Project Summary, available on the Partnerships Victoria website (www.partnerships.vic.gov.au).

##### Victorian Schools Plan – Schools and school-ICT projects

This 10-year plan provides for modernisation, regeneration or replacement of every Victorian school. The Victorian Schools Plan delivers far-reaching community benefits by providing new facilities for the use of schools, Technical and Further Education providers and their neighbouring communities. Overall $1.9 billion is being invested to rebuild, renovate or extend all schools by 2016-17, and includes the introduction of the Ultranet project.

#### Healthy Environment

##### Eastern Treatment Plant – Tertiary Treatment

This project is an upgrade to treat wastewater to Class A standard to be made available by 2012 for the continued expansion of residential, industrial and open space recycled water use.

##### Food Bowl Modernisation project

This project is designed to save up to the long term average of 225 billion litres of water in the Goulburn and Murray irrigation systems currently lost through leaks, evaporation and other inefficiencies. The water saved will be shared equally by irrigators, the environment and Melbourne and is due for completion in 2012.

##### Goldfields Superpipe – Ballarat Interconnect

The Ballarat link of the Goldfields Superpipe will secure Ballarat and its district’s future water supplies for the next 50 years by transferring water from the larger and more reliable Goulburn system to the Ballarat region. The Ballarat and district water supply system serves 97 000 residents and thousands of businesses across 50 communities and six local municipalities. The pipeline will enable the supply initially of up to eight gigalitres of water a year into the Ballarat and district water supply system, with the potential to increase this volume to 18 gigalitres per year over the longer term if required. The pipeline was officially opened in May 2008.

##### Melbourne Main Sewer replacement

The Melbourne Main Sewer replacement aims to reduce environmental and public health risks. It will also cater for forecast growth in sewage flows in the catchment, and allow the continued provision of sewerage services to Melbourne Docklands, the Central Business District, and parts of Port Melbourne and South Melbourne.

The project is scheduled to be completed by March 2012.

##### Northern Sewerage project

This project will construct a 12.4 kilometre sewer that will connect the sewerage system near the Merri Creek at Coburg and the Moonee Ponds Creek in Pascoe Vale to Melbourne Water’s North Western Sewer in Essendon.

The project is intended to provide relief for the existing overloaded sewerage system, and ensure compliance with the State Environment Protection Policy (SEPP). The project would protect the environment by preventing sewage spills into Edgars, Darebin, Merri and Moonee Ponds Creeks. In line with the Government’s Melbourne 2030 Strategy, the project has been sized to provide capacity for the growth in the various catchments to the north and provide sewer servicing for the key development corridors of Craigieburn, Epping and South Morang.

The target completion date is December 2011.

##### Sugarloaf Pipeline

This project links the Goulburn River to the Melbourne system and transfer a share of the water savings obtained through the Food Bowl Modernisation project to Melbourne from 2010.

##### Wonthaggi Desalination project

The construction of a seawater desalination plant at Wonthaggi and associated infrastructure, including an 85 kilometre pipeline, to connect the plant to Melbourne's water supply system. The plant will provide additional water to Melbourne, Geelong, Westernport and South Gippsland.

#### Caring Communities and Vibrant Democracy

##### Building Confidence in Corrections

Enhancements to the corrections system funded in the 2008-09 Budget included the construction of a new 350-bed male prison at Ararat and expansion of capacity at various existing prison sites. This expanded capacity assists to meet projected future demand in the corrections system. In addition, asset funding will improve the management of high risk sex offenders who are subject to the new post-sentence supervision and detention scheme.

The new facility, scheduled to begin construction in mid 2010, will be built with a focus on providing an environment conducive to rehabilitation and reducing reoffences, in line with the Growing Victoria Together vision to build friendly, confident and safe communities.

##### Melbourne Recital Centre and Melbourne Theatre Company Theatre

This project reflects construction of two new arts venues. The 1 000 seat Melbourne Recital Centre is designed for optimum acoustics to enhance the performance, recording, broadcast  and enjoyment of small ensemble music and the new permanent home for the Melbourne Theatre Company includes a 500 seat stage with the latest theatre technology, a full fly tower and backstage accommodation.

Set for completion in December 2008, the venues will increase the cultural diversity of arts programming, access to the arts and the range of performance spaces.

##### Rectangular Sports Stadium

Construction of a new soccer and rugby stadium to be built in the Olympic Park precinct. The stadium will also include a sports administration campus, featuring an elite training centre and office accommodation for a range of sporting organisations. The Rectangular Sports Stadium is expected to bring together Victorian communities and create a lasting legacy for future generations to enjoy.

Chapter 2: General government asset investment program 2008-09

# Department of Education and Early Childhood Development

## Existing projects

| ($ thousand) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Academic Number (Statewide) | 5 100 |  |  | 773 | 1 711 | 2 616 |
| Albert Park Secondary College – Replacement School (Albert Park) | 16 000 |  |  | 1 920 | 12 958 | 1 122 |
| Altona/Bayside Regeneration – Altona College and Altona West Primary School (Altona) | 6 210 |  |  | 1 221 | 4 989 | .. |
| Altona/Bayside Regeneration – Bayside Secondary College (Altona North Campus) and Altona Gate Primary School – Stage 1 (Altona North) | 6 250 |  |  | 2 517 | 3 733 | .. |
| Ballarat Secondary College – Modernisation – General Purpose Classrooms, Administration, Science and Technology (Ballarat East) | 5 633 |  |  | 3 130 | 2 503 | .. |
| Beaconsfield Upper Primary School – Modernisation – General Purpose Classrooms, Staff Work Space, Student Toilets (Upper Beaconsfield) |  | 1 523 |  | 1 393 | 130 | .. |
| Beechworth Secondary College – Modernisation – Technology, Art, Student Toilets, Staff Administration, General Purpose Classrooms/ Science, Lockers (Beechworth) |  | 5 153 |  | 3 390 | 1 763 | .. |
| Bendigo Education Plan – Regeneration – Eaglehawk Secondary College (Eaglehawk) | 10 000 |  |  | 2 556 | 7 444 | .. |
| Bendigo Education Plan – Regeneration – Kangaroo Flat Secondary College (Kangaroo Flat) | 10 000 |  |  | 1 413 | 8 587 | .. |
| Bentleigh Secondary College – Modernisation – General Purpose Classrooms, Library, Fabrics, Senior Student Lounge, Science, Information Technology, Staff Work Space, Lockers (Bentleigh East) | 6 233 |  |  | 4 373 | 1 860 | .. |
| Bentleigh West Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Staff Administration, Library, Student Toilets (Bentleigh) | 6 153 |  |  | 2 641 | 3 512 | .. |
| Berwick South Primary School – New School (Berwick South) | 7 850 |  |  | 4 628 | 3 222 | .. |
| Better Schools Today (Various) | 20 000 |  |  | 14 500 | 5 500 | .. |
| Black Hill Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Staff Administration (Ballarat) | 3 013 |  |  | 1 696 | 1 317 | .. |
| Box Hill High School – Modernisation – General Purpose Classrooms, Canteen, Physical Education, Library, 3D Art, Home Economics, Staff Administration, Student Toilets (Box Hill) |  | 5 763 |  | 4 351 | 1 412 | .. |
| Broadmeadows Regeneration – Regeneration – Broadmeadows Secondary College and Broadmeadows Primary School (Broadmeadows) | 11 415 |  |  | 4 251 | 7 164 | .. |
| Broadmeadows Regeneration – Regeneration – Erinbank Secondary College and Hillcrest Secondary College (Broadmeadows) | 10 400 |  |  | 2 323 | 8 077 | .. |
| Buckley Park Secondary College – Modernisation – Staff Administration, Senior Student Lounge, Canteen, Staff and Student Toilets, General Purpose Classrooms, Information Technology, Fabrics (Essendon) | 5 003 |  |  | 4 132 | 871 | .. |
| Caroline Springs North P-9 – New School – Stage 1 (Caroline Springs) | 7 850 |  |  | 2 528 | 5 322 | .. |
| Caroline Springs P-9 (Brookside Campus) – Modernisation – Permanent Facilities for Years 7-9 including General Purpose Classrooms, Art, Science, Technology, Home Economics, Graphics, Information Technology, Fabrics, Library, Staff and Student Toilets (Caroline Springs) | 4 933 |  |  | 2 671 | 2 262 | .. |
| Carronballac P-9 (Boardwalk Campus) – Modernisation – Permanent Facilities for Years 7-9 Including General Purpose Classrooms, Art, Science, Technology, Graphics, Information Technology, Fabrics, Library, Music, Home Economics, Physical Education, Staff Administration, Lockers, Student Toilets (Point Cook) | 6 973 |  |  | 3 761 | 3 212 | .. |
| Cheltenham Secondary College – Modernisation – Stage 3 – Staff Administration, Science, Canteen, Technology (Cheltenham) | 3 858 |  |  | 3 745 | 113 | .. |
| Coburg Senior High School – Modernisation – Arts, Music, Drama (Coburg) | 3 095 |  |  | 2 173 | 922 | .. |
| Colac Regeneration – Regeneration – Colac College and Colac High School (Colac) | 5 000 |  |  | 1 269 | 3 731 | .. |
| Community Facilities Fund (Various) | 29 500 |  |  | 26 916 | 2 584 | .. |
| Craigieburn North P-12 – New School – Stage 1 (Craigieburn) |  | 7 850 |  | 3 573 | 4 277 | .. |
| Cranbourne West Primary School – Modernisation – General Purpose Classrooms, Physical Education, Staff Administration, Canteen, Student Toilets (Cranbourne) | 5 083 |  |  | 2 258 | 2 825 | .. |
| Dandenong Regeneration – Regeneration – Dandenong High School, Cleeland Secondary College and Doveton Secondary College (Dandenong) | 9 970 |  |  | 2 443 | 7 527 | .. |
| Drouin Secondary College – Modernisation – Media Classroom, Library, Student Lockers (Drouin) | 1 930 |  |  | 789 | 1 141 | .. |
| Drouin West Primary School – Secure the Future of Small Rural Schools – Relocatable Classrooms Replacement (Drouin West) | 2 000 |  |  | 217 | 1 783 | .. |
| East Doncaster Secondary College – Modernisation – General Purpose Classrooms, Fabrics, Home Economics, Science, Canteen, Student Toilets, Staff Work Space, Technology, Lockers (Doncaster East) | 6 393 |  |  | 4 060 | 2 333 | .. |
| Echuca Amalgamation – School Reorganisation – Planning (Echuca) | 500 |  |  | 88 | 412 | .. |
| Echuca College – Modernisation – Senior School Neighbourhood, Science, Student Resource Centre, Canteen, Student Amenities (Echuca) | 5 278 |  |  | 821 | 4 457 | .. |
| Elsternwick Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Library, Staff Work Space, Staff and Student Toilets (Brighton) | 4 373 |  |  | 2 737 | 1 636 | .. |
| Epping North East Primary School – New and Replacement – New School (Epping North) | 6 968 |  |  | 6 471 | 497 | .. |
| Euroa Secondary College – Modernisation – Technology, Science, Art, Library and Staff Administration (Euroa) | 3 903 |  |  | 1 986 | 1 917 | .. |
| Fitzroy High School – Modernisation – New Centre for Victorian Certificate of Education Students (Fitzroy North) |  | 3 500 |  | 1 496 | 2 004 | .. |
| Flora Hill Secondary College – Planning (Bendigo) | 1 000 |  |  | 461 | 539 | .. |
| Geelong South Primary School – Modernisation – Library, Staff Administration, Canteen, Student Toilets, Multi-Purpose Room (Geelong) | 2 120 |  |  | 1 028 | 1 092 | .. |
| Gembrook Primary School – Modernisation – Stage 2 – General Purpose Classrooms, Library, Staff Administration, Canteen, Students Toilets (Gembrook) | 2 652 |  |  | 2 453 | 199 | .. |
| Gladesville Primary School – Modernisation – General Purpose Classrooms, Library, Administration and Multi-Purpose Room, Canteen (Kilsyth) | 2 813 |  |  | 2 431 | 382 | .. |
| Glendal Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Music, Library, Canteen, Student Toilets (Glen Waverley) | 5 660 |  |  | 3 790 | 1 870 | .. |
| Greenhills Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Student and Staff Toilets (Greensborough) | 4 553 |  |  | 4 003 | 550 | .. |
| Grevillea Park Primary School – Replacement School – Building Futures – Stage 1 – School Renewal/Replacement P-8 (Wendouree West) | 5 145 |  |  | 5 000 | 145 | .. |
| Grovedale Secondary College – Modernisation – General Purpose Classrooms, Technology, Music, Art 2D and 3D, Graphics, Seminar, Student Toilets, Locker Space (Grovedale) | 2 723 |  |  | 2 633 | 89 | .. |
| Harcourt Valley Primary School – Secure the Future of Small Rural Schools – Relocatable Classrooms Replacement (Harcourt) | 2 000 |  |  | 155 | 1 845 | .. |
| Hobson’s Bay Primary School – Accelerated Modernisation – General Purpose Classrooms, Staff Administration, Multi Purpose, Library, Canteen, Student Toilets (Newport) | 2 770 |  |  | 177 | 2 593 | .. |
| Inverleigh Primary School – Modernisation – Library, Staff/Administration, First Aid Room, Staff Toilets (Inverleigh) | 1 153 |  |  | 638 | 515 | .. |
| Karingal Park Secondary College – Modernisation – General Purpose Classrooms, Commerce, Information Technology, Library, Home Economics, Administration (Frankston) | 5 565 |  |  | 2 352 | 3 213 | .. |
| Karoo Primary School – Accelerated Modernisation – General Purpose Classroom, Physical Education, Staff Administration, Library (Rowville) | 2 915 |  |  | 2 816 | 99 | .. |
| Kent Park Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Library (Ferntree Gully) | 4 043 |  |  | 2 328 | 1 715 | .. |
| Kinglake West Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Library, Multi-Purpose Room, Student Toilets (Kinglake West) | 3 163 |  |  | 1 586 | 1 577 | .. |
| Kurnai College – Morwell Campus – Modernisation – General Purpose Classrooms, Arts, Science, Technology, Physical Education, Change/Shower, Toilets, Staff Administration (Morwell) | 4 303 |  |  | 2 091 | 2 212 | .. |
| Kyabram Secondary College – Planning (Kyabram) | 4 000 |  |  | 14 | 3 986 | .. |
| Laurimar Primary School – New School – Stage 2 (Laurimar/Doreen) | 4 850 |  |  | .. | 4 850 | .. |
| Laurimar Primary School – New and Replacement – New School (Laurimar) | 3 000 |  |  | 2 036 | 964 | .. |
| Laverton Regeneration – Regeneration – Laverton Secondary College, Laverton Primary School and Laverton Plains Primary School (Laverton) | 5 660 |  |  | 1 861 | 3 799 | .. |
| Leongatha – Modernisation – Stage 1 – Special School and Further Planning (Leongatha) |  | 4 961 |  | 4 288 | 673 | .. |
| Lethbridge Primary School – Secure the Future of Small Rural Schools – Relocatable Classrooms Replacement (Lethbridge) | 2 000 |  |  | 155 | 1 845 | .. |
| Little River Primary School – Relocatable School Buildings – General Purpose Classrooms (Little River) | 1 663 |  |  | 1 334 | 329 | .. |
| Macclesfield Primary School – Modernisation – General Purpose Classrooms, Library, Staff Work Space, Student Toilets (Macclesfield) | 3 193 |  |  | 2 282 | 911 | .. |
| Maribyrnong Secondary College – Sports School at Maribyrnong (Maribyrnong) | 10 000 |  |  | 5 154 | 4 846 | .. |
| McKinnon Primary School – Modernisation – General Purpose Classroom, Art/Craft, Library, Physical Education Store, Staff Administration, Shower/Change, Student Toilets (Ormond) | 4 198 |  |  | 4 087 | 110 | .. |
| Mildura South Primary School – Accelerated Modernisation – Music, Library, Physical Education, Staff Work Space, Canteen, First Aid Room, Staff and Students Toilets (Mildura South) | 3 304 |  |  | 3 198 | 106 | .. |
| Mill Park Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Music, Library, Physical Education, Staff Administration, Canteen, Staff and Student Toilets (Mill Park) | 4 433 |  |  | 2 780 | 1 653 | .. |
| Moe (South Street) Primary School – Accelerated Modernisation – General Purpose Classrooms, Staff Administration, Library, Student Toilets (Moe) | 3 984 |  |  | 3 895 | 89 | .. |
| Monash Special Developmental School – Replacement Schools – Stage 2 – Classrooms (Clayton) | 2 700 |  |  | 608 | 2 092 | .. |
| Mooroopna North Primary School – Secure the Future of Small Rural Schools – Relocatable Classrooms Replacement (Mooroopna) | 2 500 |  |  | 155 | 2 345 | .. |
| Mount Waverley Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Library, Student Toilets (Mount Waverley) | 6 343 |  |  | 2 260 | 4 083 | .. |
| New Gisborne Primary School – Modernisation – General Purpose Classrooms, Music, Library, Physical Education, Canteen, Student Toilets (New Gisborne) | 2 873 |  |  | 2 310 | 563 | .. |
| North Melbourne Primary School – Modernisation – Physical Education, Canteen, Student Toilets, Refurbishment Works (North Melbourne) | 2 153 |  |  | 294 | 1 859 | .. |
| North Shore Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Library, Multi-Purpose Room, Student Toilets (Norlane) | 2 910 |  |  | 1 497 | 1 413 | .. |
| Oberon High School – Modernisation – Arts, Technology, Administration (Belmont) |  | 1 783 |  | 1 089 | 694 | .. |
| Pakenham Lakeside Primary School – New School (Pakenham) | 7 850 |  |  | 2 938 | 4 912 | .. |
| Pakenham Secondary College – Modernisation – Stage 3 – General Purpose Classrooms, Arts 2D and 3D, Fabrics, Graphics, Science, Technology, Lockers, Student Toilets (Pakenham) | 6 073 |  |  | 5 544 | 529 | .. |
| Parkdale Secondary College – Modernisation – General Purpose Classrooms, Science, Staff Administration, Resource Centre (Mordialloc) | 8 913 |  |  | 3 497 | 5 416 | .. |
| Pembroke Secondary College – Replacement School – Building Futures – Planning – Consolidation (Mooroolbark) | 1 000 |  |  | 802 | 198 | .. |
| Point Cook Senior Secondary College – New School – Stage 2 (Point Cook) | 6 850 |  |  | 690 | 6 160 | .. |
| Point Lonsdale Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Library, Staff Administration, Canteen, Staff and Student Toilets (Point Lonsdale) | 4 063 |  |  | 2 895 | 1 169 | .. |
| Roberts McCubbin Primary School – Modernisation – General Purpose Classrooms, Art/Craft, Music, Library, Physical Education, Staff Administration, Canteen (Box Hill South) | 6 192 |  |  | 2 398 | 3 794 | .. |
| Rockbank Primary School – Replacement School (Rockbank) | 726 |  |  | 222 | 504 | .. |
| Rural Learning Centre – Investing In Excellence – Rural Learning Centre (Glenormiston) | 2 608 |  |  | 947 | 1 661 | .. |
| Rural Learning Centre – Modernisation – Investing In Excellence – Rural Learning Centre (Rural) |  |  | 1 000 | 247 | 753 | .. |
| Sale College (McAlister campus) – Modernisation – Technology, Computer Pod, Staff Administration (Sale) | 953 |  |  | 805 | 148 | .. |
| Science Rooms Redevelopment (Various) | 3 300 |  |  | 1 000 | 2 300 | .. |
| Select Entry Schools – Planning (Various) | 1 000 |  |  | 500 | 500 | .. |
| Skene Street School – Replacement Schools (Stawell) | 5 000 |  |  | 743 | 4 257 | .. |
| Tarneit School – New and Replacement – New School – Stage 2 (Tarneit) | 6 000 |  |  | 4 265 | 1 735 | .. |
| Tate Street Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Student and Staff Toilets, Library (Geelong East) | 1 540 |  |  | 860 | 680 | .. |
| Technical Wings and Trade Equipment for Government Schools (Various) | 50 000 |  |  | 15 000 | 1 000 | 34 000 |
| Toora Primary School – Secure the Future of Small Rural Schools – Relocatable Classrooms Replacement (Toora) | 2 500 |  |  | 164 | 2 336 | .. |
| Torquay P-9 – Modernisation – Permanent Facilities for Years 7-9 including Classrooms, Art, Science, Technology, Home Economics, Staff Work Space, Student Toilets (Torquay) | 6 613 |  |  | 2 323 | 4 290 | .. |
| Traralgon Secondary College – West Campus – Modernisation – Technology, General Purpose Classrooms, Music, Art 2D and 3D, Graphics, Home Economics, Counselling/Interview, Lockers, Student and Staff Toilets (Traralgon) |  | 3 376 |  | 3 252 | 124 | .. |
| Trentham District Primary School – Secure the Future of Small Rural Schools – Relocatable Classrooms Replacement (Trentham) | 2 500 |  |  | 155 | 2 345 | .. |
| Ultranet (Various) | 60 458 |  |  | 20 956 | 10 956 | 28 546 |
| Upwey High School – Modernisation – General Purpose Classrooms, Art, Lockers (Upwey) | 4 360 |  |  | 1 148 | 3 212 | .. |
| Various Schools – Investing In Excellence – Investing In Excellence/Leading Schools Fund (Various) | 9 300 |  |  | 9 207 | 93 | .. |
| Various Schools – Leading Schools Fund – Modernisation (Various) | 12 120 |  |  | 9 335 | 2 785 | .. |
| Vermont Secondary College – Modernisation – Library, General Purpose Classrooms, Senior Student Centre, Multi-Media Centre, Staff and Student Toilets, Staff Work Space (Vermont) | 6 103 |  |  | 1 065 | 5 038 | .. |
| VicSmart Broadband Network for Government Schools (Various) | 7 300 |  |  | 5 200 | 2 100 | .. |
| Victorian College of the Arts Secondary School (VCASS) and Other Projects – Replacement School (Southbank) | 20 000 |  |  | 8 728 | 11 271 | .. |
| Wangaratta Regeneration – Regeneration – Wangaratta High School and Ovens College (Wangaratta) | 4 630 |  |  | 2 451 | 2 179 | .. |
| Werribee Secondary College – Modernisation – Science, General Purpose Classrooms, Music, Commerce, Library, Arts, Administration (Werribee) | 6 760 |  |  | 1 073 | 5 687 | .. |
| Western Heights Regeneration – Regeneration – Western Heights Secondary College – Three Campuses (Hamlyn Heights) | 13 770 |  |  | 194 | 13 576 | .. |
| Wyndham Vale P-12 (Manor Lakes) – New School – Stage 1 (Wyndham Vale) | 6 900 |  |  | 2 528 | 4 372 | .. |
| Total existing projects | 669 499 |  |  | 315 585 | 287 631 | 66 284 |

Source: Department of Education and Early Childhood Development

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

Department of Education and Early Childhood Development

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Alberton Primary School – Secure the Future of Small Rural Schools (Alberton) | 2 000 |  | .. | 615 | 1 385 |
| Altona/Bayside Regeneration – Altona College and Altona West Primary School – Stage 2 (Altona) | 5 000 |  | .. | 214 | 4 786 |
| Altona/Bayside Regeneration – Bayside Secondary College (Altona North Campus) and Altona Gate Primary School – Stage 2 (Altona North) | 5 000 |  | .. | 1 347 | 3 653 |
| Anglesea Primary School – Replacement School (Anglesea) | 5 000 |  | .. | 2 378 | 2 622 |
| Bacchus Marsh Primary School – Modernisation – Library, Music, General Purpose Classrooms, Student Toilets (Bacchus Marsh) | 6 000 |  | .. | 3 265 | 2 735 |
| Bass Coast Specialist School – Replacement School (Wonthaggi) | 5 500 |  | .. | 3 786 | 1 714 |
| Bendigo Education Plan – Eaglehawk – Eaglehawk Secondary College – Stage 2 (Eaglehawk) |  | 12 000 | .. | 4 380 | 7 620 |
| Bendigo Education Plan – Flora Hill – Flora Hill and Golden Square Secondary College (Flora Hill) | 10 000 |  | .. | 2 808 | 7 192 |
| Bendigo Education Plan – Kangaroo Flat – Kangaroo Flat Secondary College – Stage 2 (Kangaroo Flat) | 11 000 |  | .. | 2 182 | 8 818 |
| Bendigo Education Plan – Weeroona Secondary College (Bendigo) |  | 8 100 | .. | 3 774 | 4 326 |
| Better Schools Today 2008-09 (Various) | 35 000 |  | .. | 35 000 | .. |
| Broadmeadows Regeneration – Blair Street – Broadmeadows Secondary College and Broadmeadows Primary School – Stage 2 (Broadmeadows) | 6 000 |  | .. | 1 122 | 4 878 |
| Broadmeadows Regeneration – Dimboola Road – Meadowfair North Primary School, Jacana Primary School, Broadmeadows West Primary School, Westmeadows Heights Primary School (Broadmeadows) | 7 000 |  | .. | .. | 7 000 |
| Broadmeadows Regeneration – Hume Senior Campus – Broadmeadows Secondary College, Hillcrest Secondary College, Erinbank Secondary College – Stage 1 (Westmeadows) | 12 000 |  | .. | 1 128 | 10 872 |
| Buln Buln Primary School – Secure the Future of Small Rural Schools (Buln Buln) | 2 000 |  | .. | 349 | 1 651 |
| Caroline Springs College – Springside Campus – New Schools in Growth Areas – Stage 2 (Caroline Springs) | 7 000 |  | .. | 1 940 | 5 060 |
| Carrum Primary School – Modernisation – Administration, Plastering, Library, Art, Student Toilets (Carrum) | 4 000 |  | .. | 989 | 3 011 |
| Chaffey Secondary College – Modernisation – Music/Drama, Graphics, Art, Fabrics, General Purpose Classrooms, Physical Education, Administration – Stage 2 (Mildura) | 6 100 |  | .. | 3 349 | 2 751 |
| Colac Regeneration – Colac College and Colac High School – Stage 2 (Colac) | 8 000 |  | .. | 953 | 7 047 |
| Colac South West Primary School – Modernisation – General Purpose Classrooms, Library, Administration, Art and Multi-Purpose Room (Colac) |  | 4 200 | .. | 2 751 | 1 449 |
| Craigieburn North P-12 – New Schools in Growth Areas – Stage 2 (Craigieburn) | 7 000 |  | .. | 3 482 | 3 518 |
| Dandenong – Regeneration – Dandenong High, Cleeland Secondary College and Doveton Secondary College – Stage 2 (Dandenong) | 10 000 |  | .. | 933 | 9 067 |
| Darnum Primary School – Secure the Future of Small Rural Schools (Darnum) | 2 000 |  | .. | 349 | 1 651 |
| Daylesford Secondary College – Modernisation – General Purpose Classrooms, Art and Administration (Daylesford) | 3 000 |  | .. | 1 754 | 1 246 |
| Doncaster Secondary College – Modernisation – General Purpose Classrooms, Arts, Technology, Staff/Administration, Graphics, Information Technology, Fabrics (Doncaster) | 6 600 |  | .. | 2 794 | 3 806 |
| Dromana Secondary College – Modernisation – Technology, Fabrics, Information Technology and Staff Area (Dromana) | 4 000 |  | .. | 2 483 | 1 517 |
| Eagle Point Primary School – Secure the Future of Small Rural Schools (Eagle Point) | 2 000 |  | .. | 349 | 1 651 |
| Elisabeth Murdoch College – Modernisation – General Purpose Classrooms, Information Technology, Home Economics, Science, Music/Drama, Arts, Redevelop Staff Car Parking, Ground Development (Langwarrin) | 8 600 |  | .. | 5 002 | 3 598 |
| Eltham Primary School – Modernisation – General Purpose Classrooms, Art, Craft, Music, Canteen, Student Toilets (Eltham) | 4 000 |  | .. | 804 | 3 196 |
| Glen Waverley Secondary College – Modernisation – General Purpose Classrooms, Home Economics, Fabrics, Graphics, Staff Work Space, Canteen (Glen Waverley) | 9 300 |  | .. | 2 704 | 6 596 |
| Grahamvale Primary School – Secure the Future of Small Rural Schools (Grahamvale) | 2 000 |  | .. | 905 | 1 095 |
| Hartwell Primary School – Modernisation – General Purpose Classrooms (Camberwell) | 2 800 |  | .. | 938 | 1 862 |
| Horsham West – Haven Primary School (Haven Campus) – Secure the Future of Small Rural Schools (Haven) | 2 000 |  | .. | 349 | 1 651 |
| John Monash Science School – Monash University, Clayton Campus (Clayton) | 20 000 |  | .. | 14 000 | 6 000 |
| Koroit and District Primary School – Modernisation – General Purpose Classrooms Library, Staff Administration (Koroit) | 2 000 |  | .. | 1 560 | 440 |
| Lara Secondary College – Modernisation – General Purpose Classrooms, Library, Information Technology, Science Technology, Art, Administration, Canteen (Lara) | 6 200 |  | .. | 3 600 | 2 600 |
| Maffra Primary School – Modernisation – General Purpose Classrooms, Physical Education, Art Music, Administration, Canteen and Demolition Works (Maffra) | 4 100 |  | .. | 2 876 | 1 224 |
| Maffra Secondary College – Modernisation – Classrooms, Music, Art, Graphics, Information Technology, Administration and Student Toilets – Stage 2 (Maffra)(b) | 5 300 |  | .. | 2 700 | 2 600 |
| McKinnon Secondary College – Modernisation – General Purpose Classrooms and Administration (Mckinnon) | 6 000 |  | .. | 840 | 5 160 |
| Mount Evelyn Primary School – Modernisation – General Purpose Classrooms, Physical Education, Art, Library, Music, Administration, Canteen (Mount Evelyn) | 6 300 |  | .. | 3 537 | 2 763 |
| Nar Nar Goon Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Art, Library, Multi Purpose, Canteen (Nar Nar Goon) | 4 400 |  | .. | 3 515 | 885 |
| New Land for the Provision of New and Replacement Schools (Various) | 30 000 |  | .. | 30 000 | .. |
| Newham Primary School – Secure the Future of Small Rural Schools (Newham) | 2 000 |  | .. | 349 | 1 651 |
| Pascoe Vale North Primary School – Modernisation – Administration, General Purpose Classrooms, Art, Library, Student Toilets (Pascoe Vale) | 3 100 |  | .. | 2 211 | 889 |
| Port Melbourne Primary School – Modernisation – General Purpose Classrooms, Staff Administration, Art, Music, Library, Multi Purpose, Canteen (Port Melbourne) | 4 700 |  | .. | 3 078 | 1 622 |
| Princes Hill Primary School – Modernisation – Administration, General Purpose Classrooms, Physical Education, Music, Canteen (Carlton North) | 5 700 |  | .. | 2 654 | 3 046 |
| Relocatable Classroom Renewal (Various) | 26 000 |  | .. | 4 200 | 21 800 |
| Reservoir West Primary School – Modernisation – Administration, General Purpose Classrooms, Art, Physical Education, Music, Canteen (Reservoir) | 3 600 |  | .. | 2 238 | 1 362 |
| Select Entry Schools – Berwick – Monash University, Berwick Campus (Berwick) | 9 500 |  | .. | 5 500 | 4 000 |
| Select Entry Schools – Wyndham Vale (Wyndham Vale) | 9 500 |  | .. | 4 500 | 5 000 |
| Sunshine East Regeneration – Sunshine East Primary School, Braybrook Primary School, Sunvale Primary School (Sunshine) | 7 000 |  | .. | 4 413 | 2 587 |
| Surrey Hills Primary School – Modernisation – General Purpose Classrooms, Art, Library, Staff Administration, Student Toilets (Surrey Hills) | 6 200 |  | .. | 3 208 | 2 992 |
| Upper Plenty Primary School – Secure the Future of Small Rural Schools (Upper Plenty) | 2 000 |  | .. | 349 | 1 651 |
| Wallan Secondary College – New Schools in Growth Areas – Stage 3 (Wallan) | 8 000 |  | .. | 2 597 | 5 403 |
| Wangaratta West Primary School – Modernisation – Music, General Purpose Classrooms, Staff Administration, Physical Education, Canteen (Wangaratta) | 3 000 |  | .. | 2 140 | 860 |
| Wellington Secondary College – Modernisation – General Purpose Classrooms, Music/Drama, Art, Graphics, Fabrics, Home Economics, Technology, Physical Education, Canteen (Mulgrave) | 5 900 |  | .. | 1 174 | 4 726 |
| Woady Yaloak Primary School – Snake Valley Campus – Secure the Future of Small Rural Schools (Snake Valley) | 2 000 |  | .. | 349 | 1 651 |
| Wodonga Primary School – Modernisation – General Purpose Classrooms, Art, Staff Administration, Student Toilets (Wodonga) | 4 100 |  | .. | 2 486 | 1 614 |
| Wodonga South Primary School – Replacement School (Wodonga) | 8 500 |  | .. | 296 | 8 204 |
| Wyndham Vale P-9 (Manor Lakes) – New Schools in Growth Areas – Stage 2 (Wyndham Vale) | 7 000 |  | .. | 3 482 | 3 518 |
| Total new projects | 426 300 |  | .. | 203 023 | 223 277 |
| Total Education and Early Childhood Development projects | 1 095 799 |  | 315 585 | 490 654 | 289 560 |

Source: Department of Education and Early Childhood Development

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	Since the 2007-08 Budget, the government has provided an additional $5.3 million for Stage 2 redevelopment at Maffra Secondary College.

# Department of Human Services

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Aged Care Land Bank Pilot (Metropolitan) | 4 800 |  | 4 375 | 425 | .. |
| Air Ambulance Victoria and Victoria Police Air Wing Co-location – Construction (Essendon) | 3 700 |  | 1 337 | 2 363 | .. |
| Air Ambulance Victoria Fixed Wing Facility – Construction (Essendon) | 8 340 |  | 2 074 | 5 526 | 740 |
| Ambulance Development Plan 2006-08 (Statewide) | 1 775 |  | 1 638 | 137 | .. |
| Austin Elective Surgery Centre Heidelberg Repatriation Hospital Construction (Heidelberg) | 8 000 |  | 4 056 | 3 944 | .. |
| Bairnsdale Regional Health Service – Emergency Department (Bairnsdale) |  | 5 000 | 4 880 | 120 | .. |
| Ballarat Hospital Redevelopment (Ballarat) | 4 500 |  | 1 785 | 715 | 2 000 |
| Barwon Health Geelong Hospital Masterplan (Geelong) | 2 000 |  | 209 | 1 791 | .. |
| Bendigo Health Care Group Bendigo Hospital Planning and Development (Bendigo) | 2 000 |  | 15 | 1 485 | 500 |
| Box Hill Hospital Outpatients and Dialysis Centre and Associated Works (Box Hill) | 38 200 |  | 35 798 | 2 402 | .. |
| Brunswick Human Services Precinct Bouverie Centre Relocation (Brunswick) | 5 000 |  | 4 218 | 782 | .. |
| Calvary Health Care Bethlehem Interim Works (Caulfield South) | 1 600 |  | 1 316 | 284 | .. |
| Casey Aged Care Development (Doveton) | 33 300 |  | 19 966 | 13 334 | .. |
| Caulfield General Medical Centre Logistics Building and Associated Works (Caulfield) | 23 500 |  | 20 911 | 2 589 | .. |
| Caulfield General Medical Centre Redevelopment Stage 2 (Caulfield) | 28 000 |  | 1 650 | 7 850 | 18 500 |
| Colac Area Health, Polwarth Nursing Home – Residential Aged Care Strategy (Colac) | 13 600 |  | 13 431 | 169 | .. |
| Community Facility Redevelopment (Statewide) | 5 000 |  | 735 | 4 265 | .. |
| Community Health and Mental Health Redevelopment Stage 2 (Warragul) |  | 6 220 | 4 953 | 1 267 | .. |
| Disability Services Strategic Refurbishment and Replacement Program Stage 2 (Statewide) | 15 000 |  | 3 524 | 8 176 | 3 300 |
| Doutta Galla Kensington Community Health Centre Planning and Development (Kensington) | 1 000 |  | 34 | 966 | .. |
| Eastern Health Central East Community Care Unit (Camberwell) | 6 400 |  | 4 845 | 1 555 | .. |
| Eastern Health Mental Health Redevelopment Stage 1 (Box Hill, Ringwood East) | 32 100 |  | 22 566 | 9 534 | .. |
| Electronic Prescribing in Key Victorian Hospitals (Statewide) | 21 000 |  | 7 400 | 13 600 | .. |
| Ensuring our hospitals are as clean and safe as possible – Equipment (Statewide) | 5 000 |  | 500 | 2 500 | 2 000 |
| Environmental Sustainability Public Hospitals and Aged Care (Statewide) | 3 290 |  | 500 | 1 900 | 890 |
| Fire Risk Management Strategy 2004-05 (Statewide) | 9 000 |  | 8 348 | 652 | .. |
| Frankston Hospital Stage 2 (Operating Theatre Expansion and Critical Care Redevelopment) (Frankston) | 45 000 |  | 6 677 | 12 323 | 26 000 |
| Geelong Hospital Emergency Department Redevelopment (Geelong) | 26 100 |  | 22 899 | 3 201 | .. |
| Geelong Hospital Radiotherapy Service (Geelong) | 16 000 |  | 15 305 | 695 | .. |
| Grace McKellar Centre – Redevelopment Stage 2 (Geelong) | 52 000 |  | 50 678 | 1 322 | .. |
| Grovedale Aged Care Facility Development (Grovedale) | 25 000 |  | 20 226 | 4 774 | .. |
| Health Information and Communication Technology (ICT) Strategy (Statewide) | 138 500 |  | 112 280 | 26 220 | .. |
| Heidelberg Repatriation Hospital Mental Health, Veterans' Gymnasium and Pool – Redevelopment Stage 1 (Heidelberg) |  | 9 000 | 1 535 | 7 465 | .. |
| Heidelberg Repatriation Hospital Veterans' Mental Health Facility – Preliminary Works (Heidelberg) | 1 500 |  | .. | 1 500 | .. |
| Helping Working Families: Giving Children the Best Start in Life – Equipment (Statewide) | 1 200 |  | .. | 1 200 | .. |
| Intensive Care Service Expansion (Statewide) | 3 000 |  | 1 724 | 1 276 | .. |
| Kew Residential Services Redevelopment (Kew) | 86 500 |  | 80 669 | 5 831 | .. |
| Kingston Centre Kitchen Upgrade and Associated Works (Heatherton) | 26 700 |  | 11 487 | 15 213 | .. |
| Koori Youth Alcohol and Drug Healing Centre Development (Rural) | 3 700 |  | 213 | 1 583 | 1 904 |
| Leongatha Hospital Campus Stage 1 Residential Aged Care (Leongatha) | 10 000 |  | 3 501 | 5 999 | 500 |
| Maroondah Hospital Expansion Stage 1 (Ringwood East) | 8 000 |  | 3 918 | 3 082 | 1 000 |
| Medical Equipment Program (Statewide) | 47 700 |  | 47 333 | 367 | .. |
| Medical Equipment Replacement Program (Statewide) | 145 000 |  | 35 340 | 39 660 | 70 000 |
| Mental Health Services for Kids and Youth – Development Stage 2 (Footscray) | 6 664 |  | 5 721 | 943 | .. |
| Metropolitan and Rural Ambulance Services – Station Upgrades (Statewide) | 10 030 |  | 2 162 | 5 668 | 2 200 |
| Monash Medical Centre Children's Facility Planning and Development (Clayton) | 2 000 |  | 435 | 1 565 | .. |
| Murtoa Community Health Centre Redevelopment (Murtoa) | 2 500 |  | 615 | 1 885 | .. |
| Nathalia District Hospital and Aged Care Redevelopment (Nathalia) | 18 000 |  | 2 372 | 5 528 | 10 100 |
| North Richmond Community Health Centre Relocation (North Richmond) | 19 000 |  | 4 286 | 11 963 | 2 751 |
| Northeast Health Wangaratta – Nursing Home Redevelopment (Wangaratta) | 10 585 |  | 9 966 | 619 | .. |
| Northern Hospital – Mental Health Expansion and Short Stay Unit Construction (Epping) | 27 900 |  | 1 491 | 4 109 | 22 300 |
| Northern Hospital Redevelopment Stage 2a (Epping) | 24 500 |  | 23 269 | 1 231 | .. |
| Peninsula Community Health Service Redevelopment (Hastings) | 13 000 |  | 3 177 | 6 023 | 3 800 |
| Placement and Support Residential Facility Renewal Strategy Stage 6 (Statewide) | 14 200 |  | 6 906 | 6 094 | 1 200 |
| Prevention and Recovery Care Services Stage 1 – Construction (Metropolitan) | 9 640 |  | 1 496 | 7 144 | 1 000 |
| Rochester and Elmore District Health Service – Rochester Theatre and Hospital Redevelopment (Rochester) |  | 21 700 | 10 144 | 6 960 | 4 596 |
| Royal Melbourne Hospital Brickwork Rectification (Parkville)(b) | 28 475 |  | 25 662 | 1 813 | 1 000 |
| Royal Melbourne Hospital Emergency Department Redevelopment (Parkville) | 56 300 |  | 25 456 | 23 844 | 7 000 |
| Rural Ambulance Victoria Communications Infrastructure Upgrade Stage 3 (Rural) | 6 800 |  | 5 097 | 1 703 | .. |
| Shepparton Mental Health Redevelopment (Ambermere) | 6 500 |  | 6 039 | 461 | .. |
| Short Stay Units, Day Treatment Centres and Medi-Hotels – Construction (Statewide) | 4 000 |  | 856 | 3 144 | .. |
| St Vincents Orthopaedic Surgery Centre – Construction (Fitzroy) | 7 000 |  | .. | 7 000 | .. |
| Statewide Infrastructure Renewal Program (Statewide) | 80 000 |  | 19 809 | 20 191 | 40 000 |
| Stawell Health and Community Centre Redevelopment (Stawell) | 20 000 |  | 2 578 | 11 922 | 5 500 |
| Sunshine Hospital Expansion and Redevelopment Stage 1 (Sunshine) | 20 000 |  | 6 163 | 13 137 | 700 |
| Super Clinics (Metropolitan) | 42 000 |  | 40 753 | 1 247 | .. |
| The Alfred Hospital Intensive Care Unit Redevelopment (Prahran) | 20 240 |  | 19 188 | 1 052 | .. |
| Victorian Respiratory Support Service (Thornbury) | 7 100 |  | 5 221 | 1 879 | .. |
| Warracknabeal Nursing Home Stage 1 Redevelopment (Warracknabeal) | 21 800 |  | 20 027 | 1 773 | .. |
| Warrnambool Hospital Redevelopment Stage 1 (Warrnambool) | 16 000 |  | 5 540 | 8 460 | 2 000 |
| Western Hospital Redevelopment Stage 1 (Footscray) | 24 800 |  | 4 043 | 3 057 | 17 700 |
| Total existing projects | 1 472 959 |  | 843 321 | 380 457 | 249 181 |

Source: Department of Human Services

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	The Total Estimated Investment has been revised downwards by $2.6 million. Surplus funds will be used to complete the Royal Melbourne Hospital kitchen decanting works.

Department of Human Services

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Aged Care Land Bank Stage 3 (Metropolitan) | 2 500 |  | .. | 2 500 | .. |
| Alexandra District Hospital Redevelopment – Planning and Development (Alexandra) | 1 000 |  | .. | 1 000 | .. |
| Alfred Centre Stage 2 (Prahran) | 17 000 |  | 14 896 | 2 104 | .. |
| Ambulance Service Strategy (Statewide) | 7 700 |  | .. | 5 600 | 2 100 |
| Ambulance Vehicle Replacement (Statewide) | 600 |  | .. | 600 | .. |
| Ballarat Hospital – Mental Health Redevelopment (Ballarat) | 5 500 |  | .. | 500 | 5 000 |
| Bendigo Hospital Emergency Department Upgrade (Bendigo) | 9 500 |  | .. | 3 500 | 6 000 |
| Bendigo Residential Aged Care Facility (Stella Anderson Replacement) (Bendigo) | 13 600 |  | .. | 2 500 | 11 100 |
| Box Hill Hospital – Infrastructure Upgrade (Box Hill) | 8 500 |  | .. | 2 000 | 6 500 |
| Casey Hospital Special Care Nursery Expansion (Doveton) | 4 200 |  | .. | 500 | 3 700 |
| Dandenong Hospital Emergency Department Redevelopment (Dandenong) | 25 000 |  | .. | 900 | 24 100 |
| Dandenong Hospital Mental Health Redevelopment and Expansion – Planning (Dandenong) | 3 000 |  | .. | 2 000 | 1 000 |
| Frankston Hospital Maternity Service Expansion (Frankston) | 5 000 |  | .. | 500 | 4 500 |
| HealthSMART Shared Information and Communication Technology (ICT) Operations (Statewide) | 26 944 |  | .. | 6 736 | 20 208 |
| Heidelberg Repatriation Hospital Mental Health Redevelopment (Heidelberg) | 15 500 |  | .. | 7 300 | 8 200 |
| Hepburn Health Service: Trentham Campus Redevelopment (Trentham) |  | 8 000 | .. | 3 000 | 5 000 |
| Hospital Energy Supply Project (Statewide) | 23 600 |  | .. | 10 000 | 13 600 |
| Kingston Centre Redevelopment Stage 2 (Cheltenham) | 45 000 |  | .. | 2 166 | 42 834 |
| Latrobe Community Health Service – Morwell Redevelopment (Morwell) | 21 000 |  | .. | 2 000 | 19 000 |
| Melton New Dental Chairs (Melton) | 4 900 |  | .. | 1 600 | 3 300 |
| Metropolitan Ambulance Service Station Upgrades (Metropolitan) | 2 100 |  | .. | 2 100 | .. |
| Monash Medical Centre – Clayton Magnetic Resonance Imaging (Clayton) | 4 000 |  | .. | 4 000 | .. |
| Monash Medical Centre – Clayton: Pregnancy Assessment Unit (Clayton) | 4 800 |  | .. | 700 | 4 100 |
| MonashLink Community Health Service Stage 2 (Glen Waverley and Oakleigh) | 1 000 |  | .. | 500 | 500 |
| MonashLink Community Health Service (Ashwood) | 1 300 |  | .. | 520 | 780 |
| New Rural Dental Teaching Chairs (Sunraysia and Wodonga) | 8 100 |  | .. | 2 700 | 5 400 |
| Northern Hospital Maternity Expansion (Epping) | 2 500 |  | .. | 500 | 2 000 |
| Olivia Newton-John Cancer Centre (Heidelberg) | 25 000 |  | .. | 5 000 | 20 000 |
| Parkville Comprehensive Cancer Centre – Planning Funding (Parkville) | 5 000 |  | 413 | 4 587 | .. |
| Prevention and Recovery Care Services (PARCS) Stage 2 (Metropolitan) | 10 360 |  | .. | 2 000 | 8 360 |
| Redevelopment of the Royal Victorian Eye and Ear Hospital – Planning (East Melbourne) | 2 000 |  | .. | 700 | 1 300 |
| Rural Ambulance Victoria Station Upgrades and Service Expansion (Rural) | 4 500 |  | .. | 300 | 4 200 |
| Sunbury Day Hospital (Sunbury) | 14 000 |  | .. | 1 000 | 13 000 |
| Sunshine Hospital Expansion and Redevelopment Stage 2 (Sunshine)(b) | 73 500 |  | .. | 13 300 | 60 200 |
| Warrnambool Hospital Redevelopment Stage 1C (Warrnambool) | 70 100 |  | .. | 4 500 | 65 600 |
| Werribee Mercy Hospital Expansion Stage 1 (Werribee) | 14 000 |  | .. | 500 | 13 500 |
| Total new projects | 490 304 |  | 15 309 | 99 913 | 375 082 |
| Total Human Services projects(c) | 1 963 263 |  | 858 630 | 480 370 | 624 263 |

Source: Department of Human Services

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	The Total Estimated Investment does not include funding contributions from external sources.

(c)	The Total Estimated Investment for the Department of Human Services has been adjusted downwards to reflect delivery of the Royal Children’s Hospital under Partnerships Victoria.

# Department of Innovation, Industry and Regional Development

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Automotive Centre of Excellence – Kangan Batman (Docklands) | 30 000 |  | 1 160 | 10 000 | 18 840 |
| Commonwealth Games Village – Social Housing Component – Construction (Melbourne) | 35 100 |  | 25 385 | 9 715 | .. |
| East Gippsland and Sunraysia Institute of TAFE – Commonwealth Supported Project – Voice Over Internet Protocol Telephony Upgrade (Bairnsdale and Mildura) | 7 000 |  | 6 209 | 791 | .. |
| Gordon Institute – Wool Classing (East Geelong) | 3 000 |  | 170 | 2 830 | .. |
| Goulburn Ovens Institute of TAFE – Commonwealth Supported Project – Upgrade of Trade Facility (Wangaratta) | 400 |  | 18 | 382 | .. |
| Improving TAFE Equipment (Various) | 48 000 |  | 24 000 | 12 000 | 12 000 |
| Nursing Centre of Excellence (Box Hill) |  | 4 500 | 250 | 4 000 | 250 |
| Princes Pier Restoration (Port Melbourne) | 14 000 |  | 2 389 | 11 611 | .. |
| South West Institute of TAFE – Warrnambool Stage 3 Redevelopment (Warrnambool) | 11 000 |  | 1 132 | 2 500 | 7 368 |
| Technical Education Centres (Various) (b) | 32 000 |  | 6 104 | 13 000 | 12 896 |
| Transport and Logistics Centre (Planning) – Wodonga TAFE (Wodonga) | 500 |  | .. | 500 | .. |
| University of Ballarat – Commonwealth Supported Project – Grant Street Bridge Construction (Ballarat) |  | 2 100 | 149 | 1 951 | .. |
| Victoria University – Commonwealth Supported Project – Consolidation of Engineering and ICT (Footscray and Sunshine) | 13 600 |  | 13 498 | 102 | .. |
| William Angliss Institute of TAFE – Commonwealth Supported Project – New Teaching Facility and Campus Redevelopment (Melbourne) | 12 100 |  | 3 035 | 9 065 | .. |
| Total existing projects | 213 300 |  | 83 499 | 78 447 | 51 354 |

Source: Department of Innovation, Industry and Regional Development

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	The expenditure to 30 June 2008 reflects a change in the treatment of funding paid to the Victorian Skills Commission.

Department of Innovation, Industry and Regional Development

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Ballarat University – School of Mines Car Park Redevelopment (Ballarat) | 3 250 |  | .. | 3 000 | 250 |
| Bendigo Institute of TAFE – Charleston Road Campus Redevelopment (Bendigo) |  | 11 000 | .. | 800 | 10 200 |
| Central Gippsland Institute of TAFE – Commonwealth Supported Project – New Campus (Leongatha) | 6 000 |  | .. | 3 400 | 2 600 |
| Chisholm Institute of TAFE – Commonwealth Supported Project – Amenities Upgrade (Berwick) | 2 500 |  | .. | 1 650 | 850 |
| Chisholm Institute of TAFE – Commonwealth Supported Project – Building W Upgrade (Dandenong) | 2 300 |  | .. | 2 300 | .. |
| Chisholm Institute of TAFE – Commonwealth Supported Project – Trade (Automotive and Logistics) Training Centre (Dandenong) | 11 500 |  | .. | 3 650 | 7 850 |
| East Gippsland Institute of TAFE – Commonwealth Supported Project – Learning and Common Centre Redevelopment (Bairnsdale) | 2 800 |  | .. | 900 | 1 900 |
| Geelong Future Cities Master Plan – Cultural Precinct Stage 1 – Construction (Geelong) | 7 865 |  | .. | 1 964 | 5 901 |
| Gordon Institute of TAFE – Commonwealth Supported Project – Campus Redevelopment (East Geelong) | 500 |  | .. | 500 | .. |
| Goulburn Ovens Institute of TAFE – Commonwealth Supported Project – New Primary Industries Centre (Wangaratta) | 8 100 |  | .. | 4 050 | 4 050 |
| Kangan Batman Institute of TAFE – Commonwealth Supported project – Aerospace Industry Training Centre – Planning (Tullamarine) | 250 |  | .. | 250 | .. |
| Noble Park Campus – Commonwealth Supported Project – Demolition of Engineering Workshop (Noble Park) | 300 |  | .. | 300 | .. |
| Northern Melbourne Institute of TAFE – Campus Redevelopment Stage 1 (Epping) | 10 450 |  | .. | 2 950 | 7 500 |
| Northern Melbourne Institute of TAFE – Commonwealth Supported Project – Building Q Redevelopment (Fairfield) | 8 000 |  | .. | 1 750 | 6 250 |
| South West Institute of TAFE – Commonwealth Supported Project – ICT Upgrade (Warrnambool) | 4 000 |  | .. | 4 000 | .. |
| Sunraysia Institute of TAFE – Commonwealth Supported Project – Design, Technology and Information Centre (Mildura) | 500 |  | .. | 500 | .. |
| Swinburne Institute of TAFE – Commonwealth Supported Project – WA and WJ Refurbishment (Wantirna) | 2 200 |  | .. | 2 200 | .. |
| TAFE Student Management System – Replacement (Statewide) | 1 730 |  | .. | 1 730 | .. |
| Victoria University – Commonwealth Supported Project – New Trade Centre-Planning (Sunshine) | 750 |  | .. | 250 | 500 |
| William Angliss Institute of TAFE – Commonwealth Supported Project – Building E External Facade Upgrade (Melbourne) | 600 |  | .. | 600 | .. |
| William Angliss Institute of TAFE – Commonwealth Supported Project – Training Kitchen Upgrades (Melbourne) | 3 000 |  | .. | 2 000 | 1 000 |
| Wodonga Institute of TAFE – National Logistics and Driver Skills Training Centre (Wodonga) | 15 500 |  | .. | 4 000 | 11 500 |
| Total new projects | 103 095 |  | .. | 42 744 | 60 351 |
| Total Innovation, Industry and Regional Development projects | 316 395 |  | 83 499 | 121 191 | 111 705 |

Source: Department of Innovation, Industry and Regional Development

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

# Department of Justice

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| 10 Year Prison Cell Safety Project – Upgrade safety of cells and buildings (Statewide) | 40 144 | 36 665 | 3 479 | .. |
| Ararat Police Station (Police Stations Program 2007-08) – Construction (Ararat)(b) | 13 500 | 768 | 5 982 | 6 750 |
| Bayside Police Station (Police Stations Program 2007-08) – Construction (Sandringham)(b) | 13 000 | 581 | 5 925 | 6 494 |
| Better Pathways – Women's Offending – Asset Enhancement (Metropolitan) | 8 654 | 8 124 | 530 | .. |
| Box Hill Police Station (Police Stations Program 2007-08) – Construction (Box Hill)(b) | 16 500 | 1 609 | 6 636 | 8 255 |
| Brunswick and Collingwood Police Complexes – Upgrades (Brunswick and Collingwood) | 12 206 | 9 595 | 2 611 | .. |
| Carlton-North Melbourne Police Station – Construction (Carlton-North Melbourne) | 15 900 | 8 324 | 7 576 | .. |
| Carrum Downs Police Station (Police Stations Program 2007-08) – Construction (Carrum Downs)(b) | 14 000 | 906 | 6 075 | 7 019 |
| Community Based Corrections Facilities – Construction (Melbourne)(c) | 9 208 | 9 123 | 85 | .. |
| Crime Department Upgrade – Construction (Melbourne) | 8 000 | 3 000 | 5 000 | .. |
| Diversionary Program for Adult Aboriginal Offenders – Construction (Statewide)(d) | 6 160 | 5 328 | 832 | .. |
| Foster Police Station (Police Stations Program 2007-08) – Construction (Foster)(b) | 1 500 | 72 | 676 | 752 |
| Hastings Police Station (Priority Projects – Rural/Regional Police Station) – Construction (Hastings)(e) | 2 500 | 619 | 1 881 | .. |
| Improving VicSES Facilities and Infrastructure – Construction/ Replacement (Statewide) | 2 000 | 1 850 | 150 | .. |
| Increased Police Car Fleet – Asset Enhancement (Statewide) | 2 340 | .. | 971 | 1 369 |
| Integrated Courts Management System (ICMS) – Asset Enhancement (Statewide) | 32 255 | 23 100 | 9 155 | .. |
| Justice System Major Crimes Resourcing Needs – Asset Enhancement (Statewide) | 13 646 | 12 827 | 819 | .. |
| Kyneton Police Station (Police Stations Program 2007-08) – Construction (Kyneton)(b) | 11 000 | 209 | 5 295 | 5 496 |
| Lilydale Police Station – Construction (Lilydale) | 13 500 | 1 956 | 11 544 | .. |
| Macleod Forensic Capability – Asset Enhancement (Metropolitan) | 1 696 | 1 126 | 570 | .. |
| Melbourne Legal Precinct Master Plan – Construction (Melbourne)(f) | 35 313 | 22 503 | 12 810 | .. |
| Modernising Coronial Services – Construction (Melbourne) | 31 676 | 1 000 | 6 000 | 24 676 |
| Moorabbin Court Complex – Construction (Moorabbin)(g) | 28 051 | 27 598 | 453 | .. |
| North Wyndham Police Station – Construction (North Wyndham) | 6 540 | 1 596 | 4 944 | .. |
| Organised Crime and Counter Terrorism – Asset Enhancement (Statewide)(h) | 15 366 | 15 198 | 168 | .. |
| Ouyen Police Station (Police Stations Program 2007-08) – Construction (Ouyen)(b) | 1 000 | 66 | 433 | 501 |
| Putting Children First: Promoting Child Safe Workplaces – Fitout/ Equipment (Statewide) | 1 345 | 394 | 951 | .. |
| Reducing Court Delays – Construction (Melbourne) | 1 910 | 1 834 | 76 | .. |
| Road Safety Enforcement – Road Policing Asset Enhancement (Statewide) | 2 220 | 1 900 | 310 | 10 |
| Sexual Assault Reform – Asset Enhancement (Statewide)(i) | 3 558 | 3 062 | 496 | .. |
| Sunbury Police Station (Police Stations Program 2007-08) – Construction (Sunbury)(b) | 1 000 | 71 | 428 | 501 |
| Swan Hill Police Station (Police Stations Program 2007-08) – Construction (Swan Hill)(b)(e) | 15 000 | 1 568 | 6 067 | 7 365 |
| VICSES Support – Construction and Asset Enhancement (Statewide)(j) | 11 816 | 3 544 | 5 348 | 2 924 |
| Victoria Police Airwing – Asset Purchase (Statewide) | 7 700 | 3 225 | 4 475 | .. |
| Victoria Police Weapons and Equipment – Asset Enhancement (Statewide) | 9 700 | .. | 3 234 | 6 466 |
| Victorian Institute of Forensic Medicine – Equipment Upgrade Program (Statewide) | 3 500 | 1 629 | 1 351 | 520 |
| Wallan Police Station – Construction (Wallan) | 5 344 | 5 251 | 93 | .. |
| Yarra Junction Police Station (Priority Projects – Rural/Regional Police Station) – Construction (Yarra Junction)(e) | 1 000 | 749 | 251 | .. |
| Yarrawonga Police Station Replacement (Stage 8) – Construction (Yarrawonga) | 2 097 | 1 118 | 979 | .. |
| Total existing projects | 421 845 | 218 089 | 124 659 | 79 097 |

Source: Department of Justice

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	This project was previously reported as part of the Police Stations Program 2007-08, which aggregated a number of police stations.

(c)	The Total Estimated Investment (TEI) has been reduced by $0.2 million, as the project scope was reduced.

(d)	The TEI has been increased by $1.9 million, to manage the increased scope of the project.

(e)	This project was previously reported as part of the Priority Projects – Rural/Regional Police Stations, which aggregated a number of police stations.

(f)	This project is a combination of the Melbourne Legal Precinct Masterplan and 2007-08 Melbourne Legal Precinct Masterplan projects, which were previously reported separately.

(g)	The TEI has been reduced by $0.2 million, due to the project being completed at a lower cost than anticipated.

(h)	The TEI has been reduced by $8.1 million, due to reclassification of some expenditure (predominately IT software) from asset funding to output funding.

(i)	The TEI has been increased by $1 million, due to reclassification of some expenditure from output funding to asset funding.

(j)	The TEI has been reduced by $0.2 million, due to reclassification of some expenditure from asset funding to output funding.

Department of Justice

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Building Confidence in Corrections – Construction/Asset Enhancement (Statewide/Rural) | 316 587 |  | .. | 78 217 | 238 370 |
| Children's Court Workload and Resourcing – Enhancement (Melbourne/Metropolitan) | 355 |  | .. | 255 | 100 |
| Evidentiary Audio Visual Recording Equipment – Replacement (Melbourne) | 19 040 |  | .. | 7 516 | 11 524 |
| Improving Dispute Resolution Services – Enhancement (Statewide) | 323 |  | .. | 171 | 152 |
| Infringement Management and Enforcement Services – Enhancement/Equipment (Statewide) | 27 939 |  | 2 500 | 2 493 | 22 946 |
| Magistrates' Court – Safety, Security and Risk Management – Equipment/ Enhancement (Metropolitan) |  | 1 980 | .. | 1 980 | .. |
| Melbourne Legal Precinct Master Plan – Old County Court Refurbishment – Construction/ Enhancement (Melbourne) | 22 500 |  | .. | 17 500 | 5 000 |
| Mortuary Services – Construction/ Enhancement (Melbourne) | 38 000 |  | .. | .. | 38 000 |
| Police Stations Priority Upgrade Program – Asset Enhancement (Statewide) | 10 000 |  | .. | 2 000 | 8 000 |
| Reducing Court Delays – Supreme Court – Enhancement (Melbourne) | 511 |  | .. | 287 | 224 |
| Revitalising Central Dandenong – New Asset (Dandenong) | 4 255 |  | .. | .. | 4 255 |
| Sexual Assault Reform (Rural and Regional and Geelong) – Equipment/ Enhancement (Statewide) |  | 1 267 | .. | 834 | 433 |
| Victoria Police Asset Replacement – Equipment (Statewide) | 4 790 |  | .. | 4 790 | .. |
| Victoria Police Forensic Capability – Equipment (Statewide) | 1 709 |  | .. | 673 | 1 036 |
| Victoria State Emergency Service (VICSES) Critical Asset Replacement Program – Replacement (Statewide) | 2 644 |  | .. | 2 644 | .. |
| Total new projects | 451 900 |  | 2 500 | 119 360 | 330 040 |
| Total Justice projects | 873 745 |  | 220 589 | 244 019 | 409 137 |

Source: Department of Justice

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

# Department of Planning and Community Development

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Electronic Document and Records Management System – IT Upgrade (Melbourne) | 4 000 | 600 | 2 300 | 1 100 |
| Footscray Transit City – Upgrade (Footscray) | 38 459 | 10 198 | 21 303 | 6 958 |
| Improving Major Sporting Precincts – Upgrade Works (Albert Park) | 4 200 | 3 300 | 900 | .. |
| Rectangular Sports Stadium – Construction (Olympic Park)(b) | 211 500 | 79 725 | 106 275 | 25 500 |
| Ringwood Transit City – Upgrade (Ringwood) | 3 433 | .. | 3 433 | .. |
| Transit Cities: Revitalising Central Dandenong – Upgrade Works (Dandenong) | 243 446 | 75 184 | 59 748 | 108 514 |
| Total existing projects | 505 038 | 169 007 | 193 959 | 142 072 |

Source: Department of Planning and Community Development

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	$6 million was expended in 2005-06 on works in Gosch’s Paddock and to develop detailed plans for the stadium in the Olympic Park Precinct. The original Total Estimated Investment of $143 million for the initiative was increased to reflect a higher overall Total Estimated Investment requirement due to the provision of increased seating capacity, and the timing of funding has been adjusted to reflect the revised construction program.

Department of Planning and Community Development

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Aboriginal Heritage Information System – IT System (Melbourne) | 4 419 | .. | 1 495 | 2 924 |
| Northbank Promenade Access and Safety Improvements – Construction (Melbourne) | 15 100 | .. | 6 200 | 8 900 |
| Revitalising Central Dandenong – Building fit out (Dandenong) | 709 | .. | .. | 709 |
| State Sports Facilities Project – Upgrade (Various) | 50 300 | .. | 11 200 | 39 100 |
| Total new projects | 70 528 | .. | 18 895 | 51 633 |
| Total Planning and Community Development projects | 575 566 | 169 007 | 212 854 | 193 705 |

Source: Department of Planning and Community Development

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

# Department of Premier and Cabinet

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Arts and Cultural Facilities Maintenance (Various)(b) | 24 937 | 18 689 | 6 248 | .. |
| Arts Centre Precinct – Design and Business Case Development (Southbank)(c) | 2 363 | 292 | 2 071 | .. |
| Australian Centre for the Moving Image – New Exhibition of 100 Years of the Moving Image (Melbourne) | 8 857 | 5 006 | 3 851 | .. |
| City of Literature – State Library of Victoria Refurbishment for Centre for Books, Writing and Ideas (Melbourne)(d) | 8 000 | 547 | 6 453 | 1 000 |
| Melbourne Recital Centre and Melbourne Theatre Company Theatre – Construction (Southbank)(e) | 128 007 | 116 871 | 11 136 | .. |
| Public Record Office Victoria – Asset Management (North Melbourne)(f) | 7 585 | 6 419 | 1 166 | .. |
| Redevelopment of Core Business Systems (Melbourne) | 4 000 | 2 659 | 1 341 | .. |
| Total existing projects | 183 749 | 150 483 | 32 266 | 1 000 |

Source: Department of Premier and Cabinet

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	The Total Estimated Investment (TEI) of $25.202 million was further revised to reflect a change in the accounting treatment of the project expenses with $0.265 million of the TEI reclassified as operating expenditure.

(c)	The original TEI of $5.000 million was revised to reflect a change in the accounting treatment of the project expenses with $2.637 million of the TEI reclassified as operating expenditure.

(d)	The original 2 year project cash flow has been rephased over 3 years to allow for the finalisation of the detailed client brief and integrated construction program.

(e)	TEI increased by $6.497 million involving additional contributions external to State Government funding.

(f)	The original TEI of $8.135 million was revised to reflect a change in the accounting treatment of the project expenses with $0.550 million of the TEI reclassified as operating expenditure.

Department of Premier and Cabinet

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Centre for Books, Writing and Ideas – Fitout (Melbourne) | 3 200 | .. | 3 200 | .. |
| Museum Victoria – Exhibition Renewal (Melbourne) | 8 000 | .. | 4 000 | 4 000 |
| Total new projects | 11 200 | .. | 7 200 | 4 000 |
| Total Premier and Cabinet projects | 194 949 | 150 483 | 39 466 | 5 000 |

Source: Department of Premier and Cabinet

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

# Department of Primary Industries

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Fish Production Facility – Development (Northern Victoria)(b) |  | 1 300 | .. | 1 300 | .. |
| Lysterfield Lake Park – Land Purchase (Lysterfield) | 3 000 |  | 1 440 | 60 | 1 500 |
| Melbourne Wholesale Markets – Redevelopment (Epping)(c) | 218 270 |  | .. | 42 208 | 176 062 |
| Replacement of Fisheries Catch and Effort Data and Information System – System replacement (Melbourne)(d) |  | 3 193 | .. | 3 193 | .. |
| Total existing projects | 225 763 |  | 1 440 | 46 761 | 177 562 |

Source: Department of Primary Industries

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	Actual location to be determined. An options paper to identify production requirements and site selection criteria has been drafted.

(c)	This figure excludes any Treasury Corporation of Victoria funding for this project.

(d)	Tender process is complete and implementation has commenced.

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Resource Rights Allocation and Management Capability – System replacement (Melbourne) | 11 713 | .. | 1 652 | 10 061 |
| Victorian Renewable Energy Target Scheme – System Development (Melbourne)(b) | 2 200 | 1 100 | 1 100 | .. |
| Total new projects | 13 913 | 1 100 | 2 752 | 10 061 |
| Total Primary Industries projects | 239 676 | 2 540 | 49 513 | 187 623 |

Source: Department of Primary Industries

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b) 	This system may also be used for the administration of the Victorian Energy Efficiency Target (VEET).

# Department of Sustainability and Environment

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| A New Deal for Regional Local Ports – Upgrade (Various) | 9 970 | 2 470 | 2 500 | 5 000 |
| Australian Garden Stage 2, Royal Botanic Gardens, Cranbourne – Restoration (Cranbourne) | 20 900 | 2 920 | 8 180 | 9 800 |
| Barwon Water – Shell Recycling Project – Construction (Barwon) | 9 420 | 2 050 | 6 100 | 1 270 |
| Bike Trails for a Liveable City – Construction (Melbourne) | 2 200 | 500 | 1 000 | 700 |
| Bushfire Recovery 2007-08 – Restoration (Statewide) | 11 900 | 1 651 | 6 843 | 3 406 |
| Crown Land Caravan and Camping Parks Improvement Program – Upgrade (Statewide) | 4 680 | 680 | 1 500 | 2 500 |
| Epsom Spring Gully Water Recycling Project (Commonwealth) | 6 300 | 5 900 | .. | 400 |
| Food Bowl Modernisation Project – Goulburn Murray (Upgrade) | 600 000 | 76 000 | 74 112 | 449 888 |
| Geelong – Melbourne Pipeline (Various) | 20 000 | .. | 3 000 | 17 000 |
| Goldfields Superpipe – Ballarat Interconnect – Commonwealth Component – Construction (Ballarat)(b) | 90 000 | 90 000 | .. | .. |
| Goldfields Superpipe – Ballarat Interconnect (Ballarat)(b) | 70 660 | 70 660 | .. | .. |
| Goldfields Superpipe – Bendigo Interconnect (Commonwealth)(c) | 25 000 | 25 000 | .. | .. |
| Great Parks for a Liveable City – Establish (Metropolitan) | 13 250 | 9 710 | 2 440 | 1 100 |
| Hamilton – Grampians Pipeline | 10 000 | 1 000 | 3 500 | 5 500 |
| Improving Victoria's Natural Tourism Attractions – National Parks Upgrades (Statewide) | 11 500 | 1 790 | 5 040 | 4 670 |
| Integrated Asset Management System – Systems Development (Statewide) | 8 400 | 8 089 | 300 | 11 |
| Melbourne Zoo Seal Pool Redevelopment – Construction (Parkville) | 20 000 | 10 000 | 7 000 | 3 000 |
| Modernisation of Shepparton Irrigation Area – Construction (Shepparton) | 37 500 | 37 500 | .. | .. |
| Mullum Mullum Park – Upgrade (Mullum Mullum) | 1 100 | 150 | 275 | 675 |
| National Reserve – Land acquisition (Metropolitan) | 2 313 | 571 | 360 | 1 382 |
| National Water Initiative – Living Murray Initiatives – Restoration (Statewide) | 18 879 | 16 703 | 2 176 | .. |
| National Water Initiative – Macalister – Construction (Boisdale) | 20 000 | 18 660 | 1 340 | .. |
| Northern Grid – Promoting Interconnection (Drought Relief) – Construction (Northern Grid) | 2 500 | 750 | 1 750 | .. |
| Our Water Our Future – Renew/ Upgrade (Statewide)(d) | 43 122 | 38 204 | 4 918 | .. |
| Piers and Jetties – Upgrade (Port Phillip and Westernport Bays) | 10 000 | 1 090 | 3 920 | 4 990 |
| Point Nepean and Walking Track – Construction (Point Nepean) | 600 | 40 | 560 | .. |
| Ports and Risk Mitigation Renew (Various) | 7 392 | 1 614 | 2 000 | 3 778 |
| Protection of Beaches and Foreshores – Maintenance (Statewide) | 8 000 | .. | 500 | 7 500 |
| Provincial Services – Replace Existing Assets (Various) | 1 896 | 1 846 | .. | 50 |
| Solar Panels at Schools (Victorian Solar Profile 500) – Construction (Statewide) | 5 000 | .. | 1 250 | 3 750 |
| Summerland Estate – Restoration (Summerland) | 15 400 | 3 743 | 5 100 | 6 557 |
| Sustainable Management of Victoria's Parks – Renew (Statewide) | 55 183 | 31 450 | 8 371 | 15 362 |
| Sustainable Water Initiatives – Maintenance (Statewide) | 18 188 | .. | 4 522 | 13 666 |
| Urban Parks and Paths – Construction (Statewide) | 7 800 | 800 | 3 320 | 3 680 |
| Victorian Water Trust Assets – Upgrades (Various)(e) | 152 571 | 123 463 | 16 307 | 12 801 |
| Wimmera-Mallee Pipeline Project – Commonwealth Component – Construction (Mallee/Wimmera)(f)(g) | 266 000 | 244 999 | 21 001 | .. |
| Wimmera-Mallee Pipeline Project – State Component – Construction (Mallee/Wimmera)(f)(h) | 266 000 | 207 949 | 58 000 | 51 |
| Total existing projects | 1873 624 | 1037 952 | 257 185 | 578 487 |

Source: Department of Sustainability and Environment

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	The Goldfields Superpipe – Ballarat Interconnect has a total TEI of $178 million. The water authority’s contribution is included in Chapter 3.

(c)	The Goldfields Superpipe – Bendigo Interconnect has a total TEI of $98 million. The State Government contributed $30 million towards this project in 2006-07, and the Commonwealth Government contributed $25 million towards this project in 2007-08. The water authority’s contribution is included in Chapter 3.

(d)	The TEI for Our Water Our Future – Renew/Upgrade (Statewide) has been increased by $5.879 million. This amount has been transferred from DSE Provision of Outputs in accordance with the reclassification of works from output to asset.

(e)	The TEI for the Victorian Water Trust Assets – Upgrades (Various) has decreased by $50 million. This is to reflect that the Victorian Water Trust will contribute $50 million towards the Food Bowl Modernisation Project.

(f)	The TEI for Wimmera-Mallee Pipeline Project – Commonwealth Component - Construction (Mallee/Wimmera) has increased by $99 million to reflect a matching contribution to the project from the Commonwealth Government. Commonwealth funding for the project may increase by an additional $25 million subject to conditions being agreed by the relevant parties.

(g)	The Wimmera-Mallee Pipeline Project has a total TEI of $790 million with the State and Commonwealth Governments each contributing $266 million and Grampians Wimmera-Mallee Water Corporation contributing $258 million (including on-farm works).

(h)	The TEI for Wimmera-Mallee Pipeline Project – State Component - Construction (Mallee/Wimmera) has increased by $99 million to reflect the State Government’s approval of additional funding towards this project.

Department of Sustainability and Environment

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Bays and Maritime Capital Works Program – Upgrade (Port Phillip Bay) | 2 500 | 2 500 | .. | .. |
| Enhancing Victoria's Parks and Reserves | 1 600 | .. | 375 | 1 225 |
| Fire Protection Access: Bridge replacement | 60 000 | .. | 15 000 | 45 000 |
| Wonthaggi Desalination Project Stage 1 | 32 000 | 2 000 | 30 000 | .. |
| Total new projects | 96 100 | 4 500 | 45 375 | 46 225 |
| Total Sustainability and Environment Projects | 1969 724 | 1042 452 | 302 560 | 624 712 |

Source: Department of Sustainability and Environment

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

# Department of Transport

## Existing projects

| ($ thousand) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  |  |  |  | Expenditure to 30.06.08(a) |  | Estimated Expenditure 2008-09 |  |  | Remaining Expenditure |
| Accessible Public Transport in Victoria: Disability Discrimination Act (DDA) Compliance for Train, Tram and Bus (Statewide) | 129 200 |  |  |  |  | 48 615 |  | 41 785 |  |  | 38 800 |
| Caulfield-Dandenong Rail Corridor Stage 1 – Cranbourne Stabling and Station Upgrade (Cranbourne) | 35 100 |  |  |  |  | 10 000 |  | 25 028 |  |  | 72 |
| Congestion Improvements Program (Various) | 30 000 |  |  |  |  | 9 620 |  | 14 441 |  |  | 5 939 |
| Connect Freight (Melbourne) | 2 000 |  |  |  |  | 740 |  | 1 260 |  |  | .. |
| Coolaroo Station (Coolaroo) | 36 000 |  |  |  |  | 50 |  | 9 950 |  |  | 26 000 |
| Cranbourne Frankston Road Duplication (Hall Road and the Western Port Highway) | 30 000 |  |  |  |  | 2 850 |  | 10 800 |  |  | 16 350 |
| Dynon Port Rail Link (Melbourne) | 15 100 |  |  |  |  | 8 100 |  | 7 000 |  |  | .. |
| EastLink – Burwood Highway/ Mountain Highway Pedestrian Overpass (Wantirna) | 3 000 |  |  |  |  | .. |  | 3 000 |  |  | .. |
| EastLink – Maroondah Highway Pedestrian Overpass (Ringwood) | 3 500 |  |  |  |  | 700 |  | 2 800 |  |  | .. |
| Geelong Rail Access Improvement Project (Corio/North Geelong) | 33 360 |  |  |  |  | 14 642 |  | 18 718 |  |  | .. |
| Geelong Ring Road – Bypass/New Road (Geelong) | 194 000 |  |  |  |  | 116 204 |  | 47 903 |  |  | 29 893 |
| Geelong Ring Road Stage 4 – Geelong Ring Road to Anglesea Road (City of Greater Geelong) | 62 500 |  |  |  |  | 13 000 |  | 14 000 |  |  | 35 500 |
| Hallam Park and Ride (Hallam) | 3 000 |  |  |  |  | 1 800 |  | 1 200 |  |  | .. |
| Metropolitan Train Control Reliability (Melbourne) | 87 900 |  |  |  |  | 17 794 |  | 28 352 |  |  | 41 754 |
| Metropolitan Train Safety Communications System (Metro Various) | 134 900 |  |  |  |  | 11 535 |  | 48 293 |  |  | 75 072 |
| Metropolitan Train Services (Metro Various)(b) | 565 817 |  |  |  |  | 32 500 |  | 123 500 |  |  | 409 817 |
| Mildura Rail Line Upgrade (Non Metro Various) | 53 000 |  |  |  |  | 30 218 |  | 17 782 |  |  | 5 000 |
| Narre Warren Cranbourne Road Duplication (Centre Road and Pound Road) (Narre Warren South) | 7 400 |  |  |  |  | 798 |  | 5 249 |  |  | 1 353 |
| New Ticketing Solution – Technology and Installation (Statewide) | 460 900 |  |  |  |  | 180 000 |  | 149 900 |  |  | 131 000 |
| North Melbourne Station Interchange Upgrade (North Melbourne) | 38 577 |  |  |  |  | 28 577 |  | 10 000 |  |  | .. |
| Public Transport Security Package (Various) | 13 600 |  |  |  |  | 9 000 |  | 4 600 |  |  | .. |
| Railway Crossing Upgrades (Statewide)(c) | 119 962 |  |  |  |  | 49 600 |  | 29 053 |  |  | 41 309 |
| Regional Rollingstock (Non Metro Various)(d) | 100 150 |  |  |  |  | 55 620 |  | 23 792 |  |  | 20 738 |
| SmartBus: Green Orbital – Nunawading to Airport West (Metro Various) | 29 316 |  |  |  |  | 1 806 |  | 13 587 |  |  | 13 923 |
| SmartBus: Red Orbital – Box Hill to Altona (Metro Various) | 29 080 |  |  |  |  | 11 261 |  | 17 819 |  |  | .. |
| Stations and Modal Interchanges Program (Various) | 20 500 |  |  |  |  | 2 100 |  | 4 200 |  |  | 14 200 |
| Track Duplication: Clifton Hill to Westgarth (Metro Various) | 52 000 |  |  |  |  | 12 791 |  | 33 554 |  |  | 5 655 |
| Vigilance Control and Event Recording System on Metropolitan Trains (VICERS) (Metro Various) | 37 269 |  |  |  |  | 17 224 |  | 20 045 |  |  | .. |
| West Gate – Monash Freeways Improvement Package (Metro Various) | 1100 000 |  |  |  |  | 149 622 |  | 360 238 |  |  | 590 140 |
| Whole of Government – Transit Cities – Ballarat Second Station (Ballarat) | 11 000 |  |  |  |  | 3 819 |  | 7 181 |  |  | .. |
| Wodonga Rail Bypass(Wodonga)(e) | 111 500 |  |  |  |  | 14 704 |  | 6 656 |  |  | 90 140 |
| Better Roads – Rural Arterial Road Projects |  |  |  |  |  |  |  |  |  |  |  |
| Barwon Heads Bridge Replacement (Barwon Heads) | 22 300 |  |  |  |  | 3 317 |  | 13 900 |  |  | 5 083 |
| Bass Highway Duplication Stage 1 –King Road to Woolmer Road (Bass, Anderson) | 27 100 |  |  |  |  | 5 298 |  | 9 000 |  |  | 12 802 |
| Bass Highway Duplication Stage 5 – Grantville to King Road (Grantville) | 23 600 |  |  |  |  | 20 309 |  | 2 700 |  |  | 591 |
| Breakwater Road Upgrade (Belmont, Geelong) | 40 000 |  |  |  |  | 1 604 |  | 10 000 |  |  | 28 396 |
| Calder Highway Section 2 (118.0km to 135.0km) – Faraday to Ravenswood (Faraday, Harcourt, Ravenswood South, Ravenswood) | 111 500 |  |  |  |  | 99 417 |  | 5 821 |  |  | 6 262 |
| Calder Highway Upgrade (90.8km to 118.0km) – Kyneton to Faraday (Kyneton, Malmsbury, Taradale, Elphingstone) | 87 675 |  |  |  |  | 81 475 |  | 2 170 |  |  | 4 030 |
| Glenelg Highway Passing Lanes (Scarsdale and Linton – Golden Plains Shire) | 3 000 |  |  |  |  | 700 |  | 2 300 |  |  | .. |
| Better Roads – Metropolitan (including Outer Metropolitan) |  |  |  |  |  |  |  |  |  |  |  |
| Baxter-Tooradin Road (2.46km to 2.49km) New Roundabout – Fultons Road/Hawkins Road (Baxter) | 5 000 |  |  |  |  | 475 |  | 3 025 |  |  | 1 500 |
| Berwick Cranbourne Road Duplication (3km – 5km) – Pound Road to Thompsons Road (Cranbourne North, Clyde North) | 15 000 |  |  |  |  | 9 486 |  | 4 919 |  |  | 595 |
| Cranbourne Frankston Road Duplication (10.2km – 11.9km) – Centre Road to Western Port Highway (Langwarrin) | 11 400 |  |  |  |  | 7 641 |  | 2 855 |  |  | 904 |
| Derrimut Road Duplication (3.5km – 5.12km) – Hogans Road to Sayers Road (Hoppers Crossing) | 14 700 |  |  |  |  | 6 425 |  | 3 688 |  |  | 4 587 |
| Duplication of Thompsons Road (Carrum Downs) | 30 500 |  |  |  |  | 6 996 |  | 11 032 |  |  | 12 472 |
| Duplication of Thompsons Road (Cranbourne) | 22 000 |  |  |  |  | 3 711 |  | 10 101 |  |  | 8 188 |
| Ferntree Gully Road Widening – Jells Road to Stud Road (Scoresby) | 32 000 |  |  |  |  | 7 597 |  | 24 403 |  |  | .. |
| Frankston Bypass Environment Effects Statement (Frankston) | 5 000 |  |  |  |  | 2 800 |  | 2 200 |  |  | .. |
| George Street Bridge – New Bridge to link George Street to Brighton Road (Dandenong) | 17 500 |  |  |  |  | 9 163 |  | 6 037 |  |  | 2 300 |
| Nepean Highway Bridge Replacement – Mordialloc Creek (Kingston City) |  |  | 10 200 |  |  | 5 397 |  | 3 763 |  |  | 1 040 |
| Signalisation of Lower Dandenong Road and Boundary Road (Braeside) |  | 5 000 |  |  |  | 200 |  | 2 500 |  |  | 2 300 |
| Springvale Road (2km to 2.2km) New Intersection Signals – Old Warrandyte Road Intersection (Donvale) | 3 000 |  |  |  |  | 165 |  | 2 435 |  |  | 400 |
| Taylors Road (15.2km to 15.8km) – Bypass/New Road – Sydenham Road to East Esplanade – Grade Separation (St Albans) | 54 000 |  |  |  |  | 38 365 |  | 8 082 |  |  | 7 553 |
| Vineyard Road (Obeid Drive and Mitchells Lane, Sunbury) | 25 000 |  |  |  |  | 3 969 |  | 11 423 |  |  | 9 608 |
| Western Highway: Deer Park Bypass and Leakes Road Interchange Upgrade (Deer Park) | 66 000 |  |  |  |  | 21 216 |  | 41 844 |  |  | 2 940 |
| Western Port Highway Duplication (0km – 4km) Cranbourne Frankston Road to North Road (Langwarrin, Cranbourne South) | 36 800 |  |  |  |  | 12 143 |  | 18 668 |  |  | 5 989 |
| State Funded Rural Road Projects |  |  |  |  |  |  |  |  |  |  |  |
| Regional Arterial Road and Bridge Links (Non Metro various) | 41 930 |  |  |  |  | 36 929 |  | 1 850 |  |  | 3 151 |
| Transport Accident Commission |  |  |  |  |  |  |  |  |  |  |  |
| Safer Road Infrastructure Program 3 (Various) | 722 202 |  |  |  |  | 55 022 |  | 80 000 |  |  | 587 180 |
| AusLink (Commonwealth Funding) |  |  |  |  |  |  |  |  |  |  |  |
| Calder Highway (118.0km to 135.0km) – Bypass/New Road – Faraday to Ravenswood (Faraday, Harcourt, Ravenswood South, Ravenswood) | 107 000 |  |  |  |  | 96 743 |  | 10 257 |  |  | .. |
| Dynon Port Rail Link (Melbourne) | 110 000 |  |  |  |  | 82 532 |  | 27 468 |  |  | .. |
| Geelong Ring Road – Bypass/New Road (Geelong) | 186 000 |  |  |  |  | 161 903 |  | 24 097 |  |  | .. |
| Hume Highway – Donnybrook Road Interchange – Grade Separation (Beveridge, Craigieburn) | 39 000 |  |  |  |  | 19 859 |  | 13 719 |  |  | 5 422 |
| Upgrade the Railway Track between Geelong and Mildura (Non Metro Various) | 20 000 |  |  |  |  | 2 000 |  | 18 000 |  |  | .. |
| Western Bypass – Deer Park Bypass including Leakes Road Interchange (Deer Park) | 265 000 |  |  |  |  | 211 729 |  | 53 271 |  |  | .. |
| Wodonga Rail Bypass (Wodonga)(e) | 45 000 |  |  |  |  | .. |  | 35 000 |  |  | 10 000 |
| Outer Commonwealth Funded |  |  |  |  |  |  |  |  |  |  |  |
| Murray River Bridge Replacements – Crossings (Corowa, Echuca and Robinvale) | 15 000 |  |  |  |  | .. |  | 3 000 |  |  | 12 000 |
| Total existing projects | 5769 038 |  |  |  |  | 1869 876 |  | 1571 214 |  |  | 2327 948 |

Source: Department of Transport

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	Total Estimated Investment of $565.8 million reflects announced funding for the purchase of 18 new metropolitan trains, adjusted for identified cost savings.

(c)	Total Estimated Investment incorporates all funding for pedestrian and level crossing programs from 2006-07 to 2011-12.

(d)	Total Estimated Investment of $100.2 million includes $65.1 million announced in 2006-07 for 14 new regional train carriages and $35.1 million announced in 2007-08 for an additional 8 regional train carriages.

(e)	The Total Estimated Investment for the North East Rail Revitalisation Project including the Wodonga Rail Bypass is $501.3 million. This comprises $171.3 million from the State and $45 million from the Commonwealth. A further $285 million is provided from the Australian Rail Track Corporation, which is not reported in this publication.

Department of Transport

## New projects

| ($ thousand) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  |  | Expenditure to 30.06.08(a) |  | Estimated Expenditure 2008-09 |  |  | Remaining Expenditure |
| Caulfield – Dandenong Rail Corridor Stage Two – Westall Rail Upgrade (Springvale) | 151 061 |  |  | .. |  | 19 589 |  |  | 131 472 |
| Congestion Measures | 6 300 |  |  | .. |  | 6 300 |  |  | .. |
| Country Passenger Rail Network Renewal and Maintenance (Non Metro Various) | 142 305 |  |  | .. |  | 37 560 |  |  | 104 745 |
| Country Rail Freight Network Maintenance (Non Metro Various) | 23 700 |  |  | .. |  | 23 700 |  |  | .. |
| Craigieburn Station Track Upgrade (Craigieburn) | 29 783 |  |  | .. |  | 13 019 |  |  | 16 764 |
| EastLink – High Street Road Pedestrian Overpass (Wantirna South) |  | 3 000 |  | 200 |  | 2 800 |  |  | .. |
| Geelong Ring Road Stage 4b Anglesea Road to Princes Highway West (Geelong) | 65 000 |  |  | .. |  | 5 000 |  |  | 60 000 |
| Laverton Rail Upgrade (Laverton) | 91 975 |  |  | .. |  | 23 052 |  |  | 68 923 |
| Metropolitan Park and Ride Program – Stage 2 (Metro Various) | 26 900 |  |  | .. |  | 4 200 |  |  | 22 700 |
| Noble Park Train Station Upgrade (Noble Park) | 1 400 |  |  | 350 |  | 1 050 |  |  | .. |
| North East Rail Revitalisation Project (Various)(b) | 59 800 |  |  | 300 |  | 18 202 |  |  | 41 298 |
| South Gippsland Public Transport Service Improvement Package (South Gippsland) | 2 870 |  |  | .. |  | 2 870 |  |  | .. |
| South Morang Rail Extension Development Funding (South Morang) | 10 400 |  |  | .. |  | 4 000 |  |  | 6 400 |
| Tram Electrical Upgrade and Maintenance (Metro Various) | 9 501 |  |  | .. |  | 3 667 |  |  | 5 834 |
| Windsor and Prahran Stations Upgrade (Windsor and Prahran) | 3 000 |  |  | .. |  | 1 000 |  |  | 2 000 |
| Better Roads – Metropolitan (including Outer Metropolitan) |  |  |  |  |  |  |  |  |  |
| Kororoit Creek Road Duplication – Grieve Parade to Millers Road (Altona) | 48 500 |  |  | .. |  | 1 200 |  |  | 47 300 |
| Pound Road – South Gippsland Highway – South Gippsland Freeway Intersection Upgrade (Dandenong) | 36 800 |  |  | .. |  | 1 300 |  |  | 35 500 |
| Tram and Bus Priority Program (Metro various) | 36 200 |  |  | .. |  | 6 000 |  |  | 30 200 |
| Better Roads – Rural Arterial Road Projects |  |  |  |  |  |  |  |  |  |
| Princes Highway West Stage 1 – Waurn Ponds to Winchelsea (Geelong) | 110 000 |  |  | .. |  | 5 000 |  |  | 105 000 |
| Western Highway Realignment – Anthony's Cutting (Melton to Bacchus Marsh) | 40 000 |  |  | .. |  | 5 000 |  |  | 35 000 |
| Yarra Glen Truck Bypass (Yarra Glen) | 9 000 |  |  | .. |  | .. |  |  | 9 000 |
| Total new projects | 907 495 |  |  | 850 |  | 184 509 |  |  | 722 136 |
| Total Transport projects | 6676 533 |  |  | 1870 726 |  | 1755 723 |  |  | 3050 084 |

Source: Department of Transport

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

(b)	The Total Estimated Investment for the North East Rail Revitalisation Project including the Wodonga Rail Bypass is $501.3 million. This comprises $171.3 million from the State and $45 million from the Commonwealth. A further $285 million is provided from the Australian Rail Track Corporation, which is not reported in this publication.

# Department of Treasury and Finance

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08 | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Intra-Government Secured Network – System Development (Statewide)(a) | 7 470 | .. | 7 470 | .. |
| State Revenue Office – Revenue Management System Maintenance (Melbourne) | 8 305 | 3 685 | 2 466 | 2 154 |
| WoG ICT Standardisation Strategy – Office of the Chief Information Officer (Melbourne)(b) | 2 437 | 1 374 | 1 063 | .. |
| Total existing projects | 18 212 | 5 059 | 10 999 | 2 154 |
| Total Treasury and Finance projects | 18 212 | 5 059 | 10 999 | 2 154 |

Source: Department of Treasury and Finance

Notes:

(a) 	The Total Estimated Investment of $7.830 million was revised to reflect a change in the accounting treatment of the project expenses with $0.360 million in 2007-08 reclassified as operating expenditure.

(b) 	The Total Estimated Investment of $5.304 million was revised to reflect a change in the accounting treatment of the project expenses with $2.867 million in 2007-08 reclassified as operating expenditure.

## New projects

| ($ thousand) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08 |  | Estimated Expenditure 2008-09 |  | Remaining Expenditure |  |
| Nil |  | .. |  | .. |  | .. |  | .. |
| Total new projects |  | .. |  | .. |  | .. |  | .. |
| Total Treasury and Finance projects |  | .. |  | .. |  | .. |  | .. |

Source: Department of Treasury and Finance

# Parliament

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Auditor-General's Office – Asset replacement (Melbourne) | 4 101 | 3 501 | 600 | .. |
| Heritage Asset Management Strategy (Melbourne) | 9 049 | 2 225 | 4 549 | 2 275 |
| Integrated Public Sector Audit Methodology – Development of Financial Audit Methodology (Melbourne) | 957 | 842 | 50 | 65 |
| Total existing projects | 14 107 | 6 568 | 5 199 | 2 340 |

Source: Parliament

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Webcasting of Parliamentary Proceedings (Melbourne) | 3 800 | .. | 860 | 2 940 |
| Total new projects | 3 800 | .. | 860 | 2 940 |
| Total Parliament projects | 17 907 | 6 568 | 6 059 | 5 280 |

Source: Parliament

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by departments as at May 2008.

# Country Fire Authority

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment(a) | Expenditure to 30.06.08(b) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Fire Station – Construction (Bayswater) | 167 | 99 | 68 | .. |
| Fire Station – Construction (Ocean Grove) | 2 535 | 1 958 | 577 | .. |
| Fire Station – Construction and Office Accommodation (Ballarat) | 500 | 162 | 250 | 88 |
| Fire Station – Operational Support Staff – Construction (Statewide) | 15 000 | 12 747 | 2 253 | .. |
| Fire Station – Replacement – Construction (Statewide) | 39 180 | 4 646 | 12 000 | 22 534 |
| Tanker Replacement Program (Statewide) | 38 200 | 35 645 | 2 555 | .. |
| Vehicles – Hazmat (Statewide) | 1 650 | 328 | 1 322 | .. |
| Vehicles – Heavy Pumpers (Statewide) | 6 780 | 3 078 | 3 702 | .. |
| Vehicles – Light Pumpers (Statewide) | 216 | 147 | 69 | .. |
| Vehicles – Light Tankers (Statewide) | 4 462 | 99 | 2 500 | 1 863 |
| Vehicles – Medium Tankers (Statewide) | 7 661 | 7 577 | 83 | .. |
| Vehicles – Pumper Tankers (Statewide) | 4 222 | 1 038 | 3 185 | .. |
| Vehicles – Rescue (Statewide) | 1 408 | 1 224 | 185 | .. |
| Total existing projects | 121 980 | 68 747 | 28 749 | 24 484 |

Source: Country Fire Authority

Notes:

(a) 	Total Estimated Investment includes contributions external to state government.

(b)	Expenditure for the year to 30 June 2008 based on information provided by the agency as at May 2008.

Country Fire Authority

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment(a) | Expenditure to 30.06.08(b) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Fire Station Construction (Belgrave Heights) | 350 | 35 | 315 | .. |
| Fire Station Construction (Statewide) | 5 175 | .. | 3 000 | 2 175 |
| Vehicles – Critical Response (Statewide) | 11 800 | 197 | 4 000 | 7 603 |
| Vehicles (Statewide) | 12 700 | .. | 6 000 | 6 700 |
| Total new projects | 30 025 | 232 | 13 315 | 16 478 |
| Total Country Fire Authority projects | 152 005 | 68 979 | 42 064 | 40 962 |

Source: Country Fire Authority

Notes:

(a)	Total Estimated Investment includes contributions external to state government.

(b)	Expenditure for the year to 30 June 2008 based on information provided by the agency as at May 2008.

# Metropolitan Fire and Emergency Services Board

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment(a) | Expenditure to 30.06.08(b) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Altona Fire Station Land Purchase (Metropolitan) | 1 519 | .. | .. | 1 519 |
| Chemical/Biological/Radio-Active Terrorism – Additions/Upgrade/ Replacement (Metropolitan) | 3 690 | 1 091 | 2 599 | .. |
| Computer Equipment and Software – Upgrade/Replacement 07-08 (Metropolitan) | 2 435 | 1 250 | 1 185 | .. |
| Computers Software – Upgrade/ Replacement (Metropolitan) | 19 039 | 16 863 | 2 176 | .. |
| Laverton Fire Station Land Purchase (Metropolitan) | 440 | .. | .. | 440 |
| Malvern Fire Station Land Purchase (Metropolitan) | 3 000 | .. | .. | 3 000 |
| Plant and Equipment Replacement/ Upgrade 07/08 (Metropolitan) | 6 467 | 1 934 | 4 533 | .. |
| Plant Equipment – Replacement (Metropolitan) | 11 230 | 6 692 | 4 538 | .. |
| Stations – Alterations and Major Maintenance (Metropolitan) | 3 893 | 740 | 3 153 | .. |
| Templestowe Fire Station – Construction (Metropolitan) | 3 868 | 150 | 2 250 | 1 468 |
| Vehicles – Car/Light Truck Replacement (Metropolitan) | 2 772 | 2 355 | 417 | .. |
| Vehicles – Fire Fighting Appliances Upgrade/Replacement (Metropolitan) | 1 891 | 120 | 1 771 | .. |
| Total existing projects | 60 244 | 31 195 | 22 622 | 6 427 |

Source: Metropolitan Fire and Emergency Services Board

Notes:

(a)	Total Estimated Investment includes contributions external to state government.

(b)	Expenditure for the year to 30 June 2008 based on information provided by the agency as at May 2008.

Metropolitan Fire and Emergency Services BoaRd

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment(a) | Expenditure to 30.06.08(b) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Breathing Apparatus – Replacement (Metropolitan) | 1 070 | .. | 835 | 235 |
| Computer Equipment and Software Upgrade/Replacement (Metropolitan) | 4 982 | .. | 3 000 | 1 982 |
| Laverton Fire Station – Construction (Metropolitan) | 1 373 | .. | 140 | 1 233 |
| Laverton North Fire Station – Land Purchase (Metropolitan) | 1 070 | .. | .. | 1 070 |
| Moonee Ponds Fire Station – Construction (Metropolitan) | 1 636 | .. | 136 | 1 500 |
| Moonee Ponds Fire Station – Land Purchase (Metropolitan) | 1 700 | .. | 1 700 | .. |
| North Laverton Fire Station – Construction (Metropolitan) | 2 600 | .. | .. | 2 600 |
| Nunawading Fire Station – Construction (Metropolitan) | 5 336 | .. | 3 200 | 2 136 |
| Oakleigh Fire Station – Upgrade (Metropolitan) | 3 337 | .. | 2 700 | 637 |
| Plant and Equipment – Replacement (Metropolitan) | 7 809 | .. | 4 700 | 3 109 |
| Spotswood Fire Station – Land Purchase (Metropolitan) | 1 042 | .. | .. | 1 042 |
| Station Alterations and Major Maintenance (Metropolitan) | 8 669 | .. | 5 000 | 3 669 |
| Vehicles – Car/Light Truck Replacement (Metropolitan) | 2 439 | .. | 2 200 | 239 |
| Vehicles – Fire Fighting Appliances Upgrade/Replacement (Metropolitan) | 4 761 | .. | 3 350 | 1 411 |
| Total new projects | 47 824 | .. | 26 961 | 20 863 |
| Total Metropolitan Fire and Emergency Services Board projects | 108 068 | 31 195 | 49 583 | 27 290 |

Source: Metropolitan Fire and Emergency Services Board

Notes:

(a)	Total Estimated Investment includes contributions external to state government.

(b)	Expenditure for the year to 30 June 2008 based on information provided by the agency as at May 2008.

Chapter 3: Major public non-financial corporations asset investment program 2008-09

# Barwon Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Aireys Inlet Water Reclamation Plant Southern Drain Upgrade (Aireys Inlet) | 453 |  | .. | .. | 453 |
| Aireys Inlet Water Treatment Plant Renewal and System Upgrade (Aireys Inlet) | 502 |  | 291 | 75 | 136 |
| Allen Reservoir Embankment Upgrade (Lorne) | 830 |  | .. | .. | 830 |
| Alvie Basin Lining and Covering and Associated Works (Alvie) | 1 017 |  | 398 | 619 | .. |
| Anglesea Borefield Project (Anglesea) | 50 527 |  | 14 098 | 26 758 | 9 671 |
| Apollo Bay Bulk Water Supply (Apollo Bay) | 10 870 |  | 1 119 | .. | 9 751 |
| Apollo Bay Pump Station No. 1 Upgrade (Apollo Bay) | 1 159 |  | .. | .. | 1 159 |
| Apollo Bay Water Treatment Plant Renewal and System Upgrade (Apollo Bay) | 337 |  | 122 | 23 | 192 |
| Apollo Bay Water Treatment Plant Membrane Replacement (Apollo Bay) | 375 |  | 171 | .. | 204 |
| Armstrong Creek Feeder Mains (Geelong) | 36 193 |  | .. | 282 | 35 912 |
| Armstrong Creek Sewerage Scheme (Grovedale) | 37 737 |  | .. | 277 | 37 459 |
| Ballan Channel Reconstruction (She Oaks) | 3 713 |  | .. | .. | 3 713 |
| Bannockburn Basin Lining and Covering (Bannockburn) | 2 023 |  | .. | .. | 2 023 |
| Bannockburn pump station and rising main replacement (Bannockburn) | 3 803 |  | 31 | 321 | 3 451 |
| Bannockburn Pump Stations Upgrade/ Replace (Bannockburn) | 8 333 |  | .. | .. | 8 333 |
| Bannockburn Tank (Bannockburn) | 2 825 |  | 446 | .. | 2 379 |
| Bannockburn Water Reclamation Plant – Reuse System Upgrade (Bannockburn) | 712 |  | .. | .. | 712 |
| Bannockburn West Feeder Main (Bannockburn) | 1 125 |  | .. | .. | 1 125 |
| Barwon Downs Observation Bores Refurbishment (Barwon Downs) | 385 |  | 44 | 331 | 10 |
| Barwon Heads Pump Station No. 1 Upgrade (including Rising Main) (Barwon Heads) | 5 689 |  | 323 | .. | 5 366 |
| Barwon Heads Sewer Pipe Upsizing (Barwon Heads) | 409 |  | 80 | 5 | 324 |
| Barwon Heads to Black Rock transfer main replacement (Barwon Heads) | 6 068 |  | 120 | 600 | 5 348 |
| Barwon Heads West Pump Station Construction (Barwon Heads) | 1 708 |  | 12 | 250 | 1 446 |
| BASIS Replacement (Geelong) | 12 549 |  | .. | .. | 12 549 |
| Bellarine Tank (Wallington) | 3 495 |  | 6 | .. | 3 488 |
| Bellarine Transfer Main Stage 5 (Geelong) | 15 647 |  | .. | 150 | 15 497 |
| Belmont Pump Station and Highton Interceptor Sewer Upgrade (Belmont) | 6 519 |  | .. | .. | 6 519 |
| Birregurra Sewerage Scheme (Birregurra) | 7 524 |  | .. | 307 | 7 217 |
| Birregurra Water Treatment Plant Renewal and System Upgrade (Birregurra) | 251 |  | 87 | 42 | 122 |
| Birregurra Water Treatment Plant Upgrade (Birregurra) | 546 |  | 174 | .. | 372 |
| Black Rock Water Reclamation Plant – Landscaping (Barwon Heads) |  | 1 729 | 698 | 578 | 453 |
| Black Rock Water Reclamation Plant – Replacement of plant items (Barwon Heads) |  | 6 824 | 1 172 | 505 | 5 147 |
| Callahans Channel Syphon Replacement – Stage 2 (Barwon Downs) | 1 585 |  | .. | 32 | 1 554 |
| Callahans Channel Syphon Replacement (Barwon Downs) | 463 |  | 51 | .. | 412 |
| Clifton Springs Pump Station No. 1 Upgrade (Clifton Springs) | 3 032 |  | .. | .. | 3 032 |
| Clifton Springs Pump Station No. 2 Upgrade (Clifton Springs) | 1 385 |  | .. | .. | 1 385 |
| Clifton Springs Pump Station Upgrade (Wallington) | 1 165 |  | .. | .. | 1 165 |
| Clifton Springs Rising Main No. 1 Replacement (Clifton Springs) | 10 449 |  | .. | .. | 10 449 |
| Colac No. 1 Rising Main Replacement (Colac) | 2 838 |  | 4 | 1 796 | 1 038 |
| Colac Pipeline Replacement – Future Stages (Colac) | 11 996 |  | 50 | 105 | 11 841 |
| Colac Water Treatment Plant Renewal and System Upgrade (Colac) | 829 |  | 368 | 59 | 402 |
| Computer Hardware – Infrastructure (Various) | 20 543 |  | 7 425 | 1 051 | 12 068 |
| Computer Hardware – User Requests (Various) | 3 001 |  | 1 821 | 105 | 1 075 |
| Computer Network Modelling (Various) |  | 300 | 156 | 21 | 123 |
| Corporate Buildings Refurbishment Works (Geelong) | 1 866 |  | 1 125 | 200 | 541 |
| Cowies Creek Sewerage Pump Station Upgrade (Geelong) |  | 2 359 | 128 | 900 | 1 331 |
| Dewing Creek Diversion Reinstatement (Barwon Downs) | 578 |  | .. | .. | 578 |
| Disinfection Plants – Duty/Standby Systems (Various) | 1 557 |  | 1 292 | 60 | 205 |
| Document Management System (Geelong) | 3 035 |  | 2 260 | 598 | 177 |
| Flow Metering (Various) | 747 |  | 187 | 105 | 455 |
| Flow Monitoring (Various) | 507 |  | 286 | 39 | 181 |
| Fyansford Feeder Main (Geelong) | 406 |  | 5 | 375 | 26 |
| Geelong-Melbourne Pipeline (Various) | 137 865 |  | .. | 600 | 137 265 |
| Gellibrand Water Treatment Plant Renewal and System Upgrade (Gellibrand) | 283 |  | 143 | 34 | 106 |
| Headworks Minor Asset Creation (Various) | 1 708 |  | 543 | 116 | 1 049 |
| Highton Feeder Main Replacement (Geelong) | 6 818 |  | 83 | 1 272 | 5 463 |
| Highton High Level Pump Station Upgrade (Wandana Heights) | 731 |  | .. | .. | 731 |
| Highton High Level Tank No. 2 (Wandana Heights) | 3 653 |  | .. | .. | 3 653 |
| Indented Head St Leonards Feeder Main Stage 2 (Indented Head) | 4 237 |  | .. | .. | 4 237 |
| Inlet Channel Reconstruction (Moriac) | 6 620 |  | 3 058 | 762 | 2 800 |
| Jan Juc High Level Water Supply System (Torquay) | 2 114 |  | 15 | .. | 2 099 |
| Jetty Road Feeder Main (Drysdale) | 4 601 |  | .. | .. | 4 601 |
| Korweinguboora Reservoir Embankment Upgrade (Korweinguboora) | 933 |  | .. | .. | 933 |
| Leopold Feeder Main (Leopold) | 2 480 |  | .. | 260 | 2 220 |
| Leopold Pump Station No. 1 Upgrade (Leopold) | 3 817 |  | 40 | 2 455 | 1 323 |
| Leopold Rising Main Number 1 Replacement (Geelong) | 11 641 |  | 55 | 268 | 11 318 |
| Lethbridge Water Supply Improvements (Lethbridge) | 14 732 |  | .. | .. | 14 732 |
| Lining Of Main Sewers (Various) | 26 295 |  | 16 610 | 3 728 | 5 958 |
| Lonsdale West Pump Station Construction (Point Lonsdale) | 1 703 |  | .. | 36 | 1 667 |
| Lorne No. 3 Tank Replacement (Lorne) | 1 008 |  | 908 | 10 | 90 |
| Lorne Water Treatment Plant Renewal and System Upgrade (Lorne) | 536 |  | 154 | 64 | 318 |
| Lovely Banks Basins Lining and Covering (Lovely Banks) | 6 604 |  | 25 | .. | 6 579 |
| Lower Stony Creek Reservoir Risk Reduction Works (Anakie) | 708 |  | .. | .. | 708 |
| Main Outfall Sewer Duplication (Various) | 38 254 |  | .. | .. | 38 254 |
| Mains Replacement/Rehabilitation and System Improvements (Various) | 16 787 |  | 8 778 | 2 241 | 5 768 |
| Mains Replacements (Various) | 55 735 |  | 18 562 | 4 203 | 32 971 |
| Major Mains Manhole Rehabilitation (Various) | 779 |  | 38 | 366 | 376 |
| Matilda Court Sewer Diversion Upgrade (Belmont) | 881 |  | .. | .. | 881 |
| Melaluka Road Sewer Upgrade (Leopold) | 2 930 |  | .. | .. | 2 930 |
| Meredith Water Treatment Plant Asset Renewal and System Upgrade (Meredith) | 648 |  | 399 | 48 | 201 |
| Meredith Water Treatment Plant Clarification (Meredith) | 673 |  | 46 | .. | 627 |
| Meter Replacement Program (Various) | 4 143 |  | 2 789 | 305 | 1 049 |
| Minor Reticulation Improvements (Various) | 2 677 |  | 1 774 | 168 | 735 |
| Montpellier (Basins 2 and 4) (Geelong) | 7 246 |  | 4 157 | 3 081 | 8 |
| Moolap Sewerage Scheme (Moolap) | 16 124 |  | .. | .. | 16 124 |
| Moorabool Water Treatment Plant Improvements (Moorabool) | 1 132 |  | 450 | 78 | 604 |
| New and Replacement House Connections – Sewer (Various) | 5 949 |  | 1 561 | 399 | 3 989 |
| New Replacements and Conversions (Various) | 5 493 |  | 2 108 | 378 | 3 006 |
| Northern Flow Retarding Facility Stage 2 (Geelong) | 3 237 |  | 577 | 2 650 | 10 |
| Northern Water Reclamation Plant (Geelong) | 89 407 |  | 187 | 1 310 | 87 910 |
| Ocean Grove Banks Road Pump Station Construction (Ocean Grove) | 1 628 |  | .. | .. | 1 628 |
| Ocean Grove North Feeder Mains (Wallington) | 1 190 |  | .. | .. | 1 190 |
| Ocean Grove North Pump Station (Wallington) | 695 |  | .. | .. | 695 |
| Ocean Grove Pump Station No. 1 Upgrade (Ocean Grove) | 756 |  | 84 | 245 | 427 |
| Ocean Grove Pump Station No. 2 Upgrade (Ocean Grove) | 2 106 |  | 102 | 260 | 1 743 |
| Ocean Grove Pump Station No. 3 Upgrade (Ocean Grove) | 676 |  | .. | .. | 676 |
| Ocean Grove Pump Station No. 4 Upgrade (Ocean Grove) | 3 135 |  | 282 | 1 300 | 1 553 |
| Ocean Grove Rising Main No. 1 Duplication (Ocean Grove) | 389 |  | .. | .. | 389 |
| Ocean Grove Rising Main No. 2 Upgrade (including. bridge crossing) (Ocean Grove) | 8 350 |  | .. | 112 | 8 238 |
| Odour and Corrosion Programs (Various) | 2 360 |  | 766 | 159 | 1 435 |
| Office Building Mechanical Services (Various) | 1 452 |  | 1 216 | 21 | 215 |
| Office Furniture And Equipment (Various) | 815 |  | 580 | 21 | 214 |
| OH&S Items (Various) | 1 218 |  | 590 | 116 | 512 |
| Olangolah Reservoir – Embankment and Spillway (Gellibrand) | 1 050 |  | 1 027 | 20 | 3 |
| Outfall to Ovoid Cross Connection Booster Pump Station (Geelong) | 3 769 |  | .. | .. | 3 769 |
| Ovoid Sewer Replacement Racecourse to Carr Street (Geelong) | 4 747 |  | .. | .. | 4 747 |
| Painkalac Reservoir – Embankment (Aireys Inlet) | 2 380 |  | 252 | .. | 2 128 |
| PeopleSoft Upgrade (Various) | 1 150 |  | .. | 1 150 | .. |
| Pettavel and Highton Basin Road Construction (Geelong) | 692 |  | .. | .. | 692 |
| Pettavel Basin Cover Replacement (Waurn Ponds) | 1 037 |  | .. | .. | 1 037 |
| Plant and Machinery (Geelong) | 5 355 |  | 3 826 | 362 | 1 166 |
| Portarlington Pump Station No. 1 Upgrade (Portarlington) | 971 |  | .. | .. | 971 |
| Portarlington Pump Station No. 6 Upgrade (Portarlington) | 816 |  | .. | .. | 816 |
| Portarlington Rising Main No. 1 Replacement (Portarlington) | 4 742 |  | .. | .. | 4 742 |
| Portarlington Water Reclamation Plant Reuse Upgrade (Portarlington) | 5 188 |  | .. | .. | 5 188 |
| Portarlington Water Reclamation Plant Treatment Plant Upgrade (Portarlington) | 979 |  | .. | .. | 979 |
| Portarlington-Clifton Springs Rising Main Construction (Portarlington) | 11 472 |  | .. | .. | 11 472 |
| Portarlington-Clifton Springs Transfer Pump Station Construction (Portarlington) | 1 145 |  | .. | .. | 1 145 |
| Printing and Photocopying Equipment (Various) | 258 |  | 151 | 11 | 96 |
| Point Lonsdale Feeder Main (Point Lonsdale) | 499 |  | .. | .. | 499 |
| Pump Replace (Geelong and Otway) (Various) | 2 988 |  | 1 470 | 215 | 1 303 |
| Pump Station OH&S Issues (Various) | 1 696 |  | 516 | 122 | 1 058 |
| Queenscliff Basins – Lining and Covering (Queenscliff) | 3 707 |  | 557 | 3 145 | 5 |
| Queenscliff Pump Station No. 4 Upgrade (Queenscliff) | 678 |  | 26 | 34 | 618 |
| Queenscliff Rising Main No. 4 Replacement (Queenscliff) | 1 142 |  | .. | .. | 1 142 |
| Queenscliff Transfer Main Replacement (Wallington) | 5 578 |  | .. | .. | 5 578 |
| Queenscliff-Ocean Grove Rising Main Replacement (Point Lonsdale) | 4 635 |  | .. | 97 | 4 537 |
| Regional Treat Plants – Minor Improvements (Various) | 4 682 |  | 1 870 | 260 | 2 551 |
| Replacement House Connections – Water (Various) | 4 948 |  | 705 | 357 | 3 886 |
| Sewer level and flow monitoring facilities (Various) | 798 |  | .. | 27 | 771 |
| Sewer Reticulation Improvements (Various) | 4 519 |  | 1 455 | 308 | 2 756 |
| Shannon Avenue Feeder Main Replacement (Geelong) | 1 574 |  | 1 490 | 84 | .. |
| Shared Sewerage Assets (<300mm) (Various) | 8 164 |  | 33 | 610 | 7 521 |
| Shared Water Reticulation Assets (Various) | 11 811 |  | 21 | 1 050 | 10 740 |
| South East Feeder Main (Geelong) | 310 |  | 80 | 230 | .. |
| Spatial Information Equipment (Various) | 466 |  | 237 | 11 | 219 |
| Switchboard Replacements (Various) | 1 740 |  | 1 156 | 108 | 476 |
| Torquay – Horseshoe Bend Road sewer Stage 2 (Torquay) | 911 |  | 418 | .. | 493 |
| Torquay High Level Feeder Mains Stage 2 (Torquay) | 14 235 |  | 3 | 980 | 13 252 |
| Torquay High Level Tank (Torquay) | 5 662 |  | .. | .. | 5 662 |
| Torquay Pump Station Upgrade No. 1 (Torquay) | 947 |  | 867 | 80 | .. |
| Vehicles (Geelong) | 37 473 |  | 18 057 | 2 600 | 16 815 |
| Water Leakage Reduction (Various) | 1 481 |  | 270 | 142 | 1 069 |
| Water Main Replacements – Feeder Mains (Various) | 10 016 |  | 17 | 318 | 9 680 |
| Waurn Ponds Feeder Main (Geelong) | 1 133 |  | 162 | 945 | 26 |
| Weddell Road Syphon Duplication (North Geelong) | 655 |  | .. | .. | 655 |
| West Barwon Outlet Tower Reinforcement (Forrest) | 643 |  | .. | .. | 643 |
| West Gellibrand Reservoir Upgrade (Forrest) | 2 040 |  | .. | .. | 2 040 |
| Western Gully Submain relief sewer (Geelong) | 531 |  | .. | .. | 531 |
| Winchelsea Feeder Main Replacement (Winchelsea) | 2 040 |  | 23 | 80 | 1 937 |
| Winchelsea Sewerage System Upgrades (Winchelsea) | 1 475 |  | .. | .. | 1 475 |
| Winchelsea Water Reclamation Plant Upgrade (Winchelsea) | 287 |  | 73 | 204 | 10 |
| Wurdee Boluc Reservoir East Embankment Upgrade (Winchelsea) |  | 470 | .. | .. | 470 |
| Wurdee Boluc Water Treatment Plant Lime Clarification (Winchelsea) | 687 |  | 25 | 651 | 11 |
| Wurdee Boluc Water Treatment Plant UV Disinfection (Winchelsea) | 2 557 |  | .. | .. | 2 557 |
| Wurdee Buloc Renewal and System Upgrade (Moriac) | 2 718 |  | 1 855 | 142 | 721 |
| Wurdee Buloc Separate Backwash and Filter (Moriac) | 6 375 |  | 4 420 | 1 929 | 26 |
| Wye River and Separation Creek Sewerage Scheme (Wye River) | 5 386 |  | .. | .. | 5 386 |
| Total existing projects | 1 019 880 |  | 142 296 | 79 906 | 797 678 |

Source: Barwon Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Barwon Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Colac Water Treatment Plant Coagulant Storage and Delivery Area (Colac) | 264 | .. | 251 | 13 |
| Construction of Barwon Heads No. 11 Sewage Pump Station (Barwon Heads) | 2 062 | 36 | 170 | 1 855 |
| Distribution – Minor Projects and Improvements (Various) | 1 756 | 446 | 101 | 1 210 |
| Fluoridation (Various) | 5 297 | 90 | 3 090 | 2 117 |
| Plant Centre Relocation (Connewarre) | 534 | .. | 300 | 234 |
| Water Main Improvements (Various) | 371 | 3 | 365 | 3 |
| Total new projects | 10 285 | 575 | 4 277 | 5 433 |
| Total Barwon Region Water Corporation projects | 1 030 165 | 142 871 | 84 183 | 803 111 |

Source: Barwon Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Central Gippsland Regional Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Agricultural Minor Works (Various) | 943 |  | 243 | 70 | 630 |
| Asset Drawing Upgrades (Corporate) | 450 |  | .. | 50 | 400 |
| Boolarra Water Supply Augmentation (Boolarra) | 2 494 |  | 336 | 1 904 | 254 |
| Brodribb Road Pump Station Improvements (Morwell/Churchill) | 428 |  | 4 | 424 | .. |
| Buckleys Hill Upgrade Works – Construction (Morwell) | 5 000 |  | .. | .. | 5 000 |
| Buckleys Hill Upgrade Works – Documentation (Morwell) | 500 |  | .. | .. | 500 |
| Bulk Waste Water Minor Capital Projects (Various) | 871 |  | 196 | 75 | 600 |
| Bulk Water Minor Capital Projects (Various) | 1 080 |  | 330 | 75 | 675 |
| Buln Buln High Level Pump Station Upgrade (Warragul/Drouin) | 247 |  | 30 | 191 | 26 |
| Buln Buln high level tank relocation (Buln Buln) | 847 |  | .. | .. | 847 |
| Cathodic Protection on Gippsland Water Assets (Various) | 898 |  | 268 | 70 | 560 |
| Cathodic Protection on Saline Water Outfall Pumps Assets (Sale) | 323 |  | 53 | 30 | 240 |
| Channel and Saline pipe diversion (Various) | 250 |  | .. | .. | 250 |
| Communications Infrastructure (Various) | 355 |  | 175 | 20 | 160 |
| Continued Software Development of Supervisory Control And Data Acquisition (SCADA) (Various) | 2 128 |  | 328 | 200 | 1 600 |
| Coongulla clear water storage basin liner installation (Coongulla) | 678 |  | 102 | 508 | 68 |
| Corporate Systems (Traralgon) | 2 535 |  | 105 | 220 | 2 210 |
| Customer Information and Billing System (Various) | 4 468 |  | 2 668 | 250 | 1 550 |
| Customer Meter replacements (Various) | 5 513 |  | 1 913 | 400 | 3 200 |
| Department of Infrastructure – Review of Security Risk Management in Victoria's Energy Industries (Various) | 554 |  | 104 | 50 | 400 |
| Desludging Program – Agribusiness (Dutson) | 1 330 |  | .. | 100 | 1 230 |
| Desludging Program – Resource Recovery Facility (Dutson) | 750 |  | .. | 750 | .. |
| Desludging Program – Treatment Group (Various) | 750 |  | .. | 350 | 400 |
| Drouin Sewerage – Outfall Augmentation (Drouin) | 1 695 |  | .. | .. | 1 695 |
| Drouin Waste Water – Gravity/Rising Main and Sewer Pump Station Upgrade (Drouin) | 2 808 |  | 683 | 524 | 1 601 |
| Drouin Waste Water Treatment Plant – Membrane or Reverse Osmosis treatment (Drouin) |  | 3 387 | .. | 102 | 3 285 |
| Drouin Waste Water Treatment Plant – Provision of Primary Screen and Grit Removal System (Drouin) |  | 425 | .. | .. | 425 |
| Duplicate ESSO line from tank pond (Longford) | 1 000 |  | .. | .. | 1 000 |
| Dutson – ESSO Saline Pond to No. 2 Pond Pipeline Duplication (Dutson Downs) | 1 187 |  | .. | .. | 1 187 |
| Dutson Downs Farm: Fodder Storage (Dutson) | 581 |  | 341 | 60 | 180 |
| Dutson ESSO Pond – Leachate Return System Upgrade (Dutson) | 247 |  | 42 | .. | 205 |
| Emerging Back Log Schemes Water – Connection Upgrades (Various) | 600 |  | 150 | 50 | 400 |
| Emerging Back Log Schemes Water – Main Extensions (Various) | 1 154 |  | 524 | 70 | 560 |
| Emerging Backlog Wastewater Schemes – Connection Upgrades (Various) | 571 |  | 121 | 50 | 400 |
| Emerging Backlog Wastewater Schemes – Main Extension (Various) |  | 1 145 | 500 | 70 | 575 |
| Field Operation Depot Expansion (Traralgon) | 250 |  | .. | 250 | .. |
| Fixing of Lined Basins which have lifted (Various) | 1 017 |  | .. | .. | 1 017 |
| Fleet – Agribusiness Tractors Combine Harvestor (Dutson Downs) | 1 560 |  | 210 | .. | 1 350 |
| Fleet – Dutson Downs: Articulated Loader and Backhoe and Tractor (Duston Downs) | 1 056 |  | 127 | .. | 929 |
| Fleet Purchases (Various) | 17 782 |  | 7 150 | 1 158 | 9 474 |
| Geographic Information System (Web Based Deployment) (Various) | 1 295 |  | 215 | 150 | 930 |
| Gippsland Water Factory Stage 1 (Various) | 173 900 |  | 145 198 | 28 702 | .. |
| Gippsland Water Factory – Mini Hydro and Biogas Generation Projects (Gippsland) | 4 300 |  | .. | 4 300 | .. |
| Gippsland Water Factory – Multi Function Amenities Centre (Morwell) |  | 4 900 | .. | 4 900 | .. |
| Hazelwood No. 5 Storage Upgrade (Various) | 526 |  | 1 | .. | 525 |
| Hydraulically powered high lift pump (Traralgon) | 509 |  | .. | .. | 509 |
| Improvements for System Security Transfer and Process Capital Projects (Various) | 438 |  | 96 | 38 | 304 |
| Information Technology Hardware Upgrades (Various) | 2 751 |  | 891 | 260 | 1 600 |
| Install Sewer Openings at Property Boundaries (Various) | 1 596 |  | 324 | 132 | 1 140 |
| Irrigation Minor Works (Various) | 450 |  | .. | 50 | 400 |
| IT Infrastructure (Various) | 430 |  | 75 | 35 | 320 |
| Labertouche Watermain Condition Renewal (Various) | 1 022 |  | 13 | 23 | 986 |
| Lining and Covering of Service Basins – Clarkes Road No. 1 Service Basin (Hazelwood North) | 425 |  | .. | .. | 425 |
| Lining and Covering of Service Basins – Mirboo North Service Basin (Mirboo North) | 425 |  | .. | .. | 425 |
| Lining and Covering of Service Basins – Yallourn North Service Basin (Yallourn North) | 425 |  | .. | .. | 425 |
| Maffra Waste Water Stage 2 – Princes Street Sewer Pump Station and Rising Main (Maffra) | 1 948 |  | .. | .. | 1 948 |
| Maffra Waste Water Stage 3 – Rising Maing and Sewer (Maffra) | 572 |  | .. | .. | 572 |
| Maffra Water Treatment Plant – New Sludge Handling System (Maffra) | 509 |  | 77 | 381 | 51 |
| Maffra Water Treatment Plant Upgrade (Maffra) | 3 048 |  | .. | .. | 3 048 |
| Mainpac Replacement (Various) | 1 022 |  | 102 | 600 | 320 |
| Major Client – Pressure Reduction and Replacement (Morwell) | 3 216 |  | 177 | 376 | 2 663 |
| Management Information Systems/Portal (Various) | 313 |  | 73 | 50 | 190 |
| Mechanical and Electrical costs along the Regional Outfall Sewer (Various) | 1 575 |  | .. | 150 | 1 425 |
| Mirboo North High Level Pump Station upgrade (Mirboo North) | 258 |  | 2 | 39 | 217 |
| Mirboo North Water Rising Main Replacement (Mirboo North) | 3 387 |  | .. | .. | 3 387 |
| Mirboo North Water Supply – Augmentation with Groundwater Supply (Mirboo North) | 1 695 |  | .. | .. | 1 695 |
| Mobile Car Kit Replacements (Various) | 262 |  | 82 | 20 | 160 |
| Modifications to Dutson No. 2 Lagoon Channel and ESSO to No. 2 Saline Pipe Diversion (Longford) | 425 |  | .. | 64 | 361 |
| Moe Waste Water – Western Branch Augmentation (Moe) | 3 387 |  | .. | .. | 3 387 |
| Moe Waste Water Decomm Sewer Pump Station and Construct Shared Gravity Main (Moe) | 933 |  | .. | .. | 933 |
| Moe Waste Water Treatment Plant: New Ultra Violet Unit (Moe) | 427 |  | 2 | .. | 425 |
| Moe Water Supply – Augmentation with Groundwater Supply (Moe) | 8 465 |  | .. | 85 | 8 380 |
| Moe Water Supply – Coach Road Tank System Upgrade (Moe) | 1 356 |  | .. | .. | 1 356 |
| Moe Water Supply – Moe South Tank Upgrade (Moe) | 509 |  | 77 | 381 | 51 |
| Moe Water Supply – Replacement of Tanjil raw water pumps (Moe) | 1 695 |  | .. | .. | 1 695 |
| Moe Water Treatment Plant – Cover Clarifiers (Moe) | 425 |  | .. | .. | 425 |
| Moe Water Treatment Plant – Moe Reticulation Low Level Basin (Moe) | 769 |  | 692 | 77 | .. |
| Moe Water Treatment Plant – Sludge Handling System (Moe) | 678 |  | 102 | 508 | 68 |
| Moe Waste Water Treatment Plant – Install tertiary filters on final effluent stream (Moe) | 8 041 |  | .. | .. | 8 041 |
| Moe/Newborough Waste Water Trunk Sewer Upgrade (Moe) | 4 080 |  | 16 | .. | 4 064 |
| Moondarra Dam Risk Management Plan works (Moondarra) | 650 |  | 200 | 50 | 400 |
| Moondarra Upgrade Works – Construction (Moondarra) | 5 000 |  | .. | .. | 5 000 |
| Moondarra Upgrade Works – Documentation (Moondarra) | 500 |  | .. | .. | 500 |
| Morwell High Level System Upgrade (Morwell/Churchill) | 341 |  | 2 | 51 | 288 |
| Morwell Waste Water Treatment – Provide Grit Removal System (Morwell) | 425 |  | .. | .. | 425 |
| Morwell Water Supply – Churchill Distribution Main Duplication (Morwell) | 1 695 |  | .. | .. | 1 695 |
| Morwell Water Treatment Plant – Erect roofing over clarifiers (Morwell) | 1 017 |  | .. | .. | 1 017 |
| Morwell Waste Water Treatment Plant – Install tertiary solids filter (sand filter, membrane) (Morwell) | 5 079 |  | .. | .. | 5 079 |
| Neerim South – Waste Water Treatment Plant Upgrade (Neerim South) | 5 079 |  | .. | .. | 5 079 |
| Neerim South Reticulation Main Duplication (Neerim South) | 339 |  | .. | .. | 339 |
| New – Water Quality Improvement Minor Works (Various) | 3 136 |  | 1 002 | 231 | 1 903 |
| New Intranet Software (Various) | 490 |  | 140 | 50 | 300 |
| New minor Capex resulting from Annual reviews of Dams (Moondarra) | 1 000 |  | 100 | 100 | 800 |
| New Nojee service tank (Noojee) | 847 |  | .. | .. | 847 |
| Nilma – Darnum Water Main Augmentation (Bonlac Expansion) (Nilma) | 1 560 |  | 193 | 1 206 | 161 |
| No. 2 Storage Upgrade – Modification for new waste stream (Dutson) | 250 |  | .. | 250 | .. |
| No Till Sowing Machinery (Duston Downs) | 400 |  | .. | .. | 400 |
| Occupational Health and Safety – Heavy Manhole replacement (Various) | 646 |  | 196 | 50 | 400 |
| Odour Issue with Toongabbie/ Glengarry/Marshalls Road East Waste Water Supply (Various) | 1 525 |  | .. | .. | 1 525 |
| Pine Gully Upgrade Works – Construction (Yallourn North) | 2 000 |  | .. | .. | 2 000 |
| Pressure Reduction Improvements (Various) | 1 136 |  | 1 | 120 | 1 015 |
| Raw Water Metering Project (Various) | 465 |  | 15 | 50 | 400 |
| Rawson Waste Water Treatment Plant – Tertiary Filters (Rawson) | 3 387 |  | .. | .. | 3 387 |
| Regional Outfall Sewer Upgrade Works (Various) | 2 260 |  | 290 | 200 | 1 770 |
| Replace 5km of Saline Waste Outfall Sewer Pipe at McGaurans (Various) | 5 000 |  | .. | .. | 5 000 |
| Replace or Rehab Sale Rising Main across the Sale Common and Latrobe River (Sale) | 1 684 |  | 40 | 204 | 1 440 |
| Replace remaining Pre Stressed Concrete pipe along DG Main (Various) | 2 000 |  | .. | .. | 2 000 |
| Replacement of Furniture (Various) | 524 |  | 189 | 70 | 265 |
| Replacement of Head Quarters air-conditioning unit (Traralgon) | 1 510 |  | 1 010 | .. | 500 |
| Replacement of Regional Outfall Sewer Creek Crossings (Various) | 885 |  | 785 | 100 | .. |
| Reticulation Asset Upsizing Projects – Wastewater Water Plan II (Various) | 1 660 |  | 600 | 132 | 928 |
| Reticulation Renewals (Various) | 23 145 |  | 4 245 | 2 100 | 16 800 |
| Sale Water Treatment Plant Upgrade (Sale) | 6 772 |  | .. | .. | 6 772 |
| Sale Waste Water Station – Sale No. 1 Sewer Pump Station Upgrade for Odour Control (Sale) | 5 079 |  | .. | .. | 5 079 |
| Sale/Fulham Irrigation Infrastructure (Sale) | 1 905 |  | .. | 670 | 1 235 |
| Saline Waste Outfall Pipeline Water Recycling System (Option) (Various) | 55 849 |  | .. | .. | 55 849 |
| Supervisory Control and Data Acquisition on Regional Outfall Sewer (Various) | 450 |  | .. | 50 | 400 |
| Seaspray (New Tank) Merrimans Creek Pump Station Upgrade (Seaspray) | 944 |  | 262 | 682 | .. |
| Seaspray Waste Water System – Raw Water Storage Basin (Seaspray) | 1 083 |  | 165 | 810 | 108 |
| Security Program (Various) | 7 650 |  | .. | 850 | 6 800 |
| Sewer Backlog Programme (Various) | 3 060 |  | .. | 340 | 2 720 |
| Sewer Camera Purchase of Cables and Replacement of Camera Head (Various) | 404 |  | 24 | 100 | 280 |
| Sewer pump Station Renewals and Augmentation (Various) | 22 647 |  | 647 | 2 000 | 20 000 |
| Sewer Reticulation Customer Charter Initiative – Minor Capital Projects (Various) | 3 098 |  | 434 | 145 | 2 519 |
| Sewer Reticulation Upgrades – All Systems (Various) | 15 462 |  | 1 462 | 1 000 | 13 000 |
| Sewermain upgrade – Mountain View Estate Moe (Moe) | 678 |  | .. | .. | 678 |
| Shared Asset Projects (Various) | 11 800 |  | .. | .. | 11 800 |
| Software Development of Supervisory Control And Data Acquisition – Emergency Backup system (Various) |  | 263 | 197 | .. | 66 |
| Software upgrade – Microsoft office (Corporate) | 700 |  | 250 | 100 | 350 |
| Soil and Organic Recycling Facility Stage 2 – Construct 3 in Vessel Composting Units (Dutson) | 1 356 |  | .. | 41 | 1 315 |
| Supply and Distribution Security Improvement Works (Various) | 4 806 |  | 610 | 339 | 3 858 |
| System Security Improvements for Water Supplies Minor Projects – Planning and Development (Various) | 717 |  | 87 | 70 | 560 |
| Thorpdale Water Supply – Replacement with Groundwater Supply (Thorpdale) | 847 |  | 127 | 635 | 85 |
| Toongabbie Disinfection Relocation (Toongabbie) | 509 |  | .. | .. | 509 |
| Transfer Main Renewal Project (Various) | 4 550 |  | 50 | 500 | 4 000 |
| Transfer Main System Improvement Projects (Various) | 4 550 |  | 50 | 500 | 4 000 |
| Traralgon Sewer Pump Station and Rising Main for Eastern Industrial Development (Traralgon) | 2 452 |  | 77 | 2 095 | 280 |
| Traralgon Water Treatment Plant – Cover sludge lagoons (Traralgon) | 425 |  | .. | .. | 425 |
| Traralgon Water Treatment Plant – Sludge Dewatering System (Traralgon) | 1 356 |  | .. | .. | 1 356 |
| Treated Water Tank Replacement Projects (Various) | 1 804 |  | 4 | 200 | 1 600 |
| Unplanned Capex Projects for Water – Asset Improvement Group (Various) |  | 364 | 22 | 38 | 304 |
| Unplanned Plant Failures for Wastewater, e.g. Pumps, Instruments, Plant Component Failures (Various) | 7 622 |  | 972 | 650 | 6 000 |
| Unplanned Wastewater Project Works (Various) | 342 |  | .. | 38 | 304 |
| Upgrade Firmins Lane Pump Station (Morwell) | 350 |  | .. | .. | 350 |
| Upgrade Hazelwood Emergency Storage Pump Station (Hazelwood) | 350 |  | .. | 350 | .. |
| Upgrade Maintenance Holes pits along Tyers River Conduit (Various) | 800 |  | .. | .. | 800 |
| Upgrade of Non Water and Waste Infrastructure (Various) | 1 944 |  | 514 | 150 | 1 280 |
| Upgrade steel lids on manholes (Various) | 707 |  | 167 | 60 | 480 |
| Upgrade Saline Water Outfall Pipeline pumps (Various) | 500 |  | .. | .. | 500 |
| Upgrade Tunnel section along Tyers River Conduit (Various) | 500 |  | .. | .. | 500 |
| Upgrade Tyers River Pump Station (Tyers) | 500 |  | .. | .. | 500 |
| Various Sewer Pump Stations – Install Telemetry (Various) | 751 |  | 76 | 75 | 600 |
| Warragul/Drouin Water Supply – Queen Street Water Main Extension (Warragul/Drouin) | 411 |  | 50 | 318 | 43 |
| Warragul High Level System Upgrade (Warragul) | 339 |  | .. | .. | 339 |
| Warragul Sewer – North East Augmentation (Warragul) | 1 526 |  | 1 | .. | 1 525 |
| Warragul Waste Water Treatment Plant – Sludge Dewatering (Warragul) | 2 412 |  | 2 195 | 110 | 107 |
| Warragul Waste Water Treatment Plant – Upgrade for tertiary filtration (Warragul) | 8 041 |  | .. | .. | 8 041 |
| Warragul Waste Water Treatment Plant Pump Station No. 2 – Rising Main Upgrade (Warragul) | 2 590 |  | 505 | 2 085 | .. |
| Warragul Waste Water – Howitt St Main Sewer Augmentation, Flow Retardation and Attenuation Basin (Warragul) | 1 601 |  | 198 | 1 238 | 165 |
| Warragul Water Supply – Connection to Moe System Stage 1 (Yarragon to Darnum) | 4 232 |  | 7 | 119 | 4 106 |
| Warragul Water Supply Distribution System Duplication (Warragul) | 8 465 |  | .. | .. | 8 465 |
| Warragul Water System – Connection to Moe System – (Darnum to Warragul South) | 3 809 |  | 1 | .. | 3 808 |
| Warragul Waste Water – Hazel Creek Trunk sewer Stage 1 (Warragul) | 7 109 |  | 9 | .. | 7 100 |
| Warragul Waste Water – Hazel Creek Trunk sewer Stage 2 (Warragul) | 2 400 |  | .. | .. | 2 400 |
| Warragul Waste Water Treatment Plant – Electronic switch room. Extend to accommodate aerators in old pump station (Warragul) | 328 |  | 40 | 254 | 34 |
| Water by Agreement – Main Extension Projects (Various) | 940 |  | 40 | 100 | 800 |
| Water Quality Database (Various) | 485 |  | 100 | 10 | 375 |
| Water Resource Systems Upgrade (Various) | 1 950 |  | 100 | 200 | 1 650 |
| Water Reticulation Improvement Minor Works (Various) | 2 418 |  | 820 | 145 | 1 453 |
| Water Treatment Minor Capital Projects (Various) | 12 520 |  | 2 720 | 1 000 | 8 800 |
| Wet Well Washer Installation – approx 10 per year for 5 years (Various) | 416 |  | 216 | 50 | 150 |
| Willow Grove Waste Water Treatment Plant – Purchase travelling irrigator (Willow Grove) | 339 |  | .. | .. | 339 |
| Yallourn North Sewerage Pump Station Rising Main Replacement (Yallourn North) | 1 695 |  | .. | .. | 1 695 |
| Yallourn Service Basin Pipework Upgrade (Yallourn) | 1 020 |  | 12 | 889 | 119 |
| Total existing projects | 628 872 |  | 187 138 | 73 362 | 368 373 |

Source: Central Gippsland Regional Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Central Gippsland Regional Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Soil Organic Recycling Facility – Windrow Turner (Dutson Downs) | 500 | .. | 500 | .. |
| Total new projects | 500 | .. | 500 | .. |
| Total Central Gippsland Regional Water Corporation projects | 629 372 | 187 138 | 73 862 | 368 373 |

Source: Central Gippsland Regional Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Central Highlands Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Asset Management System – Implementation (Ballarat) | 3 912 |  | 1 040 | 696 | 2 176 |
| Billing System Enhancements (Ballarat) | 686 |  | 227 | 109 | 350 |
| Data Collection Systems – Telemetry Pt 2 (Various) | 2 583 |  | 1 553 | 213 | 817 |
| Environmental Management System Implementation (Ballarat) | 900 |  | 263 | 84 | 553 |
| Farm Reuse Projects (Various) | 7 649 |  | 6 483 | .. | 1 166 |
| Goldfields Superpipe – Ballarat Interconnect (Ballarat) | 178 676 |  | 129 582 | 25 318 | 23 776 |
| Information Management Implementation (Ballarat) | 3 122 |  | 311 | 869 | 1 942 |
| Information technology Infrastructure (Ballarat) | 4 334 |  | 1 178 | 747 | 2 409 |
| Land Development – Developer Augmentations (Various) | 4 779 |  | 1 920 | 527 | 2 332 |
| Offices Upgrade (Ballarat) | 595 |  | 322 | .. | 273 |
| Plant and equipment (Ballarat) | 18 475 |  | 4 913 | 2 375 | 11 187 |
| Sewerage Collection System Upgrade (Ballarat) | 24 764 |  | 5 673 | 1 302 | 17 789 |
| Sewerage Collection System Upgrade (Daylesford) | 2 227 |  | 444 | 232 | 1 551 |
| Sewerage Treatment Plant Upgrade and Reuse (Beaufort) | 4 236 |  | 195 | 50 | 3 991 |
| Sewerage Treatment Plant Upgrade and Reuse (Daylesford) | 3 173 |  | 1 722 | .. | 1 451 |
| Sewerage Treatment Plant Upgrade and Reuse (Maryborough) | 937 |  | 12 | 71 | 854 |
| Waste Water Reticulation and Treatment Scheme (Blackwood) | 7 017 |  | 155 | 210 | 6 652 |
| Waste Water Reticulation and Treatment Scheme (Gordon) | 3 967 |  | 121 | 200 | 3 646 |
| Waste Water Reticulation and Treatment Scheme (Smythesdale) | 4 883 |  | 180 | 540 | 4 163 |
| Waste Water Reticulation and Treatment Scheme (Waubra) | 1 801 |  | 188 | 490 | 1 123 |
| Waste Water Reticulation Replacements (Various) | 1 855 |  | 545 | .. | 1 310 |
| Waste Water Re-Use (Ballarat North) | 7 188 |  | 2 505 | 4 683 | .. |
| Waste Water Treatment Plant Improvements (Daylesford) | 375 |  | .. | .. | 375 |
| Waste Water treatment Plant Upgrade – Ballarat North and Creswick (Ballarat) | 55 771 |  | 38 981 | 10 536 | 6 254 |
| Water Meters Purchase (Various) | 906 |  | 271 | 117 | 518 |
| Water Meters Replacement (Various) | 3 325 |  | 980 | 421 | 1 924 |
| Water Quality Improvements (Various) | 3 769 |  | 291 | 531 | 2 947 |
| Water Resource Security (Maryborough Catchment Entitlements) |  | 2 547 | 2 327 | .. | 220 |
| Water Resource Security (Other Districts) (Various) | 2 676 |  | 593 | 962 | 1 121 |
| Water Reticulation Replacement (Ballarat) | 14 779 |  | 5 697 | 1 460 | 7 622 |
| Water Supply (Tanks, Control Valves) Renew (Various) | 7 294 |  | 2 417 | 1 020 | 3 857 |
| Water Treatment Plant Upgrade (Avoca) | 5 598 |  | 200 | 230 | 5 168 |
| Water Treatment Plant Upgrade (Landsborough) | 698 |  | 96 | .. | 602 |
| Total existing projects | 385 497 |  | 211 385 | 53 993 | 120 119 |

Source: Central Highlands Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Central Highlands Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Headworks Improvements – Construction (Ballarat) | 11 541 | 2 165 | 1 052 | 8 324 |
| Water Resource Security – Construction (Various) | 3 124 | 1 910 | 258 | 956 |
| Water Treatment Plant – Upgrade (Daylesford) | 505 | 157 | 331 | 17 |
| Water Treatment Plant – Upgrade (Maryborough) | 1 766 | 304 | 816 | 646 |
| Water Treatment Plant – Upgrade (Various) | 2 835 | 957 | 909 | 969 |
| Total new projects | 19 771 | 5 493 | 3 366 | 10 912 |
| Total Central Highlands Region Water Corporation projects | 405 268 | 216 878 | 57 359 | 131 031 |

Source: Central Highlands Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Coliban Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Buildings and Land – Construct (Bendigo) | 4 607 |  | 1 175 | 1 716 | 1 716 |
| Buildings and Land – Purchase (Various) | 706 |  | 53 | 331 | 322 |
| Buildings and Land – Upgrade (Bendigo) | 2 986 |  | 297 | 39 | 2 650 |
| Goldfields Superpipe – Bendigo Interconnect (Bendigo) | 71 848 |  | 69 712 | 2 136 | .. |
| Office Equipment – Replace (Bendigo) | 1 265 |  | 215 | 225 | 825 |
| Recycled Water Pipeline – Construction (Bendigo) | 37 000 |  | 36 301 | .. | 699 |
| Sewer Rising Mains – Replacement (Various) | 804 |  | 132 | 107 | 566 |
| Sewer Software Model – Purchase (Bendigo) | 1 014 |  | 800 | 214 | .. |
| Software – Upgrade (Bendigo) | 7 986 |  | 2 053 | 1 161 | 4 772 |
| Trunk Wastewater Main – Replace (Bendigo) | 7 271 |  | 991 | 671 | 5 609 |
| Wastewater Main Shared Assets – Construct (Bendigo) | 17 250 |  | 1 449 | 427 | 15 374 |
| Wastewater Pumping – Construction (Castlemaine) | 1 164 |  | 310 | 854 | .. |
| Wastewater Pumping – Replacement (Echuca) | 2 719 |  | 989 | 1 730 | .. |
| Wastewater Scheme – Construct (Korong Vale) | 4 149 |  | .. | .. | 4 149 |
| Wastewater Scheme – Construct (Newbridge) | 721 |  | .. | .. | 721 |
| Wastewater Treatment – Upgrade (Castlemaine) | 8 941 |  | 6 000 | 2 941 | .. |
| Wastewater Treatment Compliance – upgrade (Various) | 27 367 |  | 186 | .. | 27 181 |
| Wastewater Treatment Fencing – replace (Various) | 579 |  | 24 | .. | 555 |
| Water Channel – Upgrade (Various) | 136 716 |  | 823 | 2 136 | 133 757 |
| Water Distribution – Purchase (Bendigo) | 53 939 |  | 24 557 | 18 687 | 10 695 |
| Water Main – Upgrade (Various) | 3 471 |  | 200 | 221 | 3 050 |
| Water Main Shared Assets – Construct (Bendigo) |  | 16 340 | 289 | 427 | 15 624 |
| Water Meter – Replace (Bendigo) | 1 222 |  | 608 | .. | 614 |
| Water Pipeline – Construct (Axedale) | 2 649 |  | 1 345 | 1 304 | .. |
| Water Reservoir – Construct (Malmsbury) | 549 |  | 516 | 6 | 26 |
| Water Reservoir Compliance – Upgrade (Malmsbury) | 4 037 |  | 25 | .. | 4 013 |
| Water Reservoir Fencing – Construct (Malmsbury) | 879 |  | 7 | 175 | 696 |
| Water Software Model – Purchase (Bendigo) | 987 |  | 400 | 587 | .. |
| Water Tank – Replace (Boort) | 1 250 |  | 626 | 624 | 1 |
| Water Tank – Replace (Leitchville) | 1 701 |  | 153 | 1 548 | .. |
| Water Tank OH&S – Construct (Various) | 886 |  | 330 | .. | 556 |
| Water Treatment – Construct (Rochester) | 1 478 |  | .. | .. | 1 478 |
| Water Treatment – Upgrade (Tooborac) | 807 |  | .. | 68 | 739 |
| Water Treatment Quality – Upgrade (Various) | 28 233 |  | 6 877 | 10 678 | 10 678 |
| Total existing projects | 453 521 |  | 157 443 | 49 012 | 247 067 |

Source: Coliban Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Coliban Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Buildings and Land OH&S – Construction (Bendigo) | 562 | .. | 85 | 477 |
| Disaster Recovery Software – Upgrade (Bendigo) | 545 | 331 | 214 | .. |
| High Lift Water Pump Station – Replacement (Rochester) | 2 038 | .. | 2 038 | .. |
| Office Communication Hardware – Replacement (Bendigo) | 249 | .. | 249 | .. |
| Recycled Water Pipeline – Construction (Heathcote) | 457 | .. | 457 | .. |
| Software Billing System – Upgrade (Bendigo) | 572 | .. | 148 | 423 |
| Software Field Force – Purchase (Bendigo) | 356 | .. | 178 | 178 |
| Software Geographic Information System – Upgrade (Bendigo) | 594 | .. | 53 | 540 |
| Supply Water Main – Construction (Bridgewater) | 11 606 | 128 | 5 739 | 5 739 |
| Wastewater Assets Communications Equipment – Upgrade (Bendigo) | 1 094 | .. | 43 | 1 052 |
| Wastewater Main 300mm Duplication Kangaroo Flat – Construction (Bendigo) | 3 560 | .. | 3 560 | .. |
| Wastewater Main 375 and 450mm Duplication Kangaroo Flat – Construction (Bendigo) | 6 562 | .. | 6 562 | .. |
| Wastewater Main Access Chambers – Replacement (Various) | 396 | .. | 53 | 343 |
| Wastewater Main Blockage Reduction – Upgrade (Various) | 6 519 | .. | 916 | 5 603 |
| Wastewater Main General – Replacement (Castlemaine) | 1 206 | .. | 156 | 1 050 |
| Wastewater Main General – Replacement (Echuca) | 1 624 | .. | 296 | 1 328 |
| Wastewater Main General – Replacement (Kyneton) | 538 | .. | 85 | 453 |
| Wastewater Main Small Towns – Replacement (Various) | 269 | .. | 43 | 226 |
| Wastewater Main Upsizing and Duplication – Construction (Bendigo) | 5 210 | .. | 269 | 4 941 |
| Wastewater Outfall Rising Main – Construction (Lockington) | 385 | .. | 385 | .. |
| Wastewater Pumping – Upgrade (Various) | 1 293 | .. | 240 | 1 053 |
| Wastewater Pumping General – Replacement (Various) | 1 002 | 431 | 110 | 461 |
| Wastewater Pumping Sewage Pump Station 1 – Construction (Echuca) | 1 253 | .. | 1 014 | 239 |
| Wastewater Pumping Sewage Pump Station 12 – Replacement (Bendigo) | 587 | .. | 587 | .. |
| Wastewater Pumping Sewage Pump Station 7 – Construction (Echuca) | 374 | .. | 374 | .. |
| Water Assets Communications Equipment – Upgrade (Various) | 800 | .. | 53 | 746 |
| Water Channel Fencing – Replacement (Various) | 700 | .. | 53 | 647 |
| Water Main General – Replacement (Bendigo) | 2 940 | 1 800 | 211 | 928 |
| Water Main General – Replacement (Echuca) | 414 | .. | 83 | 331 |
| Water Main – High Street South – Construction (Echuca) | 257 | .. | 257 | .. |
| Water Main – Ogilvie Avenue – Construction (Echuca) | 968 | .. | 968 | .. |
| Water Main Small Towns – Replacement (Various) | 1 986 | .. | 239 | 1 747 |
| Water Main Valves – Replacement (Various) | 549 | .. | 160 | 389 |
| Water Pressure Improvements – Upgrade (Tylden) | 247 | .. | 247 | .. |
| Water Pressure Monitoring Stations – Construction (Various) | 348 | .. | 160 | 188 |
| Water Pump Station General – Replacement (Various) | 492 | 271 | 43 | 178 |
| Water Pump Station Junortoun Booster – Construction (Bendigo) | 267 | .. | 267 | .. |
| Water Reservoir Fencing – Replacement (Various) | 306 | .. | 16 | 290 |
| Water Reservoir General – Replacement (Various) | 593 | 24 | 21 | 548 |
| Water Reservoir Protection – Upgrade (Various) | 332 | .. | 64 | 268 |
| Water Treatment – Construction (Rochester) | 1 815 | .. | 1 815 | .. |
| Water Treatment – Upgrade (Leitchville) | 4 978 | 300 | 2 339 | 2 339 |
| Water Treatment – Upgrade (Serpentine) | 267 | .. | 267 | .. |
| Water Treatment Plant Water Tank – Upgrade (Cohuna) | 303 | .. | 303 | .. |
| Total new projects | 67 414 | 3 285 | 31 424 | 32 705 |
| Total Coliban Region Water Corporation projects | 520 936 | 160 728 | 80 436 | 279 772 |

Source: Coliban Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# East Gippsland Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Additional Wet Weather Storage (Metung) | 1 175 | 84 | 235 | 856 |
| Alternative Irrigation Scheme (Cobungra) | 1 225 | 52 | .. | 1 173 |
| Bairnsdale Wastewater Treatment Plant Augmentation (Bairnsdale) | 295 | .. | .. | 295 |
| Banksia Peninsula Sewerage Scheme (Paynesville) | 1 680 | 260 | 1 420 | .. |
| Design and Construct/Refurbish Storage – Augment Supply (Omeo) | 266 | .. | 266 | .. |
| Developer Financed Works – Wastewater (Various) | 4 764 | 1 548 | 855 | 2 361 |
| Developer Financed Works – Water (Various) | 4 800 | 1 938 | 855 | 2 007 |
| Diversion of Kalimna Sewers to East Pump Station (Lakes Entrance) | 383 | 10 | 373 | .. |
| Jennings Street – Property Development (Bairnsdale) | 1 984 | 80 | 160 | 1 744 |
| Mitchell River Supply Augmentation (Bairnsdale) | 35 316 | 6 257 | 15 828 | 13 231 |
| Motor Vehicle Purchases (Various) | 4 174 | 1 029 | 423 | 2 722 |
| Office Furniture and Equipment (Various) | 3 571 | 942 | 1 057 | 1 572 |
| Plant and Equipment Purchases (Various) | 1 898 | 1 272 | 161 | 465 |
| Sewer Main/Network Re-Lining/ Replacement (Various) | 380 | .. | 150 | 230 |
| Sewer Pump Replacements (Lakes Entrance) | 940 | 140 | 107 | 693 |
| Supervisory Control And Data Acquisition (SCADA) Implementation – Water (Various) | 1 612 | 1 292 | 320 | .. |
| Tambo Bluff Estate Wastewater Scheme (Metung) | 2 211 | 930 | 1 281 | .. |
| Tambo Bluff Estate Water Scheme (Metung) | 695 | 10 | 685 | .. |
| Upgrade Sewerage System – Lake Tyers Aboriginal Trust (Lakes Entrance) | 1 202 | .. | 593 | 609 |
| Variable Speed Drive Pump Station – Lakes Entrance (Lakes Entrance) | 459 | 48 | 411 | .. |
| Watermain Replacements (Various) | 2 088 | 678 | 267 | 1 143 |
| Woodglen Reservoir – No. 2 (Bairnsdale) | 10 294 | 410 | 6 635 | 3 249 |
| Total existing projects | 81 412 | 16 980 | 32 082 | 32 350 |

Source: East Gippsland Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

East Gippsland Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Automatic Customer Meter Reading System (AMR) (Bairnsdale) | 713 | .. | 135 | 578 |
| Clear Water Tank – Mallacoota Water Treatment Plant (Mallacoota) | 340 | .. | .. | 340 |
| Dams Risk Assessment- Augmentation Works (Various) | 352 | .. | .. | 352 |
| Pump Station Replacements (Water) – Mechanical/Electrical (Various) | 482 | .. | 80 | 402 |
| Rising Main Replacement (Newmerella) | 454 | .. | 107 | 347 |
| Supervisors Control and Data Acquisition Bulk Water Diversion Telemetry | 445 | .. | .. | 445 |
| Wastewater Reuse Schemes – Lindenow, Bairnsdale, (Various) | 285 | .. | 54 | 231 |
| Water Treatment Plant Renewals/Replacements (Various) | 400 | .. | 54 | 346 |
| Total new projects | 3 471 | .. | 430 | 3 041 |
| Total East Gippsland Region Water Corporation projects | 84 883 | 16 980 | 32 512 | 35 391 |

Source: East Gippsland Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# First Mildura Irrigation Trust

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Nil | .. | .. | .. | .. |
| Total existing projects | .. | .. | .. | .. |

Source: First Midura Irrigation Trust

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Nil | .. | .. | .. | .. |
| Total new projects | .. | .. | .. | .. |
| Total First Midura Irrigation Trust projects | .. | .. | .. | .. |

Source:First Midura Irrigation Trust

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Gippsland and Southern Rural Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Allocated Maintenance Module – Software Implementation (Maffra) | 242 | 75 | 145 | 22 |
| Automated Meter Reading – Meter Reading Hardware (Various) | 250 | .. | .. | 250 |
| Corporate IT Network Infrastructure – Network Infrastructure (Various) | 490 | 297 | 193 | .. |
| Licensing Software Improvements (Maffra) | 390 | .. | .. | 390 |
| Main Northern Program Total Channel Control – Stage 3 and 4 (Maffra) | 4 716 | 41 | 1 707 | 2 968 |
| Main Northern Program Total Channel Control – Stage 5 (Maffra) | 7 642 | 3 366 | 675 | 3 601 |
| Main Northern Program Total Channel Control – Stage 6 (Maffra) | 7 642 | 2 458 | 1 571 | 3 613 |
| Meter Replacements Boisdale Pipeline – Meter replacement (Boisdale) | 1 380 | 707 | 346 | 327 |
| Pykes Creek Structural Improvements (Ballan) | 5 332 | 468 | 4 864 | .. |
| Total existing projects | 28 084 | 7 412 | 9 501 | 11 171 |

Source: Gippsland and Southern Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Gippsland and Southern Rural Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Blue Rock Slumping – Rehabilitation (Tanjil) | 301 | .. | 280 | 21 |
| Total new projects | 301 | .. | 280 | 21 |
| Total Gippsland and Southern Rural Water Corporation projects | 28 385 | 7 412 | 9 781 | 11 192 |

Source: Gippsland and Southern Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Goulburn-Murray Rural Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Asset Management/Maintenance Management Integration (Tatura) | 330 |  |  | 45 | 285 | .. |
| Barr Creek (Kerang) | 2 500 |  |  | 200 | .. | 2 300 |
| Benwell Drain 1 (Kerang) | 3 400 |  |  | 683 | 1 660 | 1 057 |
| Business Management System/ Corporate Intent (Tatura) | 520 |  |  | 331 | 189 | .. |
| Campaspe Pipeline (Rochester) | 250 |  |  | 53 | .. | 197 |
| Central Goulburn 10/28/9 (Tongala) | 500 |  |  | 379 | 121 | .. |
| Central Goulburn 6/34/9 (Tongala) | 350 |  |  | 50 | .. | 300 |
| Central Goulburn Channel 9 Remodel (Wyuna) | 700 |  |  | 188 | .. | 512 |
| Central Goulburn Channel L6/4 and 19L6/4 Remodel (Mooroopna) | 1 410 |  |  | 991 | .. | 419 |
| Central Goulburn Drains Retrofitting (Tatura) | 500 |  |  | 1 | .. | 499 |
| Contour Offtake Replacement (Cohuna) | 400 |  |  | .. | .. | 400 |
| Deakin Drain 16 Extension, (Stage 1) (Harston) | 1 600 |  |  | 255 | 19 | 1 326 |
| Deakin Drain 16 Extension, (Stage 2) (Harston) | 1 400 |  |  | 197 | 19 | 1 184 |
| Drain 2/11 (Stage 2) (Shepparton) | 700 |  |  | 191 | .. | 509 |
| Drain Discharge Project (Shepparton) | 320 |  |  | 108 | .. | 212 |
| Drainage Course Declaration (Lockington) | 509 |  |  | 327 | .. | 182 |
| Drainage Course Declaration Construction Stanhope Depression (Stanhope) | 915 |  |  | 322 | .. | 593 |
| East Goulburn 1/10 (Shepparton) | 350 |  |  | .. | .. | 350 |
| East Goulburn 12 (Stage 3) (Shepparton) | 250 |  |  | 51 | .. | 199 |
| East Goulburn 12 (Stage 4) (Shepparton) | 240 |  |  | .. | .. | 240 |
| East Goulburn 19/12 (Shepparton) | 400 |  |  | 13 | .. | 387 |
| Geographic Information System (Tatura) | 710 |  |  | 587 | 123 | .. |
| Goulburn Weir Safety Works (Nagambie) | 4 106 |  |  | 225 | 3 881 | .. |
| Greens Lake Pumps (Rochester) | 801 |  |  | 451 | 350 | .. |
| Gunbower Weir (Cohuna) | 2 600 |  |  | 2 219 | 381 | .. |
| Improvements to Jeruselum Creek Caravan Park (Eildon) | 500 |  |  | .. | 500 | .. |
| IT strategy – Information Model Adoption (Tatura) | 1 000 |  |  | .. | 1 000 | .. |
| Kow Swamp Contour Regulator Replacement (Cohuna) | 2 000 |  |  | 1 419 | 581 | .. |
| Little Murray Weir Bank Levee Replace Left Hand Bank (Swan Hill) | 300 |  |  | .. | 160 | 140 |
| Mokoan – Return to Wetlands (Benalla) |  | 28 348 |  | 2 131 | 25 257 | 960 |
| Mosquito Community Surface Drain 24/25 (Byrneside) | 1 900 |  |  | 300 | .. | 1 600 |
| Mosquito Drain (Stage 10) (Tatura) | 790 |  |  | 624 | 38 | 128 |
| Mosquito Drain Tatura Bypass (Tatura) |  | 2 400 |  | 652 | 66 | 1 682 |
| Murray Valley Channel 8/6 (Waaia) | 250 |  |  | 60 | .. | 190 |
| Murray Valley Drain 11 (Stage 2) (Cobram) | 2 200 |  |  | 199 | .. | 2 001 |
| Murray Valley Drain 11 (Stage 3) (Cobram) | 2 000 |  |  | 199 | 94 | 1 707 |
| Murray Valley Drain 11 (Stage 4) (Cobram) | 800 |  |  | 132 | 5 | 663 |
| Murray Valley Drain 13 Retrofitting (Nathalia) | 1 305 |  |  | 220 | .. | 1 085 |
| Murray Valley Drain 3/7/3 Extension (Cobram) | 1 900 |  |  | 172 | .. | 1 728 |
| Murray Valley No. 1 Channel (Cobram) |  | 2 530 |  | 395 | .. | 2 135 |
| Nyah Pump Station Upgrade (Nyah) | 1 200 |  |  | 5 | 1 195 | .. |
| Rochester Channel 27 Remodelling (Rochester) | 350 |  |  | 49 | .. | 301 |
| Supervisors Control and Data Acquisition (Central Goulburn) (Tatura) | 826 |  |  | .. | .. | 826 |
| Supervisors Control and Data Acquisition (Channel 1) (Pyramid Hill) |  |  | 900 | 618 | .. | 282 |
| Supervisors Control and Data Acquisition (Channels) (Rochester) | 250 |  |  | 21 | .. | 229 |
| Supervisors Control and Data Acquisition (Cobram) | 1 500 |  |  | 286 | .. | 1 214 |
| Supervisors Control and Data Acquisition (Drains) (Tatura) | 711 |  |  | 2 | .. | 709 |
| Supervisors Control and Data Acquisition (Rochester) | 350 |  |  | 42 | .. | 308 |
| Supervisors Control and Data Acquisition (Stuart Murray Canal) (Nagambie) | 720 |  |  | .. | .. | 720 |
| Supervisors Control and Data Acquisition (Swan Hill Channel 9, 6/7) (Swan Hill) | 900 |  |  | 634 | .. | 266 |
| Supervisors Control and Data Acquisition (Waranga Major Offtake) (Rushworth) | 270 |  |  | 103 | .. | 167 |
| Supervisors Control and Data Acquisition (Waranga West Channel) (Rochester) | 460 |  |  | 345 | .. | 115 |
| Supervisors Control and Data Acquisition (Waranga Western Channel) (Boort) | 1 150 |  |  | 170 | .. | 980 |
| Shepparton Drain 2/11, (Stage 1) (Shepparton) | 980 |  |  | 208 | .. | 772 |
| Shepparton Drain 2/11, (Stage 2) (Shepparton) | 700 |  |  | 74 | .. | 626 |
| Stanhope Drain (Stage 2) (Stanhope) | 680 |  |  | 438 | 242 | .. |
| Stuart Murray Canal Bank and Offtake Replacement (Nagambie) | 1 510 |  |  | 33 | .. | 1 477 |
| Timmering Drainage Course Declaration (Nanneella) | 800 |  |  | 127 | .. | 673 |
| Total Channel Control CG1234 (Various) | 21 593 |  |  | 9 217 | .. | 12 376 |
| Tragowel (East of Loddon) Community Surface Drains (Kerang) |  | 4 000 |  | 150 | .. | 3 850 |
| Tresco Pump Station Upgrade (Tresco) |  | 500 |  | 70 | .. | 430 |
| Upgrade Groundwater Database for Meter Reads (Tatura) | 363 |  |  | .. | 363 | .. |
| Wandella Creek (Kerang) | 1 800 |  |  | 202 | .. | 1 598 |
| Wandella Creek Drain 1 (Stage 2) (Boort) | 700 |  |  | .. | .. | 700 |
| Waranga West Channel (West) Seepage Control (Boort) | 1 100 |  |  | 80 | .. | 1 020 |
| Waranga West Channel (West) Upgrade Regulator (Rochester) | 650 |  |  | 441 | .. | 209 |
| Total existing projects | 118 947 |  |  | 27 685 | 36 529 | 54 733 |

Source: Goulburn-Murray Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Goulburn-Murray Rural Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Asset Management System (Various) | 1 300 | .. | 1 200 | 100 |
| Laanecoorie Dam Safety Works (Laanecoorie) | 5 600 | .. | 5 600 | .. |
| William Hovell Dam Safety Works (Cheshunt) | 7 700 | .. | 2 700 | 5 000 |
| Total new projects | 14 600 | .. | 9 500 | 5 100 |
| Total Goulburn Murray Rural Water Corporation projects | 133 547 | 27 685 | 46 029 | 59 833 |

Source: Goulburn-Murray Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Goulburn Valley Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Additional Raw Water Storage (Mansfield) | 2 700 |  | 2 644 | .. | 56 |
| Additional Raw Water Storage Land Acquisition (Mansfield) | 320 |  | 177 | 100 | 43 |
| Additional Treated Water Storage (Tatura) | 2 600 |  | 10 | 360 | 2 230 |
| Additional Waste Management Facility Winter Storage Stage 2 (Tatura) | 1 390 |  | .. | .. | 1 390 |
| Additional Waste Management Facility Winter Storage (Tatura) | 2 650 |  | 2 582 | .. | 68 |
| Additional Water Treatment Plant Capacity (Tatura) | 5 200 |  | .. | .. | 5 200 |
| Alexandra – Water Treatment Plant and Pipeline (Alexandra) | 3 350 |  | 3 297 | .. | 53 |
| Alexandra to Eildon Pipeline (Alexandra) | 7 120 |  | 430 | 3 500 | 3 190 |
| All Area – Asset Acquisitions – Corporate Assets (Various) | 58 850 |  | 5 200 | 2 700 | 50 950 |
| All Areas – Above Ground Asset Replacement (Various) | 25 240 |  | 2 220 | 900 | 22 120 |
| All Areas – Cast Iron Water Main Replacement Program (Various) | 6 250 |  | 100 | 1 230 | 4 920 |
| All Areas – Clear Water Storage Tank Augmentation Program (Various) | 3 690 |  | .. | 85 | 3 605 |
| All Areas – Councils – Water and Sewer (Various) | 8 543 |  | 250 | 400 | 7 893 |
| All Areas – Electrical As-Constructed Drawings (Various) | 1 010 |  | 30 | 150 | 830 |
| All Areas – Provision of Sewage Pump Station Guard Railing (Various) | 365 |  | 105 | 260 | .. |
| All Areas – Supervisory Control and Data Acquisition Infrastructure Upgrade (Various) | 6 785 |  | 115 | 100 | 6 570 |
| All Areas – Water Meters (Replacement) (Various) | 5 306 |  | 553 | 260 | 4 493 |
| All Areas – Water Meters (Stock) (Various) | 2 952 |  | 383 | 135 | 2 434 |
| All Areas – Water Network Modelling and Master Planning (Various) | 440 |  | 230 | .. | 210 |
| All Areas – Water Quality Instruments (Various) | 1 390 |  | 565 | 260 | 565 |
| Broadford – Govett and Hamilton Streets Water Main (Broadford) | 410 |  | 404 | .. | 6 |
| Buxton Supply Main Augmentation (Marysville) | 375 |  | .. | 50 | 325 |
| Clear Water Storage Outlet Water Main Augmentation (Kilmore) | 1 050 |  | .. | .. | 1 050 |
| Cobram – Water Treatment Plant Augmentation Stage 2 (Cobram) | 4 200 |  | .. | .. | 4 200 |
| Cobram Network Augmentation (Cobram) | 890 |  | 50 | 840 | .. |
| Daldy Road Irrigation (Shepparton) | 3 670 |  | 1 595 | .. | 2 075 |
| Disinfection Upgrade (Marysville) | 840 |  | .. | .. | 840 |
| DN200 Water Main South of Raftery's Road (Shepparton) | 270 |  | .. | .. | 270 |
| DN375 Direct Feed Water Main to South Tank (Shepparton) | 2 005 |  | .. | .. | 2 005 |
| DN375 Trunk Water Main South of Kialla Lakes Drive (Shepparton) | 585 |  | .. | .. | 585 |
| Euroa – Anderson Street Water Main (Euroa) | 825 |  | .. | .. | 825 |
| Gooram Pipeline (Euroa) | 2 150 |  | .. | .. | 2 150 |
| Goulburn River to Broadford and Kilmore Pipeline (Broadford) | 15 200 |  | 3 500 | 11 700 | .. |
| Green St Water Pump Station Upgrade (Kilmore) | 420 |  | .. | .. | 420 |
| High Lift Transfer Main Augmentation (Nurmurkah) | 325 |  | .. | 40 | 285 |
| High Lift Water Pump Station Upgrade (Kyabram) | 825 |  | .. | .. | 825 |
| Kialla Lakes South Pump Station (Shepparton) | 490 |  | .. | 50 | 440 |
| Kialla Lakes South Rising Main to SHPS08 (Shepparton) | 1 350 |  | .. | 100 | 1 250 |
| Kilmore – Hollowback to Kilmore Water Treatment Plant Pipeline Augmentation (Kilmore) | 1 760 |  | 750 | .. | 1 010 |
| Kilmore – Waste Management Facility Stage 2 Irrigation (Kilmore) | 450 |  | .. | .. | 450 |
| Kyabram – Waste Management Facility Augmentation Stage 2 (Kyabram) | 1 195 |  | 1 033 | .. | 162 |
| Landowner Reticulation Works – Sewer (Various) | 71 358 |  | 11 840 | 3 200 | 56 318 |
| Landowner Reticulation Works – Water (Various) | 42 765 |  | 4 670 | 2 000 | 36 095 |
| Marysville – Distribution Works Main Supply (Marysville) | 700 |  | 35 | .. | 665 |
| Marysville – Waste Management Facility Augmentation (Marysville) | 4 620 |  | 2 800 | 900 | 920 |
| Mooroopna – High Rate Anaerobic Lagoon Upgrade (Mooroopna) | 1 240 |  | 440 | .. | 800 |
| Mooroopna – Waste Management Facility Chemical Dosing (Mooroopna) | 500 |  | .. | .. | 500 |
| Nine Mile Creek Reservoir Embankment Replacement (Longwood) | 1 660 |  | 25 | 100 | 1 535 |
| Odour Control at SHPS05 Wanganui Road (Shepparton) | 460 |  | 30 | 430 | .. |
| Plant 1 Automation (Cobram) | 245 |  | .. | 245 | .. |
| Pump Station Upgrade and Rising Main Extension (Shepparton) | 630 |  | 5 | 35 | 590 |
| Purchase of Mortimer Property (Nathalia) | 740 |  | 20 | 720 | .. |
| Raw Water Storage (Kyabram) | 1 065 |  | 65 | 60 | 940 |
| Raw Water Storage (Nurmurkah) | 4 170 |  | .. | 100 | 4 070 |
| Relining/Replacement Sewers (Various) | 16 829 |  | 1 410 | 545 | 14 874 |
| Replacement of Abbinga Reservoir (Euroa) | 5 385 |  | .. | .. | 5 385 |
| Rising Main From Sewer Pump Station No. 10 to Sewer Pump Station No. 21 (Shepparton) | 480 |  | 5 | 25 | 450 |
| Rushworth – Reclaimed Water Reuse Scheme | 380 |  | .. | .. | 380 |
| Sawmill Settlement – Water Treatment Plant (Sawmill Settlement) |  | 2 370 | 200 | 2 170 | .. |
| Shared Assets – Sewer (Various) | 12 646 |  | 750 | 600 | 11 296 |
| Shared Assets – Water (Various) | 12 919 |  | 1 200 | 600 | 11 119 |
| Shepparton – Byham Park Pump Station Upgrade Stage 2 (Shepparton) | 720 |  | 5 | 35 | 680 |
| Shepparton – Campbell’s Sewer Main Upgrade (Shepparton) | 3 573 |  | 2 030 | .. | 1 543 |
| Shepparton – Congupna Booster Pump Station (Shepparton) | 300 |  | .. | .. | 300 |
| Shepparton – Gravity Sewer Wanganui Road (Shepparton) | 1 465 |  | .. | 80 | 1 385 |
| Shepparton – Maculata Drive Tower Replacement (Shepparton) | 590 |  | .. | .. | 590 |
| Shepparton – McGill Street Pump Station Upgrade (Shepparton) | 1 540 |  | 526 | 45 | 969 |
| Shepparton – Numurkah Road and Wanganui Road Trunk Mains (Shepparton) | 1 480 |  | .. | 65 | 1 415 |
| Shepparton – Old Dookie Road Water Main (Shepparton) | 685 |  | .. | 60 | 625 |
| Shepparton – Outfall Rising Main to Daldy Road (Shepparton) | 6 790 |  | 105 | .. | 6 685 |
| Shepparton – Sewer Pump Station 20 Sewage Pump Station Upgrade (Shepparton) | 850 |  | 5 | 25 | 820 |
| Shepparton – Waste Management Facility High Rate Anaerobic Lagoon Additional Aerators and Mixers (Shepparton) | 1 100 |  | .. | .. | 1 100 |
| Shepparton – Water Supply Distribution (Kingfisher Drive) (Shepparton) | 435 |  | 206 | 52 | 177 |
| Shepparton South Pump Station Rising Main to SHPS09 Catchment (Shepparton) | 2 045 |  | .. | .. | 2 045 |
| Shepparton Welsford Street Water Treatment Plant Electrics Upgrade (Shepparton) | 510 |  | 435 | 75 | .. |
| Tatura – Brown Street Pump Station Upgrade (Tatura) | 335 |  | 142 | .. | 193 |
| Tatura – Waste Management Facility Additional Offsite Reusers (Tatura) | 1 025 |  | 300 | .. | 725 |
| Tatura – Waste Management Facility Augmentation (Tatura) | 2 900 |  | .. | .. | 2 900 |
| Waste Management Facility Anaerobic to Maturation Lagoons Transfer Pipeline Replacement (Shepparton) |  | 855 | .. | .. | 855 |
| Waste Management Facility Irrigation Upgrade (Eildon) | 490 |  | .. | 50 | 440 |
| Waste Management Facility Irrigation Upgrade (Euroa) | 370 |  | .. | .. | 370 |
| Waste Management Facility Reuse Area Redevelopment (Sawmill Settlement) | 455 |  | .. | 50 | 405 |
| Waste Management Facility Solids Handling Upgrade (Seymour) | 250 |  | .. | 45 | 205 |
| Water Mains Replacement (Various) | 15 884 |  | 1 727 | 545 | 13 612 |
| Water Tower Upgrade (Tatura) | 380 |  | .. | 45 | 335 |
| Water Treatment Plant Capacity Upgrade (Shepparton) | 14 810 |  | .. | .. | 14 810 |
| Water Treatment Plant Capacity Upgrade (Yea) | 270 |  | 20 | 250 | .. |
| Water Treatment Plant Filter Replacement (Tongala) | 2 660 |  | 70 | 2 590 | .. |
| Water Treatment Plant Filtration (Bonnie Doon) | 2 790 |  | 100 | 1 220 | 1 470 |
| Water Treatment Plant Filtration (Colbinabbin) | 700 |  | .. | .. | 700 |
| Water Treatment Plant Filtration (Dookie) | 950 |  | .. | .. | 950 |
| Water Treatment Plant Filtration (Girgarre) | 795 |  | 50 | 745 | .. |
| Water Treatment Plant Filtration (Katamatite) | 1 020 |  | .. | .. | 1 020 |
| Water Treatment Plant Filtration (Stanhope) | 980 |  | .. | .. | 980 |
| Water Treatment Plant Filtration and Clear Water Storage (Katandra) | 885 |  | .. | 220 | 665 |
| Water Treatment Plant Improvement Works (Kilmore) | 2 250 |  | .. | 400 | 1 850 |
| Water Treatment Plant Upgrade (Mansfield) | 2 405 |  | .. | .. | 2 405 |
| Water Treatment Plant Upgrade (Nurmurkah) | 4 130 |  | 100 | .. | 4 030 |
| Yea – Provision of Filtration (Yea) | 1 113 |  | 729 | .. | 384 |
| Total existing projects | 447 383 |  | 56 268 | 41 547 | 349 568 |

Source: Goulburn Valley Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Goulburn Valley Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Broadford – Waste Management Facility Irrigation Capacity Upgrade – New Works (Broadford) | 1 460 | .. | .. | 1 460 |
| Broadford to Kilmore Pipeline – Construction (Broadford) | 13 610 | .. | .. | 13 610 |
| Broadford Water Treatment Plant Upgrade – New Works (Broadford) | 5 040 | .. | .. | 5 040 |
| Clear Water Storage Upgrade – New Works (Nurmurkah) | 1 820 | .. | 50 | 1 770 |
| Raw Water Storage – New Works (Sawmill Settlement) | 2 220 | .. | .. | 2 220 |
| Shepparton Operation Centre Building Extension – Construction (Shepparton) | 600 | 10 | 590 | .. |
| Waste Management Facility Irrigation Capacity Upgrade – New Works (Kilmore) | 4 130 | .. | .. | 4 130 |
| Waste Management Facility Irrigation Capacity Upgrade – New Works (Mansfield) | 2 280 | .. | .. | 2 280 |
| Waste Management Facility Irrigation Capacity Upgrade – New Works (Nagambie) | 350 | .. | .. | 350 |
| Water Treatment Plant Membrane Unit Upgrade – New Works (Nagambie) | 350 | .. | 350 | .. |
| Waste Management Facility Lagoon Relining – New Works (Tatura) | 420 | .. | .. | 420 |
| Total new projects | 32 280 | 10 | 990 | 31 280 |
| Total Goulburn Valley Region Water Corporation projects | 479 663 | 56 278 | 42 537 | 380 848 |

Source: Goulburn Valley Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Grampians Wimmera-Mallee Rural Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Asset Management Systems – Renew (Various) | 833 |  | 134 | .. | 699 |
| Building Relocation – Renew (Horsham) | 994 |  | .. | 936 | 59 |
| Channel Seepage Lake Toolondo – Renew (Toolondo) | 444 |  | 283 | .. | 161 |
| Communications Equipment – Replace (Various) | 310 |  | 130 | .. | 180 |
| Compliance with Dam Safety Standards at Taylors Lake – Enhance (Horsham) | 3 875 |  | 237 | 156 | 3 482 |
| Computer Hardware – Replace (Various) | 2 118 |  | 399 | .. | 1 719 |
| Consolidation of Asset Management Systems – Renew (Horsham) | 270 |  | 161 | 84 | 25 |
| Dam Safety Review (Various) | 511 |  | 309 | 202 | .. |
| Divisional IT projects – Replace (Horsham) | 504 |  | 283 | .. | 221 |
| Lake Lonsdale Dam Safety – Renew (Stawell) | 1 524 |  | 43 | .. | 1 481 |
| Minor Renewal works at Reservoirs – Renew (Various) | 241 |  | 155 | .. | 86 |
| Motor Vehicles – Replace (Various) | 19 217 |  | 5 159 | 2 627 | 11 432 |
| New Sewerage Scheme (Great Western) | 1 190 |  | 3 | .. | 1 187 |
| New Sewerage Scheme (Lake Bolac) | 2 062 |  | 3 | 170 | 1 889 |
| Nhill Contribution to Wimmera Mallee Pipeline Project – Addition (Nhill) | 3 100 |  | 1 650 | .. | 1 450 |
| OH&S Review and Priority Works – Replace (Various) | 897 |  | 99 | 77 | 721 |
| Plant And Machinery – Replace (Various) | 3 067 |  | 927 | 477 | 1 663 |
| Pump Asset Renewals – Renew (Various) | 1 200 |  | 4 | 66 | 1 131 |
| Remote Personal IT Packages – Replace (Various) | 330 |  | 103 | 36 | 191 |
| Rocklands Channel Seepage – Renew (Rocklands) | 296 |  | 24 | 31 | 241 |
| Rural Meter Replacements (Various) | 237 |  | 66 | 107 | 63 |
| Sewer Facility – Replace (Various) | 1 865 |  | .. | 104 | 1 761 |
| Sewer Main Replacement (Various) | 1 650 |  | .. | 312 | 1 338 |
| Sewer Mains – Replace (Various) | 8 093 |  | .. | .. | 8 093 |
| Sewer Stack Renewals – Renew (Various) | 450 |  | 153 | 52 | 245 |
| Sewer Treatment Plant Major Infrastructure Replacement (Various) | 585 |  | .. | 77 | 508 |
| Supervisory Control and Data Acquisition – Enhance (Various) | 4 050 |  | .. | 1 829 | 2 222 |
| Surface Water Diversion Metering (Various) | 680 |  | 150 | 22 | 509 |
| Treatment for Arsenic (Murrayville) | 250 |  | .. | .. | 250 |
| Waste Water Treatment Plant – Renew (St Arnaud) | 1 538 |  | .. | 60 | 1 479 |
| Waste Water Treatment Plant – Renew (Stawell) | 2 128 |  | .. | 110 | 2 019 |
| Waste Water Treatment Plant – Replace (Ararat) | 1 157 |  | 32 | .. | 1 125 |
| Waste Water Treatment Plant – Replace (Warracknabeal) | 2 240 |  | 637 | 1 603 | .. |
| Waste Water Treatment Plant Irrigation – Renew (Nhill) | 777 |  | .. | 46 | 732 |
| Water Mains – Replace (Various) | 20 064 |  | 1 377 | 883 | 17 804 |
| Water Meters – Replace (Various) | 1 395 |  | 443 | 175 | 777 |
| Water Plan Development – Enhance (Horsham) | 490 |  | 376 | .. | 114 |
| Water Supply Strategy – Enhance (Edenhope) | 2 300 |  | 105 | 201 | 1 994 |
| Water Supply Trunk Main – Mount Cole – Replace (Ararat) | 3 060 |  | 84 | .. | 2 976 |
| Water Supply Upgrade (Lalbert) | 341 |  | 15 | 326 | .. |
| Water Supply Upgrade (Manangatang) |  | 401 | 15 | 386 | .. |
| Water Supply Upgrade (Ultima) | 341 |  | 15 | 326 | .. |
| Water Supply Upgrades – Renew (Various) | 270 |  | .. | .. | 270 |
| Water Treatment Plant – Replace (Nhill) | 4 982 |  | .. | .. | 4 982 |
| Wimmera Mallee Pipeline Project – New (Various)(b) | 790 000 |  | 426 059 | 261 941 | 102 000 |
| Total existing projects | 892 326 |  | 439 633 | 273 417 | 179 276 |

Source: Grampians Wimmera-Mallee Rural Water Corporation

Notes:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

(b)	The Wimmera Mallee Pipeline Project has a total TEI of $790 million, with the state and Commonwealth governments contributing $266 million each, and the Grampians Wimmera-Mallee Water Corporation contributing $258 million.

Grampians Wimmera-Mallee Rural Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Computer Software – Purchase (Various) | 584 | .. | 584 | .. |
| Fire Plugs – Construction (Various) | 1 140 | .. | 1 140 | .. |
| Wastewater Treatment Facility – Upgrades (Nhill) | 2 799 | 825 | 1 974 | .. |
| Water Treatment Plant Major Infrastructure – Asset Renewals (Various) | 432 | .. | 432 | .. |
| Total new projects | 4 955 | 825 | 4 129 | .. |
| Total Grampians Wimmera Mallee Water Corporation projects | 897 281 | 440 458 | 277 547 | 179 276 |

Source: Grampians Wimmera-Mallee Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Lower Murray Urban and Rural Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Divert 14th Street Pump Station to Koorlong (Mildura) | 875 | 350 | 375 | 150 |
| Drainage Pit Lids (Merbein) | 624 | 221 | 10 | 393 |
| Irrigation Concrete Section in Channel (Red Cliffs) | 3 500 | 160 | 3 000 | 340 |
| Irrigation Meter Replacement (Red Cliffs) | 800 | 300 | 300 | 200 |
| Koorlong Waste Water Treatment Plant Augmentation (Mildura) | 33 338 | 3 342 | 18 000 | 11 996 |
| Main Replacements (Various) | 68 550 | 8 228 | 450 | 59 872 |
| Mildura Cowra Avenue – Catchment Proposal (Mildura) | 1 400 | 500 | 900 | .. |
| Minor Capital Works – New (Various) | 38 797 | 5 033 | 297 | 33 467 |
| Minor Capital Works – Replacement (Various) | 42 216 | 6 495 | 916 | 34 805 |
| Murrabit Sewerage Scheme (Murrabit) | 1 070 | 294 | 450 | 326 |
| Nichols Point Sewerage Scheme (Mildura) | 2 626 | 474 | 1 326 | 826 |
| Rehabilitation of Sewers (Various) | 9 100 | 7 960 | 700 | 440 |
| Robinvale High Pressure System (Robinvale) | 57 109 | 25 155 | 16 614 | 15 340 |
| Telemetry System – Private Diverters (Various) | 712 | 212 | 250 | 250 |
| Various Land Development (Mildura) | 620 | 120 | 320 | 180 |
| Water Treatment Plant Backwash Administration (Mildura) | 450 | 155 | .. | 296 |
| Total existing projects | 261 787 | 58 998 | 43 908 | 158 881 |

Source: Lower Murray Urban and Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Lower Murray Urban and Rural Water Corporation

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Irrigation Total Channel – Refurbishment (Red Cliffs) | 750 |  | .. | 750 | .. |
| Kerang Wastewater Treatment Plant – Refurbish/Replace (Kerang) | 3 300 |  | .. | 3 300 | .. |
| Private Divertors – Metering Program (Various) | 800 |  | .. | 800 | .. |
| Red Cliffs A Relift RM Replacement (Red Cliffs) | 250 |  | .. | 250 | .. |
| Red Cliffs Wastewater Treatment Plant – Decommission (Red Cliffs) | 1 800 |  | .. | 1 800 | .. |
| Replace Motor No. 4 and Variable Speed Drive Control (Red Cliffs) | 250 |  | .. | 250 | .. |
| Swan Hill Sewer Pump Station 22 Rising Main – Replacement (Swan Hill) | 450 |  | .. | 450 | .. |
| Total Channel Control – Refurbishment (Merbein) |  | 500 | .. | 500 | .. |
| Treatment Plant – Replacement (Millewa) | 1 000 |  | .. | 1 000 | .. |
| Water Treatment Plant – Land Purchase (Swan Hill) | 300 |  | .. | 300 | .. |
| Total new projects | 9 400 |  | .. | 9 400 | .. |
| Total Lower Murray Urban and Rural Water Corporation projects | 271 187 |  | 58 998 | 53 308 | 158 881 |

Source: Lower Murray Urban and Rural Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# North East Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Aboveground Replacements – Wastewater (Various) | 9 235 | 462 | 764 | 8 009 |
| Aboveground Replacements – Water (Various) | 12 693 | 1 325 | 683 | 10 685 |
| Bright Water Treatment Plant and Storage (Bright) | 9 388 | 110 | .. | 9 278 |
| Clearwater Supply ex Yarrawonga (Tungamah) | 2 742 | 1 394 | 140 | 1 208 |
| Computer and Office Equipment (Wodonga) | 787 | 141 | 34 | 612 |
| Convert Single Pump Pumping Station to Dual Pumps (Various) | 1 124 | 696 | 241 | 187 |
| Distribution Improvements (Various) | 1 887 | 297 | 107 | 1 483 |
| Environment Management System and Occupational Health and Safety Remedial Actions (Various) | 1 421 | 440 | 45 | 936 |
| Financial System (Various) | 1 459 | 382 | 1 052 | 25 |
| Industrial Pipeline (Wangaratta) | 1 540 | 1 097 | 82 | 361 |
| Mains Renewals (Various) | 23 240 | 2 054 | 671 | 20 515 |
| Minor Assets and Plant (Various) | 1 267 | 226 | 58 | 983 |
| Sewer Rehabilitation (Various) | 32 067 | 2 390 | 1 139 | 28 538 |
| Sewer Spill Containment (Various) | 2 255 | 282 | 390 | 1 583 |
| Stage 1 – 300ML Storage – Midland Highway (Benalla) | 2 907 | 2 122 | 785 | .. |
| Technical Upgrades – Instrumentation and Control (Various) | 2 554 | 404 | 116 | 2 034 |
| Upgrade/Relocate Treatment Plant (Yarrawonga) | 4 593 | 358 | 2 070 | 2 165 |
| Vehicles (Various) | 10 998 | 2 020 | 642 | 8 336 |
| Water Quality Improvements (Various) | 1 476 | 383 | 107 | 986 |
| Water Treatment Plant Capacity Upgrade (Yarrawonga) | 327 | 4 | .. | 323 |
| Total existing projects | 123 960 | 16 587 | 9 126 | 98 247 |

Source: North East Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

North East Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Additional Storage and Reuse – Construction (Wangaratta) | 5 575 | .. | 263 | 5 312 |
| Aeration Upgrade – Asset Enhancement (Wangaratta) | 259 | .. | 259 | .. |
| Billing System – System Development (Wodonga) | 1 052 | .. | 1 052 | .. |
| Class A to Industrial – Construction (Wodonga) | 731 | .. | 252 | 479 |
| Dedicated Supply Main to Tangambalanga Tank – Construction (Kiewa) | 347 | .. | 347 | .. |
| Fluoride – Asset Enhancement (Yarrawonga) | 500 | .. | 500 | .. |
| Implement Supervisory Control and Data Acquisition Strategic Plan – Asset Enhancement (Various) | 555 | .. | 105 | 450 |
| Interim Office/DR Facilities – Construction (Wodonga) | 316 | .. | 316 | .. |
| Loombah Improvements – Construction (Benalla) | 2 954 | .. | 105 | 2 849 |
| Mt Tabor Dam Improvements – Construction (Dartmouth) | 356 | .. | 356 | .. |
| New Water Supply Extension – Construction (Wodonga) | 3 402 | .. | 3 402 | .. |
| Offstream Storage – Construction (Bright) | 8 790 | .. | 526 | 8 264 |
| Pierce Street to Beechworth Road Pump Station Link – Construction (Wodonga) | 316 | .. | 316 | .. |
| Replace PABX – Asset Enhancement (Wodonga) | 263 | .. | 263 | .. |
| Technology Development – Asset Enhancement (Various) | 611 | .. | 116 | 495 |
| Water Main Augmentations – Construction (Benalla) | 445 | .. | 445 | .. |
| Water Treatment Plant – Construction (Mt Beauty) | 3 227 | .. | 526 | 2 701 |
| Water Treatment Plant – Construction (Myrtleford) | 4 307 | .. | 526 | 3 781 |
| Total new projects | 34 006 | .. | 9 675 | 24 331 |
| Total North East Region Water Corporation projects | 157 966 | 16 587 | 18 801 | 122 578 |

Source: North East Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Office of Housing

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Acquisition – 11 Units/Sites (Gippsland) |  | 2 145 | 253 | 1 774 | 118 |
| Acquisition – 18 Units/Sites (Grampians) |  | 3 880 | .. | 3 880 | .. |
| Acquisition – 19 Units/Sites (Loddon Mallee) | 3 473 |  | 91 | 2 874 | 508 |
| Acquisition – 2 Units/Sites (Hume) | 340 |  | 101 | 164 | 75 |
| Acquisition – 31 Units/Sites (Eastern Metro) | 12 513 |  | 1 636 | 10 877 | .. |
| Acquisition – 560 Units/Sites (North-West Metro) | 109 812 |  | 44 033 | 39 505 | 26 274 |
| Acquisition – 6 Units/Sites (Barwon South-West) | 1 250 |  | .. | 1 250 | .. |
| Acquisition – 77 Units/Sites (Southern Metro) | 20 491 |  | 2 847 | 17 057 | 587 |
| Improvements – 1113 Units/Sites (North-West Metro) | 111 495 |  | 41 063 | 26 904 | 43 528 |
| Improvements – 407 Units/Sites (Hume) | 15 217 |  | 10 977 | 2 120 | 2 120 |
| Improvements – 423 Units/Sites (Loddon Mallee) | 16 672 |  | 11 797 | 2 399 | 2 476 |
| Improvements – 509 Units/Sites (Eastern Metro) | 22 570 |  | 10 600 | 5 590 | 6 380 |
| Improvements – 617 Units/Sites (Gippsland) | 25 015 |  | 14 365 | 4 750 | 5 900 |
| Improvements – 738 Units/Sites (Grampians) | 27 704 |  | 18 151 | 4 573 | 4 980 |
| Improvements – 774 Units/Sites (Barwon South-West) | 35 048 |  | 24 685 | 5 118 | 5 245 |
| Improvements – 991 Units/Sites (Southern Metro) | 67 282 |  | 20 461 | 21 056 | 25 765 |
| Redevelopment – 11 Units/Sites (Southern Metro) | 2 370 |  | 1 070 | 1 300 | .. |
| Redevelopment – 401 Units/Sites (North-West Metro) | 76 780 |  | 40 168 | 10 668 | 25 944 |
| Total existing projects | 554 057 |  | 242 298 | 161 859 | 149 900 |

Source: Office of Housing

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Office of Housing

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Acquisition – 11 Units/Sites (Gippsland) |  | 2 465 | .. | 2 085 | 380 |
| Acquisition – 127 Units/Sites (North-West Metro) | 29 163 |  | .. | 28 035 | 1 128 |
| Acquisition – 19 Units/Sites (Barwon South-West) | 3 780 |  | .. | 3 430 | 350 |
| Acquisition – 28 Units/Sites (Hume) | 5 678 |  | .. | 3 473 | 2 205 |
| Acquisition – 34 Units/Sites (Grampians) | 7 154 |  | .. | 6 420 | 734 |
| Acquisition – 44 Units/Sites (Eastern Metro) | 10 523 |  | .. | 9 356 | 1 167 |
| Acquisition – 58 Units/Sites (Loddon Mallee) | 10 885 |  | .. | 8 180 | 2 705 |
| Acquisition – 85 Units/Sites (Southern Metro) | 18 748 |  | .. | 18 471 | 277 |
| Improvements – 136 Units/Sites (North-West Metro) | 13 649 |  | .. | 10 809 | 2 840 |
| Improvements – 93 Units/Sites (Southern Metro) | 6 289 |  | .. | 6 289 | .. |
| Redevelopment – 10 Units/Sites (North-West Metro) | 19 174 |  | .. | 2 732 | 16 442 |
| Redevelopment – 24 Units/Sites (Southern Metro) | 3 054 |  | .. | 1 218 | 1 836 |
| Redevelopment – 40 Units/Sites (Barwon South-West) | 3 300 |  | .. | 1 771 | 1 529 |
| Total new projects | 133 862 |  | .. | 102 269 | 31 593 |
| Total Director of Housing projects | 687 919 |  | 242 298 | 264 128 | 181 493 |

Source: Office of Housing

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# South Gippsland Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Biosolids Management Facility (Leongatha) | 285 |  | 20 | 265 | .. |
| Computer Systems – Regular Replacement (Various) | 948 |  | 393 | 84 | 471 |
| Dams Risk – Coalition Creek (Rehabilitation-augmentation) (Korumburra) | 5 599 |  | 18 | 169 | 5 412 |
| Jacobs Park Estate Pump Station – Upgrade (Wonthaggi) | 2 060 |  | 400 | 515 | 1 145 |
| Loch Nyora Sewerage Scheme (Poowong) | 15 910 |  | 938 | 750 | 14 222 |
| Meeniyan Sewerage Scheme (Meeniyan) | 4 942 |  | 665 | 2 100 | 2 177 |
| New Venus Bay Outfall (Venus Bay) | 3 409 |  | 3 279 | 130 | .. |
| Operations Systems Improvements – Water Treatment (South Gippsland) | 1 540 |  | 174 | 150 | 1 216 |
| Pipeline Upgrade – Koonwarra to Venus Bay (Koonwarra) | 700 |  | 50 | 300 | 350 |
| Plant and Equipment (Various) | 615 |  | 185 | 56 | 374 |
| Replacement/Rehabilitation of Mains (Various) | 5 814 |  | 1 375 | 506 | 3 933 |
| Reticulation Sewers Replacement/ Rehabilitation (Various) | 3 065 |  | 424 | 300 | 2 341 |
| Stormwater Infiltration Curtailment (South Gippsland) | 2 250 |  | 160 | 125 | 1 965 |
| Strategic Land Purchases (Various) | 2 181 |  | 1 217 | 25 | 939 |
| Telemetry (Various) | 1 574 |  | 1 484 | 90 | .. |
| Trunk Main Augmentation (Wonthaggi) |  | 295 | 60 | 235 | .. |
| Vehicle Replacement (Various) | 7 615 |  | 2 524 | 700 | 4 391 |
| Wastewater Treatment Plant Sludge Handling Establishment (Leongatha) |  | 285 | 20 | 265 | .. |
| Water Meters (Various) | 1 852 |  | 391 | 169 | 1 292 |
| Total existing projects | 60 939 |  | 13 777 | 6 934 | 40 228 |

Source: South Gippsland Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

South Gippsland Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Backflow Installations – Construction (Various) | 1 055 | 5 | 600 | 450 |
| Construction of Offstream Storage 200ML – Construction (Yarram) | 6 470 | 20 | 200 | 6 250 |
| Construction of Raw Water Storage – Construction (Dumbalk) | 650 | 80 | 570 | .. |
| Environmental Obligations – Construction (Various) | 2 900 | .. | 300 | 2 600 |
| Korumburra Sludge Dewatering – Construction (Korumburra) | 1 480 | 30 | 760 | 690 |
| Lance Creek Cloramination – Construction (Inverloch) | 375 | 120 | 255 | .. |
| Leongatha Sludge Dewatering – Construction (Leongatha) | 1 650 | 50 | 830 | 770 |
| Wastewater Treatment Plant Improvements – Construction (Foster) | 3 650 | .. | 1 000 | 2 650 |
| Wastewater Treatment Plant Upgrade – Construction (Inverloch) | 416 | 166 | 91 | 159 |
| Total new projects | 18 646 | 471 | 4 606 | 13 569 |
| Total South Gippsland Region Water Corporation projects | 79 585 | 14 248 | 11 540 | 53 797 |

Source: South Gippsland Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Wannon Regional Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Bald Hill No. 2 Bore Replacement (Portland) | 2 161 |  | 1 809 | 352 | .. |
| Construction of Dales Road Water Storage No. 2 (Warrnambool) | 3 668 |  | 1 922 | 1 068 | 678 |
| Dutton Way – Sewer Scheme (Portland) | 3 915 |  | 77 | .. | 3 838 |
| Dutton Way – Water Scheme (Portland) | 2 371 |  | .. | .. | 2 371 |
| Hamilton-Grampians Pipeline (Grampians) | 37 017 |  | 636 | 13 636 | 22 745 |
| Install New Bores at Tullich (Casterton) | 1 222 |  | 644 | .. | 578 |
| Macarthur Iron Sorption Plant (Macarthur) | 919 |  | 119 | 801 | .. |
| North Dennington Trunk Sewer (Warrnambool) | 409 |  | 103 | .. | 306 |
| Ocean Outfall Replacement (Port Fairy) | 375 |  | 111 | .. | 264 |
| Plant Purchases (Various) | 10 913 |  | 2 859 | 1 612 | 6 441 |
| Port Fairy – Domestic Dewatering Upgrade (Port Fairy) | 1 829 |  | 978 | 851 | .. |
| Portland – Waste Water Treatment Plant Upgrade (Portland) | 7 797 |  | 354 | .. | 7 443 |
| Portland Aluminium Water Supply (Portland) | 2 250 |  | 157 | 2 093 | .. |
| Pre-treatment System at Tertiary Water Reclamation Plant (Hamilton) | 1 100 |  | 30 | 1 068 | 2 |
| Reticulation Extension – Wangoom Road Scheme (Warrnambool) | 300 |  | 3 | .. | 297 |
| Russells Creek Trunk Sewer (Warrnambool) | 355 |  | 260 | .. | 95 |
| Septage Receival System (Hamilton) | 488 |  | 29 | 459 | .. |
| Sewer Main Replacement Program (Various) | 751 |  | 351 | 400 | .. |
| Sewer Treatment Plant – Winter Storage and Irrigation Augmentation (Port Campbell) | 2 749 |  | 742 | 2 007 | .. |
| Sewerage Scheme Treatment Plant (Peterborough) | 2 755 |  | 2 274 | 481 | .. |
| Sewerage Treatment Plant Diffuser – Replacement (Warrnambool) | 1 001 |  | 431 | .. | 570 |
| Sludge Management at the Water Reclamation Plant (Hamilton) | 1 816 |  | 1 356 | 459 | .. |
| Telemetry Installation Program (Various) | 9 177 |  | 3 878 | 683 | 4 615 |
| Tullich Bores – Main and Casterton Water Treatment Plant Clear Water Storage (Casterton) | 707 |  | 54 | 473 | 180 |
| Tullich Bores – Main and Casterton Water Treatment Plant Tullich Transfer Pump Station (Casterton) | 308 |  | 35 | .. | 273 |
| Upgrade of Domestic Water Reclamation Plant Upgrade Aeration (Port Fairy) |  | 1 050 | 81 | 969 | .. |
| Warrnambool Office – Land Purchase (Warrnambool) | 9 617 |  | 1 274 | 4 351 | 3 991 |
| Warrnambool Office Fit Out (Warrnambool) | 416 |  | 200 | .. | 216 |
| Warrnambool Waste Water Treatment Plant – Belt Filter Press Redundancy (Warrnambool) | 1 200 |  | 68 | 1 132 | .. |
| Wastewater Treatment – Outfall Replacement (Warrnambool) | 2 462 |  | 2 225 | .. | 237 |
| Water Main Replacement Program (Various) | 7 086 |  | 2 865 | 768 | 3 453 |
| Water Meter Replacement Program (Various) | 1 146 |  | 607 | 43 | 496 |
| Water Shut Off Block and Replacement Program (Portland) | 470 |  | 52 | .. | 418 |
| Water Supply System Stormwater Harvesting Potential (Various) | 1 931 |  | 95 | 1 836 | .. |
| Water Transfer Pump and Pipeline (Coleraine) | 4 056 |  | 992 | 3 064 | .. |
| Water Treatment Plant Upgrade (Port Fairy) | 370 |  | 125 | 246 | .. |
| Water Treatment Plant Upgrades (Warrnambool) | 12 495 |  | 3 601 | .. | 8 894 |
| West Portland Sewer Scheme (Portland) | 1 987 |  | 35 | 1 951 | .. |
| Wollaston Road Pump, Tower, Rising Main (Warrnambool) | 505 |  | 91 | .. | 414 |
| Water Reclamation Plant Augmentations – Disinfection (Warrnambool) | 700 |  | .. | .. | 700 |
| Total existing projects | 141 844 |  | 31 525 | 40 803 | 69 515 |

Source: Wannon Regional Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Wannon Regional Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Camperdown Sewer Rehabilitation – Restoration (Camberdown) | 434 | .. | 28 | 406 |
| Chemical Dosing Facilities – Construction (Camperdown) | 310 | .. | 310 | .. |
| Establishment of Greenhouse Offsets – Asset purchases (Various) | 379 | .. | 76 | 303 |
| Generators for Plant/Facilities – Asset enhancement (Various) | 320 | .. | 107 | 214 |
| Grampians Wiers – Monitor flows – Maintenance (Hamilton) | 299 | .. | 299 | .. |
| Inlet Structure Water Reticulation Plant – Construction (Hamilton) | 304 | .. | 16 | 288 |
| Large Capacity Sewer Upgrades – Construction (Warrnambool) | 487 | .. | 80 | 407 |
| Mobile Management Information System – System Development (Various) | 921 | .. | 334 | 587 |
| Online Instrumentation – System Development (Various) | 400 | .. | 85 | 315 |
| Upgrade Sewer Pump Stations – Construction (Various) | 2 339 | .. | 645 | 1 694 |
| Victoria Street Rising Main – Construction (Portland) | 375 | .. | 375 | .. |
| Water Reclamation Plant – Minor projects (Various) | 328 | .. | 328 | .. |
| Water Treatment – Disinfection projects – Maintenance (Various) | 283 | .. | 283 | .. |
| Water Treatment Plant – Minor projects (Various) | 357 | .. | 357 | .. |
| Total new projects | 7 537 | .. | 3 323 | 4 214 |
| Total Wannon Regional Water Corporation projects | 149 380 | 31 525 | 44 126 | 73 730 |

Source: Wannon Regional Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Western Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Avenue of Honour – Outfall Sewer (Bacchus Marsh) | 1 918 |  | 1 518 | 400 | .. |
| Bacchus Marsh Sewer Outfall Augmentation- (Bacchus Marsh) | 2 110 |  | .. | .. | 2 110 |
| Brooklyn Road Sewer Pump Station Upgrade (Melton) | 331 |  | 6 | 325 | .. |
| Building Improvements (Various) | 629 |  | 193 | 21 | 415 |
| Bulmans Road Water Main Duplication (Melton) | 1 700 |  | 776 | .. | 924 |
| Business Development (Various) | 3 080 |  | 520 | 103 | 2 457 |
| Development – Mains Upsizing – Sewer (Melton) | 3 350 |  | 218 | .. | 3 132 |
| Development – Mains Upsizing – Sewer (Sunbury) | 3 000 |  | 144 | 100 | 2 756 |
| Development – Mains Upsizing – Sewer (Various) | 4 792 |  | 242 | 154 | 4 396 |
| Development – Mains Upsizing – Water (Melton) | 2 700 |  | 148 | 150 | 2 402 |
| Development – Mains Upsizing – Water (Sunbury) | 2 946 |  | 449 | 200 | 2 297 |
| Development – Mains Upsizing – Water (Various) | 2 772 |  | 478 | 154 | 2 140 |
| Drinking Water Quality Management System (Various) | 3 000 |  | 250 | 100 | 2 650 |
| Graphic Information System (Various) | 8 573 |  | 1 728 | 280 | 6 565 |
| Griffith Street New Watermain (Bacchus Marsh) | 870 |  | 1 | .. | 869 |
| Information Technology (Various) | 47 661 |  | 8 149 | 1 610 | 37 902 |
| Melton Ourfall Sewer (Melton) | 12 842 |  | 3 994 | 5 848 | 3 000 |
| Melton Waste Water Treatment Plant Inlet Works (Melton) | 1 384 |  | 284 | 1 100 | .. |
| Melton Waste Water Purification Plant Composting (Melton) | 581 |  | .. | .. | 581 |
| Melton Waste Water Purification Plant Lagoon Works (Melton) |  | 3 083 | 173 | .. | 2 910 |
| Northern Tank (Sunbury) | 2 518 |  | 82 | .. | 2 436 |
| Occupation Health and Safety (Various) | 1 688 |  | 150 | 51 | 1 487 |
| Plant and Equipment (Various) | 8 077 |  | 2 217 | 275 | 5 585 |
| Property Metering (Various) | 4 244 |  | 519 | 226 | 3 499 |
| Pump Station Renewals (Various) | 5 250 |  | 315 | 175 | 4 760 |
| Recycled Water Stage 1 Reuse (Gisborne) | 534 |  | 34 | 500 | .. |
| Recycled Water Stage 1 Reuse (Riddells Creek) | 496 |  | 51 | 445 | .. |
| Recycled Water – Network Extension (Sunbury) | 3 000 |  | 445 | 100 | 2 455 |
| Recycled Water Scheme (Melton) | 28 550 |  | 929 | 200 | 27 421 |
| Reticulation Modelling (Various) | 1 948 |  | 308 | 100 | 1 540 |
| Reticulation Renewals/ Replacement (Various) | 35 154 |  | 3 939 | 774 | 30 441 |
| Riddells Creek Wastewater Treatment Plant – Inlet Works (Riddells Creek) | 608 |  | 174 | .. | 434 |
| Roadwork Upgrades (Western Region) | 1 597 |  | 97 | 50 | 1 450 |
| Romsey Bore Field (Romsey) | 3 847 |  | 97 | 250 | 3 500 |
| Romsey Water Filtration Plant – New Membranes (Romsey) | 2 471 |  | 21 | 350 | 2 100 |
| Romsey/Lancefield Water Quality (Romsey) | 3 725 |  | .. | .. | 3 725 |
| Rosslynne Water Treatment Plant (Gisborne) | 357 |  | 13 | 344 | .. |
| South Gisborne Outfall Sewer (Gisborne) | 1 615 |  | 115 | 1 500 | .. |
| South Gisborne Tank – Construction of New 1ML Tank (Gisborne) | 375 |  | 1 | 374 | .. |
| Sunbury Recycled Water Plant Recycled Water Storage (Sunbury) | 1 694 |  | 1 142 | .. | 552 |
| Sunbury Wastewater Treatment Plant – New Centrifuge (Sunbury) | 1 755 |  | 753 | 740 | 262 |
| Sunbury Wastewater Treatment Plant – New Tertiary Tanks (Sunbury) | 3 179 |  | 404 | .. | 2 775 |
| Sunbury Wastewater Treatment Plant – Tank Reconfiguration (Sunbury) | 4 407 |  | 3 407 | 1 000 | .. |
| Sunbury Waste Water Purification Plant Sediment Tanks (Sunbury) | 5 011 |  | .. | .. | 5 011 |
| Vehicle Turnover (Various) | 19 925 |  | 6 749 | 1 030 | 12 146 |
| Wastewater Treatment Plant – Aeration of Primary Lagoon (Bacchus Marsh) |  | 2 666 | 186 | 250 | 2 230 |
| Wastewater Treatment Plant – Aeration Works (Melton) | 4 604 |  | 379 | 3 625 | 600 |
| Wastewater Treatment Plant – Augmentation (Riddells Creek) | 1 806 |  | 1 230 | .. | 576 |
| Wastewater Treatment Plant – Augmentation for Growth (Gisborne) |  | 2 040 | 1 340 | 700 | .. |
| Wastewater Treatment Plant – Digestion Works (Melton) | 4 708 |  | 305 | 2 940 | 1 463 |
| Wastewater Treatment Plant – Secondary Sedimentation Tanks (Melton) | 10 488 |  | 2 131 | 3 000 | 5 357 |
| Wastewater Treatment Plant – Site Improvements Biodiversity (Various) | 1 545 |  | 216 | 50 | 1 279 |
| Wastewater Treatment Plant – Sludge Treatment (Gisborne) | 1 489 |  | 144 | .. | 1 345 |
| Wastewater Treatment Plant – Sludge Treatment Stage 1 (Melton) | 1 406 |  | 1 146 | .. | 260 |
| Wastewater Treatment Plant – Upgrade (Woodend) | 5 274 |  | 92 | 1 800 | 3 382 |
| Water Treatment Plant – Decommission Plant and Irrigation System (Bacchus Marsh) | 415 |  | 241 | .. | 174 |
| Total existing projects | 285 788 |  | 48 643 | 31 394 | 205 751 |

Source: Western Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Western Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Brooklyn and Coburns Road Sewer Pump Station – Inlet Main Upgrade (Melton) | 325 | .. | 325 | .. |
| Greenhouse Gas Strategy Implementation – Purchase (Various) | 950 | .. | 200 | 750 |
| Melton South Sewer – Construction (Melton) | 26 900 | .. | 100 | 26 800 |
| Recycled Water Scheme – Construction (Romsey) | 410 | .. | 205 | 205 |
| Recycled Water Plant – Augment Inlet Works/Grit Trap – Upgrade (Gisborne) | 718 | .. | 718 | .. |
| Sunbury/Melton Pipeline – Upgrade (Melton) | 350 | .. | 350 | .. |
| Total new projects | 29 653 | .. | 1 898 | 27 755 |
| Total Western Region Water Corporation projects | 315 441 | 48 643 | 33 292 | 233 506 |

Source: Western Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

# Westernport Region Water Corporation

## Existing projects

| ($ thousand) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Class A Ultra Violet (Cowes) | 250 | 100 | 150 | .. |
| Glen Forbes Water Treatment Plant – Process Upgrade (Glen Forbes) | 4 787 | 1 247 | 690 | 2 850 |
| Information Technology and Office Systems (Newhaven) | 1 694 | 730 | 367 | 597 |
| Plant and Equipment – Purchase (Various) | 1 972 | 726 | 227 | 1 019 |
| Telemetry Improvements (Various) | 750 | 30 | 150 | 570 |
| Under Channel Pipeline (San Remo) | 900 | 100 | 50 | 750 |
| Wastewater Pump Station – Building Upgrades (Various) | 1 000 | 178 | 50 | 772 |
| Wastewater Pump Station – Mechanical Upgrades (Various) | 1 230 | 288 | 200 | 742 |
| Wastewater Treatment Plant – Process Upgrade (Cowes) | 1 138 | 421 | 240 | 477 |
| Total existing projects | 13 721 | 3 820 | 2 124 | 7 777 |

Source: Westernport Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Westernport Region Water Corporation

## New projects

| ($ thousand) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Description | Total Estimated Investment |  | Expenditure to 30.06.08(a) | Estimated Expenditure 2008-09 | Remaining Expenditure |
| Candowie Bypass – Construction (Glen Forbes) | 475 |  | .. | .. | 475 |
| Candowie Embankment – Construction (Glen Forbes) | 13 900 |  | .. | 100 | 13 800 |
| Cowes Basin – Construction (Cowes) | 690 |  | .. | .. | 690 |
| Cowes Reuse Branch Main – Construction (Cowes) | 350 |  | .. | .. | 350 |
| Upgrade Bass River Pump Station and Pipeline – Construction (Glen Forbes) |  | 1 100 | .. | .. | 1 100 |
| Total new projects | 16 515 |  | .. | 100 | 16 415 |
| Total Westernport Region Water Corporation projects | 30 236 |  | 3 820 | 2 224 | 24 192 |

Source: Westernport Region Water Corporation

Note:

(a)	Expenditure for the year to 30 June 2008 based on information provided by agencies as at May 2008.

Appendix A: Contact addresses and telephone numbers

# General government sector

| Department of Education and Early Childhood Development | 2 Treasury Place EAST MELBOURNE VIC 3002 Telephone: (03) 9637 2000 |
| --- | --- |
| Department of Human Services | Level 6, 50 Lonsdale Street MELBOURNE VIC 3000 Telephone: (03) 9096 7686 |
| Department of Innovation, Industry and Regional Development | Level 31, 121 Exhibition Street MELBOURNE VIC 3000 Telephone: (03) 9651 7686 |
| Department of Justice | Level 21, 121 Exhibition Street MELBOURNE VIC 3000 Telephone: (03) 8684 7300 |
| Country Fire Authority | 8 Lakeside Drive BURWOOD EAST VIC 3151 Telephone: (03) 9262 8444 |
| Metropolitan Fire and Emergency Services Board | 456 Albert Street EAST MELBOURNE VIC 3002 Telephone: (03) 9662 2311 |
| Victoria Police (Office of the Chief Commissioner of Police) | Level 10, Building A World Trade Centre MELBOURNE VIC 3005 Telephone: (03) 9247 6360 |
| Department of Planning and Community Development | Level 12, 1 Spring St MELBOURNE VIC 3000 Telephone: (03) 9208 3777 |
| Department of Premier and Cabinet | Ground Floor, 1 Treasury Place MELBOURNE VIC 3002 Telephone: (03) 9651 0084 |
| Department of Primary Industries | 1 Spring Street MELBOURNE VIC 3000 Telephone: (03) 9658 4267 |
| Department of Sustainability and Environment | Level 13, 8 Nicholson Street EAST MELBOURNE VIC 3002 Telephone: (03) 9637 8696 |
| Environment Protection Authority | Herald Weekly Times Building 40 City Road SOUTHBANK VIC 3006 Telephone: (03) 9695 2722 |
| Department of Transport | Level 9, 121 Exhibition Street MELBOURNE VIC 3000 Telephone: (03) 9655 6698 |
| Roads Corporation | 60 Denmark Street KEW VIC 3101 Telephone: (03) 9854 2183 |
| Department of Treasury and Finance | Level 4, 1 Treasury Place MELBOURNE VIC 3002 Telephone: (03) 9651 6239 |
| Parliament of Victoria | 55 St Andrews Place EAST MELBOURNE VIC 3002 Telephone: (03) 8682 2662 |
| Victorian Auditor-General's Office | Level 24, 35 Collins Street MELBOURNE VIC 3000 Telephone: (03) 8601 7000 |

# Public non-financial corporations

| Director of Housing (PNFC) | GPO Box 4057 MELBOURNE VIC 3001 Telephone: (03) 9096 8827 |
| --- | --- |
| V/Line Passenger Corporation | GPO Box 5343 MELBOURNE VIC 3001 Telephone: (03) 9619 5900 |
| Victorian Rail Track | Level 8, 1010 Latrobe Street DOCKLANDS VIC 3008 Telephone: (03) 9619 8850 |
| Barwon Region Water Corporation | PO Box 659 GEELONG VIC 3220 Telephone: 1300 656 007 |
| Central Gippsland Region Water Corporation | PO Box 348 TRARALGON VIC 3844 Telephone: (03) 5177 4634 |
| Central Highlands Region Water Corporation | PO Box 152 BALLARAT VIC 3353 Telephone: (03) 5320 3165 |
| Coliban Region Water Corporation | PO Box 2770 Bendigo Delivery Centre BENDIGO VIC 3554 Telephone: (03) 5434 1222 |
| East Gippsland Region Water Corporation | PO Box 52 BAIRNSDALE VIC 3875 Telephone: (03) 5150 4400 |
| First Mildura Irrigation Trust | PO Box 5024 MILDURA VIC 3502 Telephone: (03) 5021 1811 |
| Gippsland and Southern Rural Water Corporation | PO Box 153 MAFFRA VIC 3860 Telephone: (03) 5139 3100 |
| Goulburn-Murray Rural Water Corporation | PO Box 165 TATURA VIC 3616 Telephone: (03) 5833 5500 |
| Goulburn Valley Region Water Corporation | PO Box 185 SHEPPARTON VIC 3632 Telephone: (03) 5832 0400 |
| Grampians Wimmera-Mallee Water Corporation | PO Box 481 HORSHAM VIC 3402 Telephone: (03) 5382 4611 |
| Lower Murray Urban and Rural Water Corporation | PO Box 1438 MILDURA VIC 3502 Telephone: (03) 5051 3400 |
| North East Region Water Corporation | PO BOX 863 WODONGA VIC 3689 Telephone: (02) 6022 0555 |
| South Gippsland Region Water Corporation | PO Box 102 FOSTER VIC 3960 Telephone: (03) 5682 0444 |
| Wannon Region Water Corporation | PO Box 1158 WARRNAMBOOL VIC 3280 Telephone: (03) 5564 7600 |
| Western Region Water Corporation | PO Box 2371 SUNBURY DC VIC 3427 Telephone: (03) 9218 5400 |
| Westernport Region Water Corporation | 2 Boyshome Road NEWHAVEN VIC 3925 Telephone: (03) 5956 4100 |

Appendix b: location index

A

Aireys Inlet, 79, 84

Albert Park, 23, 57

Alberton, 34

Alexandra, 45, 117

Altona, 23, 34, 71

Altona North, 23, 34

Alvie, 79

Anakie, 82

Anglesea, 34, 79

Apollo Bay, 79

Ararat, 52, 124

Ashwood, 46

Avoca, 100

Axedale, 103

B

Bacchus Marsh, 34, 72, 140, 141, 142

Bairnsdale, 40, 48, 50, 107, 108, 109

Ballan, 111

Ballarat, 24, 40, 45, 48, 50, 62, 67, 75, 99, 100, 101

Ballarat East, 23

Bannockburn, 79, 80

Barwon, 62

Barwon Downs, 80, 81

Barwon Heads, 67, 80, 87

Barwon South-West, 132, 133

Bass, Anderson, 67

Baxter, 68

Bayswater, 75

Beaufort, 99

Beechworth, 23

Belgrave Heights, 76

Belmont, 30, 67, 80, 82

Benalla, 114, 129, 130

Bendigo, 26, 34, 40, 45, 50, 102, 103, 104, 105

Bentleigh, 24

Bentleigh East, 24

Berwick, 38, 50

Berwick South, 24

Beveridge, 69

Birregurra, 80

Blackwood, 99

Boisdale, 63, 111

Bonnie Doon, 121

Boolarra, 88

Boort, 103, 115

Box Hill, 24, 40, 45, 48, 52

Box Hill South, 31

Braeside, 68

Bridgewater, 104

Bright, 129, 130

Brighton, 26

Broadford, 118, 122

Broadmeadows, 24, 34, 35

Brunswick, 40, 52

Buln Buln, 35, 88

Byrneside, 114

C

Camberdown, 139

Camberwell, 36, 41

Camperdown, 139

Carlton, 52

Carlton North, 38

Caroline Springs, 24, 25, 35

Carrum, 35

Carrum Downs, 52, 68

Casterton, 136, 137

Castlemaine, 102, 104

Caulfield, 40

Caulfield South, 40

Cheltenham, 25, 46

Cheshunt, 116

Clayton, 29, 36, 42, 46

Clifton Springs, 81

Clyde North, 68

Cobram, 114, 118, 119

Coburg, 25

Cohuna, 106, 113, 114

Colac, 25, 35, 40, 81, 87

Colbinabbin, 121

Coleraine, 137

Collingwood, 52

Connewarre, 87

Coolaroo, 66

Coongulla, 88

Corowa, 70

Corporate, 88, 94

Cowes, 144, 145

Craigieburn, 25, 35, 69, 71

Cranbourne, 25, 62, 66, 68

Cranbourne North, 68

Cranbourne South, 69

D

Dandenong, 25, 35, 45, 50, 55, 57, 58, 68, 72

Darnum, 35, 96

Darnum to Warragul South, 96

Dartmouth, 130

Daylesford, 36, 99, 100, 101

Deer Park, 69

Docklands, 48

Doncaster, 36

Doncaster East, 26

Donvale, 69

Dookie, 121

Doreen, 28

Doveton, 40, 45

Dromana, 36

Drouin, 25, 88, 89, 95

Drouin West, 26

Drysdale, 82

Dumbalk, 135

Duston Downs, 90, 93

Dutson, 89, 92, 94

Dutson Downs, 89, 90, 98

E

Eagle Point, 36

Eaglehawk, 23, 34

East Geelong, 48, 50

East Melbourne, 46

Eastern Metro, 132, 133

Echuca, 26, 70, 102, 104, 105

Edenhope, 124

Eildon, 114, 120

Elphingstone, 68

Eltham, 36

Epping, 42, 43, 46, 51, 61

Epping North, 26

Essendon, 24, 40

Euroa, 26, 118, 119, 120

F

Fairfield, 51

Faraday, 68, 69

Ferntree Gully, 28

Fitzroy, 43

Fitzroy North, 26

Flora Hill, 34

Footscray, 42, 44, 48, 57

Forrest, 86

Foster, 52, 135

Frankston, 27, 41, 45, 68

G

Geelong, 26, 40, 41, 50, 55, 66, 67, 69, 71, 72, 79, 80, 81, 82, 83, 84, 85, 86

Geelong East, 31

Gellibrand, 81, 84

Gembrook, 26

Gippsland, 90, 132, 133

Girgarre, 121

Gisborne, 141, 142, 143

Glen Forbes, 144, 145

Glen Waverley, 27, 36, 46

Glenormiston, 31

Golden Plains Shire, 68

Gordon, 99

Grahamvale, 36

Grampians, 132, 133, 136

Grantville, 67

Great Western, 123

Greensborough, 27

Grovedale, 27, 41, 79

H

Hallam, 66

Hamilton, 136, 137, 139

Hamlyn Heights, 33

Harcourt, 27, 68, 69

Harston, 113

Hastings, 43, 52

Haven, 36

Hazelwood, 95

Hazelwood North, 90

Heathcote, 104

Heatherton, 42

Heidelberg, 40, 41, 42, 45, 46

Hoppers Crossing, 68

Horsham, 123, 124

Hume, 132, 133

I

Indented Head, 82

Inverleigh, 27

Inverloch, 135

K

Kangaroo Flat, 23, 34

Katamatite, 121

Katandra, 121

Kensington, 41

Kerang, 113, 115, 128

Kew, 42

Kiewa, 130

Kilmore, 118, 121, 122

Kilsyth, 27

Kinglake West, 28

Kingston City, 68

Koonwarra, 134

Koroit, 37

Korong Vale, 102

Korumburra, 134, 135

Korweinguboora, 82

Kyabram, 28, 118, 119

Kyneton, 53, 68, 104

L

Laanecoorie, 116

Lake Bolac, 123

Lakes Entrance, 107, 108

Lalbert, 124

Landsborough, 100

Langwarrin, 36, 68, 69

Lara, 37

Laurimar, 28

Laverton, 28, 71

Leitchville, 103, 106

Leongatha, 28, 42, 50, 134, 135

Leopold, 82

Lethbridge, 28, 82

Lilydale, 53

Little River, 28

Lockington, 105, 113

Loddon Mallee, 132, 133

Longford, 89, 91

Longwood, 119

Lorne, 79, 82

Lovely Banks, 82

Lysterfield, 61

M

Macarthur, 136

Macclesfield, 29

Maffra, 37, 90, 91, 111

Mallacoota, 109

Mallee, 63, 64

Malmsbury, 68, 103

Manangatang, 124

Mansfield, 117, 121, 122

Maribyrnong, 29

Maryborough, 99, 101

Maryborough Catchment Entitlements, 100

Marysville, 118, 119

Mckinnon, 37

Meeniyan, 134

Melbourne, 48, 49, 51, 52, 53, 55, 57, 58, 59, 60, 61, 62, 66, 69, 73, 74

Melton, 46, 72, 140, 141, 142, 143

Merbein, 127, 128

Meredith, 83

Metroplitan, 69

Metropolitan, 40, 43, 45, 46, 52, 53, 55, 62, 63, 68, 71, 77, 78

Metung, 107

Mildura, 35, 48, 51, 127

Mildura South, 29

Mill Park, 29

Millewa, 128

Mirboo North, 90, 91

Moe, 29, 91, 92, 94

Moolap, 83

Moondarra, 92

Moorabbin, 53

Moorabool, 83

Mooroolbark, 30

Mooroopna, 29, 113, 119

Mordialloc, 30

Moriac, 82, 86

Morwell, 28, 46, 88, 90, 91, 92, 95

Morwell/Churchill, 88, 92

Mount Evelyn, 37

Mount Waverley, 29

Mt Beauty, 130

Mulgrave, 39

Mullum Mullum, 63

Murrabit, 127

Murrayville, 124

Murtoa, 42

Myrtleford, 131

N

Nagambie, 113, 115, 122

Nanneella, 115

Nar Nar Goon, 37

Narre Warren South, 67

Nathalia, 42, 114, 119

Neerim South, 92

Nepean, 63

New Gisborne, 30

Newbridge, 102

Newham, 37

Newhaven, 144

Newmerella, 109

Newport, 27

Nhill, 123, 124, 126

Nilma, 92

Noble Park, 50, 71

Non Metro Various, 66, 67, 69, 71

Noojee, 92

Norlane, 30

North Geelong, 66, 85

North Melbourne, 30, 52, 59, 67

North Richmond, 42

North Wyndham, 53

Northern Grid, 63

Northern Victoria, 61

North-West Metro, 132, 133

Nurmurkah, 118, 119, 121, 122

Nyah, 114

O

Oakleigh, 46

Ocean Grove, 75, 83

Olympic Park, 57

Omeo, 107

Ormond, 29

Ouyen, 53

P

Pakenham, 30

Parkville, 43, 46, 62

Pascoe Vale, 37

Paynesville, 107

Peterborough, 137

Point Cook, 25, 30

Point Lonsdale, 30, 82, 84, 85

Poowong, 134

Port Campbell, 136

Port Fairy, 136, 137

Port Melbourne, 38, 48

Port Phillip Bay, 63, 65

Portarlington, 84

Portland, 136, 137, 139

Prahran, 43, 45

Pyramid Hill, 114

Q

Queenscliff, 85

R

Ravenswood, 68, 69

Ravenswood South, 68, 69

Rawson, 93

Red Cliffs, 127, 128

Region, 141

Reservoir, 38

Riddells Creek, 141, 142

Ringwood, 57, 66

Ringwood East, 41, 42

Robinvale, 70, 127

Rochester, 43, 103, 104, 106, 113, 114, 115

Rockbank, 31

Rocklands, 124

Romsey, 141, 143

Rowville, 28

Rural, 31, 42, 43, 46, 55

Rushworth, 115

S

Sale, 31, 88, 93

San Remo, 144

Sandringham, 52

Sawmill Settlement, 119, 121, 122

Scoresby, 68

Seaspray, 94

Serpentine, 106

Seymour, 121

She Oaks, 79

Shepparton, 63, 113, 115, 118, 119, 120, 121, 122

Smythesdale, 99

Snake Valley, 39

South Gippsland, 71, 134

South Morang, 71

Southbank, 32, 59

Southern Metro, 132, 133

Springvale, 71

St Albans, 69

St Arnaud, 124

Stanhope, 113, 115, 121

Statewide, 23, 40, 41, 42, 43, 45, 46, 51, 52, 53, 54, 55, 56, 62, 63, 64, 66, 67, 73, 75, 76

Stawell, 31, 43, 123, 124

Summerland, 63

Sunbury, 46, 53, 69, 140, 141

Sunshine, 38, 43, 46, 48, 51

Surrey Hills, 38

Swan Hill, 53, 114, 115, 128

T

Tanjil, 112

Taradale, 68

Tarneit, 31

Tatura, 113, 114, 115, 117, 120, 121, 122

Telemetry, 109

Thornbury, 43

Thorpdale, 94

Tongala, 113, 121

Tooborac, 103

Toolondo, 123

Toongabbie, 94

Toora, 31

Torquay, 31, 82, 85

Traralgon, 32, 88, 89, 90, 93, 95

Trentham, 32, 45

Tresco, 115

Tungamah, 129

Tyers, 95

Tylden, 105

U

Ultima, 124

Upper Beaconsfield, 23

Upper Plenty, 38

Upwey, 32

V

Various, 24, 25, 31, 32, 34, 37, 38, 48, 58, 59, 62, 63, 64, 66, 67, 69, 71, 81, 82, 83, 84, 85, 87, 88, 89, 90, 91, 92, 93, 94, 95, 96, 99, 100, 101, 102, 103, 104, 105, 106, 107, 108, 109, 111, 115, 116, 117, 118, 119, 121, 123, 124, 125, 126, 127, 128, 129, 130, 134, 135, 136, 137, 139, 140, 141, 142, 143, 144

Venus Bay, 134

Vermont, 32

W

Waaia, 114

Wallan, 38, 54

Wallington, 80, 81, 83, 85

Wandana Heights, 82

Wangaratta, 32, 38, 42, 48, 50, 129, 130

Wantirna, 51, 66

Wantirna South, 71

Warracknabeal, 43, 124

Warragul, 41, 88, 95, 96

Warrnambool, 43, 47, 48, 51, 136, 137, 138, 139

Waubra, 99

Waurn Ponds, 84

Wendouree West, 27

Werribee, 32, 47

Westernport Bay, 63

Westmeadows, 35

Willow Grove, 97

Wimmera, 63, 64

Winchelsea, 86

Windsor and Prahran, 71

Wodonga, 39, 46, 48, 51, 67, 69, 129, 130

Wonthaggi, 34, 134

Woodend, 142

Wye River, 86

Wyndham Vale, 33, 38, 39

Wyuna, 113

Y

Yallourn, 97

Yallourn North, 90, 93, 97

Yarra Glen, 72

Yarra Junction, 54

Yarram, 135

Yarrawonga, 54, 129, 130

Yea, 121

Style conventions

Figures in the tables and in the text have been rounded. Discrepancies in tables between totals and sums of components reflect rounding. Percentage changes in all tables are based on the underlying unrounded amounts.

The notation used in the tables and charts is as follows:

1 million	1 000 thousand

1 basis point	0.01 per cent

nm	new measure

..	zero, or rounded to zero

tbd	to be determined

ongoing	continuing output, program, project etc

na	not applicable