## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Gender Responsive Budgeting (Note 2 GIAs were conducted for this program - one for the 2022-23 Budget and one for the 2023-24 Budget). | Program | To adapt the annual State budget process to incorporate gender responsive budget practices and, in particular, to incorporate the use of GIAs as part of the process. | For Review | No action taken | Although no specific changes were actioned as a result of the GIA, the program, by its very nature, aims to address hidden or entrenched gender inequalities by having GIAs included with most budget submissions. | Yes | As much as possible, advice, guidelines, templates and other communications referenced intersectionality alongside gender equality/inequality.
Gender Responsive Budgeting (Note 2 GIAs were conducted for this program - one for the 2022-23 Budget and one for the 2023-24 Budget). | Program | To adapt the annual State budget process to incorporate gender responsive budget practices and, in particular, to incorporate the use of GIAs as part of the process. | For Review | No action taken | Although no specific changes were actioned as a result of the GIA, the program, by its very nature, aims to address hidden or entrenched gender inequalities by having GIAs included with most budget submissions. | Yes | As much as possible, advice, guidelines, templates and other communications referenced intersectionality alongside gender equality/inequality.
Investing in social housing growth. | Program | Additional investment of $3 billion in the existing SHGF with returns to be used to procure 18,000 new social housing dwellings via the community housing sector. | New | No action taken | Service already accounted for gender inequality in access to social housing and incorporated promotion of gender equality into program design. Older single women represent the fastest growing cohort of people experiencing housing stress and homelessness, and women make up 62% of social housing tenants. Other differences in demand for social housing by gender and other priority cohorts include individuals and families that are homeless and receiving support, are escaping or have escaped family violence, with a disability or significant support needs and or with special housing needs. | Yes | The social housing needs of older women, women with disabilities, women and families escaping family violence and LGBTIQA+ people were considered as part of the GIA.
Victorian Homebuyer Fund. | Program | The Victorian Homebuyer Fund is a shared equity scheme, which makes it easier for Victorians to enter home ownership sooner. | New | No action taken | Since the Victorian Homebuyer Fund launched in October 2021, there have been a similar number of male and female participants. DTF continues to consider opportunities to provide tailored supports to encourage participation from specific cohorts. | Yes | The needs of people of certain cultural and religious backgrounds and people with a disability were considered as part of the GIA.
Maximising Outcomes Through Social Investment (2023-24 budget initiative) - Partnerships Addressing Disadvantage (PADs) pipeline: Consider genders lens in selection of focus area/cohort. | Program | Delivering two Partnerships Addressing Disadvantage programs (PADs). | New | Yes | DTF is identifying focus areas and cohorts for the PADs pipeline in consultation with departments and service providers, taking into consideration the needs and lived experiences of different genders. This includes consideration of a specific female cohort in one of the future PADs. | Yes | PADs focus on people experiencing disadvantage, and the consideration of gender in the pipeline development includes this intersectionality lens.
Maximising Outcomes Through Social Investment (2023-24 budget initiative) - Cultural safety framework - Consider intersectionality of Aboriginal women. | Program | Developing guidance materials to support cultural safety of Early Intervention Investment Framework proposals and initiatives. | New | Yes | DTF is working with the Victorian Aboriginal Child Care Agency (VACCA) to develop cultural safety guidance, and will also consider a gender lens and intersectionality in relation to Aboriginal women. | Yes | DTF is working with the Victorian Aboriginal Child Care Agency (VACCA) to develop cultural safety guidance, and will also consider a gender lens and intersectionality in relation to Aboriginal women.
Compliance and enforcement of wage theft laws. | Program | Since commencing operation on 1 July 2021, the Wage Inspectorate has had primary responsibility for detecting and punishing criminal wage theft offences in Victoria. ‘Wage theft’ refers to the deliberate and dishonest withholding of, or failure to pay or attribute, employee entitlements including wages, salaries, penalty rates, allowances, annual or sick leave, superannuation and long service leave. Wage theft is often accompanied by a deliberate failure to maintain and provide payroll and employment records, or by the maintenance and provision of inaccurate and falsified records to employees and/or regulators. These practices are also offences under the Wage Theft Act 2022 (Vic) (the Act). | New | No action taken | Industrial Relations Victoria (IRV) undertook broad community engagement to understand the impact of wage theft on the community, as well as how it can be best addressed, when drafting the Act. As an established regulator, the Wage Inspectorate commits to better understanding those it serves, and who are most impacted by its work, as one of its five strategic priorities. This involves engaging with stakeholders and the community and using their feedback to improve the service we provide and make compliance easier. | Yes | Differences in gender and vulnerable characteristics can affect, and amplify, the impacts of wage theft. As certain groups, including women and individuals with vulnerable characteristics are disproportionately impacted by wage theft, they may experience a greater net benefit by engaging with the service. Although the net benefit is difficult to quantify there are number of sources that identify how wage theft disproportionately impacts certain groups and will continue to do so if the Wage Inspectorate’s continued operations are not funded. These include: - Wage Inspectorate reporting data. - Stakeholder consultation and feedback. - The Senate Economic Reference Committee (2022) Systemic, sustained and shameful: Unlawful underpayment of employees’ remuneration. - McKell Institute, Ending Wage Theft: Eradicating underpayment in the Australian workplace (March 2019).
Better support for on-demand 'gig' workers. | Service | The Inquiry into the Victorian On-Demand Workforce (Inquiry) identified several issues affecting gig workers, including confusing and inaccessible pathways for advice and support about work status and an absence of a ‘one-stop shop’ to provide support to gig workers. The proposed service, to be known as the Gig Worker Support Service (Support Service), aligns with the Inquiry’s recommendation to establish a Support Service that provides gig workers with advice on worker rights and entitlements and dispute resolution avenues (Recommendations 8 - 9). The Inquiry also recommended the development of Standards to encourage fair conduct and accountability by platforms (Recommendation 14). These recommendations seek to assist gig workers, particularly low-leveraged, female, young and migrant workers. The Support Service is being designed to administer a compliance function for the Standards. | New | No action taken | When drafting the Act, Industrial Relations Victoria (IRV) undertook broad community engagement to understand the impact of wage theft on different groups within the community, and understand how it can be best addressed to improve outcomes for these different groups and the Victorian community as a whole. The Standards will include reference to gender specific issues (e.g. requiring platforms to review their algorithms and their practice to ensure they operate in a gender non-discriminatory way and to report publicly on the gender earnings gap of their non-employee workers). The Support Service provides for grants to assist low-leveraged workers (including women) with disputes, including through applications for funding formal mediation and/or litigation as spearheaded by relevant organisations. Further research into digital platform work is underway, consistent with the QUT Report finding that seven key areas warrant further research to identify and alleviate gendered inequities in digital platform work, including the gender pay gap, work life balance and the incidences of discrimination and harassment associated with this work. | Yes | Accessibility supports, such as translation and interpreting services for workers with disabilities and/or different cultural identities, may be required to ensure equitable access to a Support Service. Specific standards may be required to target compliance measures to prevent discrimination and proactively monitor and assess segments of the on-demand workforce who might be less likely to submit complaints due to their characteristics.
Gender equality initiatives in the Victorian public sector. | Program | To deliver the Government's response to recommendation 4 of the Inquiry into Economic Equity for Victorian Women and to further its efforts to reduce the gender pay gap in the public service. The program will help challenge gender stereotypes by providing partners (often men) with access to equal opportunities to provide care for children and to access support when trying to conceive a child or mourn the loss of a pregnancy. The Initiatives will help normalise conversations about partners (of any gender identity) taking on caring responsibilities. | New | No action taken | The program seeks to support entitlements from 2024-25 (noting the VPS EA nominal expiry date is 20 March 2024). Allowance of entitlements will also require revisions to the Public Sector Industrial Relations policies. | Yes | There are likely to be many sensitivities around the issues and circumstances that may give rise to an entitlement. Consultation with different stakeholder groups will help understand those sensitivities and ensure the messaging about the support available is framed in an appropriate way.
Standing up for workplace safety. | Program | Funding is provided to support workplace safety through a dedicated monitoring and enforcement unit for the construction sector within WorkSafe, as well as hiring new inspectors from the construction industry. While this program is delivered by WorkSafe, this GIA was completed by DTF. | New | Yes | WorkSafe will ensure the principles within its Diversity Strategy and its Gender Equality Action Plan are upheld during the recruitment of inspectors and the monitoring and enforcement team. | No | No intersectional lens applied.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and practices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 Gender composition of all levels of the workforce
1.1 Expand on the gender equality and diversity workforce data collected and reported on to improve gender equality and diversity metrics. | In progress | DTF is unable to expand gender equality and diversity workforce data collected using its current HR systems, as modification to its system would require significant investment and participation from multiple departments. DTF will continue to rely on the People Matter Survey (PMS) as a data source for expanded diversity measures, which will be supplemented upon implementation of the VPS Human Capital Management (HCM) system, SuccessFactors in coming years.
Introduce additional gender equality workforce metrics to be captured and reported on to monitor progress to improve gender equality and diversity: • increase the cultural diversity of women from 19 per cent to 20 per cent across DTF. • increase the number of employees who identify as non-binary to 10 per cent. • increase the number of women at VPS6 from 43 per cent to 50 per cent. • ensure there is 50 per cent women at all Executive bands. | In progress | DTF reports quarterly to the DTF Board on HR metrics including workforce gender composition. DTF also reports bi-annually on attrition to the DTF Board, including analysis on the impact of attrition on gender composition overall and within specific classifications. As demonstrated by progress in the gender equality indicator 'gender composition of all levels of the workforce' DTF has made progress in increasing women's representation in senior VPS classifications while reducing their overrepresentation in lower VPS classifications. This includes an increase in the proportion of women in the VPSG6 classification from 43% in 2021 to 48% in 2023. While there is improvement in the gender composition of women at the SES-1 band, overall gender composition in the SES cohort remains at 44%. DTF is unable to regularly report on sexuality and cultural diversity due to current HR system limitations, which will be resolved upon implementation of the VPS HCM system, SuccessFactors in coming years. DTF considers its target regarding non-binary representation as void due to this target being unrealistic based on broader VPS and population statistics for non-binary persons. DTF will set revised gender diversity targets based on sector, industry and population measures of gender diversity. To remove subjectivity from DTF's cultural diversity, the metric “increase the cultural diversity of women” has been discontinued. In place of this measure, DTF will set an ongoing measure to maintain its agreement rates to the PMS question “I feel culturally safe at work” above the results of its comparator group. DTF succeeded in meeting this measure in 2023 with 91% of DTF respondents agreeing to this statement in 2023 compared to 83% on average for the comparator group.
Communications campaign throughout the year (including induction) to encourage employee confidence to share their demographic details to better capture and report on gender equality and diversity metrics. | Not started | No specific communication campaign has been developed to share this information however in communications relating to surveys conducted, such as the PMS, there is an emphasis on encouraging staff to share details relating to gender equality and diversity metrics. DTF will have an opportunity to develop communications campaigns related to employees sharing their demographic details via HR systems when the VPS HCM system, SuccessFactors is launched.
Continue to work with the Victorian Public Sector Commission (VPSC) and VPS and DTF network(s) to understand workforce data to improve gender equality and diversity. | Ongoing | DTF liaises regularly with the VPSC to understand PMS questions relating to gender equality and diversity. There is an opportunity to liaise with VPS and DTF networks to better understand and improve gender equality and diversity.
1.2 Continue to deliver DTF leadership development programs, tailored for women at VPS5–VPS6, to increase gender balance. | In progress | DTF continues to promote and encourage women especially at the VPS5-6 level to register and participate in women's leadership programs offered by trusted providers. DTF also ensures its own leadership development program, targeted to VPSG6 and STS employees, has a gender balanced intake.
DTF to focus on high performing women at VPS5–6 to increase gender balance (and diversity) at VPS6 and above and/or support pathways to specialist roles. | Ongoing | The DTF People and Culture team discusses and focuses on high performing women at VPS5-6 in dealings with stakeholders and provides career development opportunities. Opportunities include tailored LinkedIn learning and external suitable leadership programs. DTF recognises the importance of focusing on this specific career development pathway to improve the gender balance at more senior levels within the organisation.
Connect and engage with the Women of Colour network on contemporary practices in the development of culturally appropriate leadership programs. | Not started | This measure is planned for commencement in 2024-25.
1.3 Continue to deliver career development, with a focus on women at VPS3–VPS5 to support transition into higher or specialised roles. | Ongoing | DTF regularly promotes training and appropriate courses available with IPAA. The courses build capability in a variety of areas with course titles such as Advanced Presentation Skills, Contract Management, and Building the Business Case. IPAA offers a range of courses suited to VPSG3-5 levels. DTF also focuses on career conversations, with People and Culture Business Partners promoting these important discussions and ensuring managers are aware of the tools and resources available to them to have meaningful career discussions.
DTF to focus on high performing women at VPS3–VPS5, to increase retention rates and to increase the career transition of women into higher or specialised roles. | Ongoing | DTF People and Culture uses Performance Development ratings data to ensure high performing women at VPSG3-5 levels are aware of appropriate courses available to develop capability. Together with their managers, the focus is on career development and formalising the Performance Development Plan to include advancing their career options.
1.4 The Gender Equality Champion to continue to lead gender equality as a key business and strategic focus and a driver for improved organisational performance and engagement. | In progress | DTF's Gender Equality Champion was instrumental in launching the Gender Equality Action Plan for DTF and made it a priority to promote Gender Equality at Executive Leadership meetings. DTF is in the process of selecting a new Gender Equality Champion as the previous Champion left DTF. Once identified they will lead key gender equality initiatives to drive organisational performance and engagement.
Gender Equality indicators and progress to continue to be a regular key agenda item for the Senior Executive Group (SEG) and to also be included in the Quarterly Board Performance Report as a mechanism for tracking and sharing progress. | Ongoing | The Quarterly Board Performance Report includes workforce gender split metrics (gender composition). Data presented includes gender split by division, gender split by grade and Senior Executive gender split. DTF Board discusses the data and recommendations for improvements. DTF is considering formalising 'Gender Equality Indicators and Progress' as a standing agenda item at DTF Board meetings.
DTF leaders consider only attending or speaking at external panels which are gender balanced. | Void/cancelled | This is a consideration and not a requirement. The gender balance will be considered however this should not impact the speaking engagement.
Establish a Gender Equality Committee to monitor progress and identify risks and challenges in the delivery of the GEAP (biannually). | In progress | DTF did establish a Gender Equality Committee during the time of developing the GEAP. This Committee included a range of VPS levels including Executives and included male staff. DTF continued to monitor progress and assess challenges with the support of the Committee. This Committee has lapsed due to resourcing constraints in the People and Culture team.
2. Gender composition of governing bodies
2.1 Continue to communicate policy guidelines promoting fair and consistent recruitment and appointment(s) to Executive roles and/or panels. | Ongoing | DTF communicates policy guidelines to interview panels and hiring managers to ensure fair and consistent appointments at the Executive level. This includes ensuring the candidate shortlist is diverse and gender balanced and discussions with hiring managers on the importance of gender equality and educating them in terms of policy and guidelines.
Regularly promote and communicate the VPSC guidelines in relation to the recruitment and appointment of governing bodies, board and/or panels to improve gender representation and diversity. | Ongoing | DTF follows the set of guidelines set for boards to ensure it represents the diversity of Victorians. DTF actively looks at the composition of boards to determine what job boards to use. Position descriptions and advertisements are also prepared with inclusive language. DTF assesses whether to advertise on 'Women on Boards', or 'Victorian Women’s Register' and other forums, such as ‘women in engineering’ via LinkedIn. The shortlisting process includes a matrix which takes into consideration the composition of the Board and enables an appropriate recruitment plan to be developed.
Director or Executive Director roles to be advertised within three months of becoming vacant, with acting arrangements not to exceed three months. | Void/cancelled | Due to the lengthy recruitment process to fill an Executive role, this initiative is cancelled.
Improve transparency of the experience, skills and capabilities required for roles on governing bodies. | In progress | DTF removes jargon from position descriptions that are being developed for roles on governing boards and uses inclusive language in position descriptions and advertisements.
3. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender
3.1 Reduce the pay gap by at least 5 per cent over the next four years. | In progress | DTF's median pay gap decreased by 3.8% for base salary and 4.6% for total remuneration. While progress has been made since the 2021 baseline audit, more frequent reporting is required to ensure DTF meets its target by June 2025 and addresses pay gaps for specific cohorts (e.g. the Executive cohort).
Continue to undertake annual pay gap data analysis (include intersectional data) and corrective action particularly when an occupation(s) and/or VPS level is identified with a pay gap of greater than 2 per cent. | Not started | Regular pay gap analysis is planned to commence in 2024, which will include quarterly reporting to the DTF Board on the base salary pay gap for DTF overall and by classification. Continued efforts to address the underrepresentation of women in high paying classifications (VPSG6 and above) will also support reduction in the gender pay gap at DTF. DTF plans to include gender pay gap analysis in its annual SES remuneration review process.
The outcomes of the gender pay analysis to be shared with all employees. | In progress | As part of the 2021 workplace gender equality audit, DTF undertook a pay gap analysis. The results of the 2021 pay gap analysis were used to determine DTF's baseline and to set measures and targets in the DTF 2021-2025 GEAP. DTF's pay gap results were published internally and communicated to all staff in the Gender Equality Workforce Audit report, which was also published on the Commission's website.
DTF to allocate specific budget annually to counter identified pay gaps. | Void/cancelled | DTF has improved equal remuneration without a specific budget set aside to address specific pay gaps. Setting aside a specific budget to counter identified pay gaps is not practical in the current fiscal setting. The Victorian Government has set significant savings requirements across the public sector which make this measure impractical as DTF faces staffing budget constraints. Based on the current trajectory of DTF's progress in achieving its equal remuneration targets, having reduced the median pay gap by 3.8% for base salary and 4.6% for total remuneration in two years, DTF's planned and existing controls will be sufficient to deliver a 5% reduction by June 2025. This measure is therefore cancelled.
Regularly review the DTF Job Classification policy to identify if there are current gender biases that are impacting upon remuneration and take corrective action. | Not started | This measure is planned for commencement in 2024-25.
4. Sexual harassment in the workplace
4.1 Continue to promote and communicate the Department’s zero-tolerance approach to sexual harassment across DTF. | Ongoing | The Department’s zero-tolerance approach to sexual harassment is promoted and communicated in regular Secretary messages to all staff and continues to be a focus for DTF. The DTF People Matter Action Plan (PMAP) for 2022-23 has an action for all staff to complete the Sexual Harassment in the Workplace eLearn and this action will be considered for inclusion in the 2023-24 PMAP.
Promote the Peer Support Network (formerly the DTF Safe People Officers program) and ensure sufficient officers are available to all employees across DTF. | Ongoing | DTF has a comprehensive Peer Support Network (Safe People program) under which there are currently ten trained Safe People who are available to support and assist DTF staff. Information about the program and all necessary details are available on TreasuryNet, DTF's intranet site.
Respectful Workplace Culture roll out of face-to-face and online training. | In progress | Respectful Workplace Culture training has been prepared and will be rolled out in person to all DTF Divisions in 2023-24 and into 2024-25. A comprehensive training pack has been developed with the support of DTF’s occupational health and safety third party provider. The online program has not been developed yet.
Sexual harassment data (without breaching confidentiality) is a standing agenda item on the DTF Work Health and Safety committee. | Ongoing | This is a standing agenda item on all DTF Work Health and Safety Committee meetings. The meetings occur every quarter and the topic of sexual harassment data is discussed with discretion due to the nature of the data.
Annually communicate and promote resources available to all employees to counter sexual harassment and emphasise DTF’s zero tolerance approach. | Ongoing | DTF’s zero tolerance approach to sexual harassment and counter sexual harassment resources are communicated formally through Secretary messages to all staff and via People and Culture Business Partners at a minimum annually. DTF has a comprehensive interactive VPSC approved eLearn on 'Sexual Harassment in the Workplace'. This is a mandatory eLearn all staff are required to complete every two years.
Implement and annually promote the anonymous reporting process being introduced across the VPS. | Not started | This measure is planned for commencement in 2024-25.
4.2 Review relevant policies and processes to ensure people of all genders feel safe to report sexual harassment. | Ongoing | DTF's Treasury Net (intranet site) has a dedicated page on Sexual Harassment and includes policies and processes on sexual harassment and reporting sexual harassment.
Regularly reviews sexual harassment guidelines and procedures to ensure these reflect the sector and community practice approach. | Ongoing | DTF’s People and Culture team regularly reviews sexual harassment policies and guidelines and communicates any changes or updates to DTF stakeholders.
5. Recruitment and promotion practices in the workplace
5.1 Continue to build DTF’s recognition externally as an employer of choice. | Ongoing | DTF is building its recognition as an employer of choice with communications and promotions on LinkedIn. Celebrating achievements in an inclusive and gender equal manner is a priority.
Promote the Department’s commitment to gender equality and diversity, inclusion, and flexible ways of working internally. | Ongoing | DTF is committed to gender equality and diversity and promotes this with inclusive advertising on position descriptions and job advertisements.
Engage with employees, relevant peak bodies, and external networks to continue to embed recruitment and engagement practices to increase gender diversity and build on being recognised as an employer of choice. | Not started | This activity is planned for commencement in 2024-25.
5.2 Review the DTF Recruitment and selection policy, to increase gender diversity, retention, and promotion rates of women. | Not started | A gender equality review of the DTF Recruitment and Selection policy has not been actioned and will be undertaken in 2024-25.
Review policy and guidelines to continue to promote and improve gender equality and diversity practices and targets within the Department’s recruitment, remuneration and promotion processes. • Increase retention rates of women at Executive Director and at VPS3–VPS5 level. • Increase the number of women applicants to DTF from 34 per cent to 50 per cent over the next four years. • Increase the promotion of women at VPS5–VPS6 to 50 per cent (from 42 per cent to 45 per cent respectively). • Increase promotion rates for women at Directors/STS and VPS5–VPS6 to 50 per cent. | In progress | DTF will consider results outlined under each category in future reviews of its recruitment, remuneration and promotion processes. Retention Women represented 56% of Executive Directors in 2021 and 50% in 2023. During the 2023 audit reporting period all Executive Director departures were women (excluding Machinery of Government transfers). Retention of women at the VPSG3-4 level was poorer with women representing 65% of departures despite comprising 55% of the overall cohort. At the VPSG5 classification retention was better with women representing 48% of departures and 50% of the overall cohort. Applicant gender composition The gender composition of DTF job applicants has improved by 2% with 36% of applicants identifying as women during the 2023 reporting period compared to 34% in 2021. Promotions Women comprised 40% of VPSG5 and 44% of VPSG6 promotions in 2021. In 2023 women comprised 50% of VPSG5 promotions and 32% of VPSG6 promotions. Promotions at the Director/STS level increased from 25% women in 2021 to 38% women in 2023.
DTF to review the performance development moderation process to enable an equitable approach to promotion through the performance development process. | Not started | A gender equality review of DTF’s performance development moderation process will commence in 2024-25.
6. Availability and utilisation of terms, conditions and practices relating to family violence leave, flexible working arrangements and working arrangements supporting workers with family or caring responsibilities
6.1 Regularly review and communicate DTF Family Violence guidelines to improve ease of access to leave. | Ongoing | DTF has a dedicated resource page on TreasuryNet (intranet) for Family Violence. This includes policy, support services, Frequently Asked Questions and details on forms and processes to follow. This content is regularly updated to reflect any changes.
In consultation with employees, DTF to regularly review guidelines and processes to improve ease of access, safety and privacy for employees when applying for leave. | Not started | This measure is planned for commencement in 2024-25.
Engage and connect with family violence external networks to understand and embed contemporary sector and community practice. | Not started | This measure is planned for commencement in 2024-25.
6.2 Continue to regularly promote DTF’s approach to flexible work arrangements to increase uptake across DTF. | In progress | DTF's People and Culture Business Partners continue to promote Flexible Work arrangements with their stakeholders. The Business Partners provide data on the uptake and discuss ways to increase flexible work. Managers continue to promote flexible work and flexible work is promoted during the recruitment process.
Annually promote the Department’s flexible work guidance materials to ensure employees are aware of arrangements available under the Enterprise Agreement 2020. | Ongoing | Since 2021, DTF has updated its flexible working policy and guidance materials to adapt to changing COVID-19 conditions and support return to office efforts with the assistance of flexible work arrangements. Regular messages have been issued by the Secretary to all staff encouraging employees to discuss flexible work needs with their managers.
People and Culture process to provide multiple opportunities for employees to share flexibility and accessibility requirements. | In progress | DTF has improved flexible work accessibility by updating the process for employees to request an arrangement. The workflow to provide employees access to flexible work arrangements has changed from a paper based to an electronic process, facilitated by DTF's payroll system. Updated, user friendly guidance has been published to assist employees with discussing arrangements with their managers and submitting them via the payroll system. Further enhancements to the flexible work process will be introduced throughout the employee lifecycle as DTF transitions to the HCM system, SuccessFactors, in coming years.
Deliver improved guidance around avoiding bias during performance assessments of employees who have additional non-work responsibilities or who use flexible work arrangements and/or work part time. | Not started | This measure is planned for commencement in 2024-25.
6.3 Improve parental leave policies and guidelines to be non-gendered. | Complete | The DTF Parental Leave Policy and Parental Leave guidelines are non-gendered.
DTF to make recommendations to improve parental leave entitlements in the next Enterprise Agreement negotiations. | Complete | Changes to the parental leave provisions were made as part of the new VPS agreement.
Continue to promote and communicate parental leave entitlements. | Ongoing | DTF’s People and Culture Business Partners promote and communicate parental leave entitlements on an individual basis and as required by staff members.
Provide a more formal approach to employees returning from periods of parental leave to support their transition back into the workplace. | Not started | A new program titled Parental Leave Support Program will commence early 2024 to address returning to work.
7. Gender segregation within the workplace
7.1. Increase gender representation and diversity in occupations with significant gender segregation. | In progress | DTF's occupational segregation remains relatively unchanged since 2021. Women remain underrepresented in managerial positions, overrepresented in clerical and administrative worker positions, and more evenly represented in professional positions. Within the professional occupational category, women continue to be underrepresented in economist roles which is a traditionally male dominated occupation.
Continue to support employment programs to increase gender balance and diversity in highly segregated occupations. | Ongoing | DTF strongly supports employment programs that are offered in the VPS to increase gender equity. Regular communication promoting employment programs are issued via DTF's intranet site and the Secretary promotes these programs in all staff messages. DTF runs a 'Women in Economics Mentoring Program'. This program is run by the Economic Division and attracts women studying in the fields of Economics or Finance. It is run annually and is a talent attraction program for DTF.
Target specific occupations with high gender segregation with a focus on recruitment and secondment arrangements to increase gender diversity. | Not started | This measure is planned for commencement in 2024-25.
Create an internal awareness campaign to promote understanding of gender segregation of occupations within the workplace, workforce and industry, and the impact gender stereotypes can have on decisions about role type and level. | Not started | This measure is planned for commencement in 2024-25.
8. Gender Impact Analysis for policy development
8.1 Establish Gender Responsive development and budgeting across DTF. | In progress | As detailed below, progress has been made on each measure under this strategy, with one complete, two ongoing and two in progress.
Develop a tool to assess the overall impact of the budget on people of different genders and establish a baseline to evaluate impact over time. | In progress | DTF considers the overall impact of the budget on gender equality as part of the budget process and provides advice to Government on this. The Government has published a Gender Equality Budget Statement since 2017-18 to outline the impacts of the budget on women and gender equality.
Gap analysis to inform future policy development. | In progress | When gender responsive budgeting was introduced, ahead of the 2022-23 Budget, the Government had received the report on the Independent Inquiry into Economic Equity for Victorian Women, led by Carol Shwartz. This report was effectively a gender gap report, recommending policy priority areas for Government consideration. Government will consider an approach to a gender gap analysis as part of future resourcing decisions (consistent with the recommendation of the PAEC Inquiry into Gender Responsive Budgeting, which the Government accepted in principle).
Embed gender responsive budgeting within the State budget process. | Ongoing | Gender responsive budgeting is in its third year in Victoria, and the Government has committed to legislating the practice in the 2024 calendar year.
Build on the achievements of the Gender Equality Act 2020 by embedding the requirement for Gender Impact Assessments for policies, programs, or services with a direct and significant impact on the public into resource allocation processes. | Ongoing | Budget business case templates and guidance have embedded the requirement for Gender Impact Assessments. DTF has provided support and training for departments to support this objective, and have tracked departmental completion rates, which have increased over the first two years. The 2024-25 Budget will be the third year of gender responsive budgeting in Victoria.
Evaluate tools and processes implemented in the 2022-23 Budget before embedding them into future budget processes. | Complete | An evaluation was undertaken after the 2022-23 Budget was completed, the first time that gender responsive budgeting principles and practices were incorporated into the State budget process.
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
The implementation of DTF's Gender Equality Action Plan was coordinated by a VPS5 Senior Adviser, Diversity and Inclusion with oversight by a VPS6 Senior Manager, Organisational Development in the People and Culture team. The Senior Adviser, Diversity and Inclusion was responsible for developing, coordinating implementation, and reporting on progress against the Gender Equality Action Plan, including undertaking a workplace gender audit, consultation with key stakeholders, implementing specific actions under the plan, and preparing a progress audit and report. The Senior Adviser, Diversity and Inclusion was also responsible for delivering a range of other items in the DTF diversity and inclusion work program, in addition to the gender equality work program. The Gender Equality Action Plan is implemented by key responsible business owner(s) that were assigned to lead the development and implementation of key strategies and actions under the plan that are relevant to their respective functions and operation. This includes The Executive Champion for Gender Equality, People and Culture, Internal Communications and DTF Executives and Managers. The Senior Adviser, Diversity and Inclusion role has not been extended beyond June 2023. Existing DTF People and Culture resources, now located in the Department of Government Services (DGS) People and Governance Branch, will continue to implement the GEAP strategies and measures.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Since 2021, the proportion of women in DTF's workforce decreased by 2% from 51% to 49% in 2023. The percentage of DTF People Matter Survey (PMS) respondents who identify as trans, non-binary or gender diverse increased from 0% in 2021 to 1% in 2023. DTF has improved the gender composition across all VPS classifications. In 2021 women were overrepresented in lower classifications and underrepresented in more senior levels of the organisation. The 2023 audit results indicate that the severity of this gender imbalance across DTF's VPS workforce has reduced; women's overrepresentation in the VPSG3-4 classifications declined from 63% to 55%, an equal balance of the genders at the VPSG5 classification was maintained, and women's representation increased at VPSG6 from 43% in 2021 to 48% in 2023. Women's representation in the SES-1 and Senior Technical Specialist (STS) classifications (level -3) has improved from 38% to 40%. The proportion of women decreased in the SES-2 (56% to 50%) and SES-3 classifications (43% to 33%). The overall gender balance of executives at DTF remains unchanged at 44% women in 2021 and 2023. Improvements in women's representation at senior VPS levels (VPSG5-6) provides DTF a growing talent pool of women to improve gender composition across its executive cohort in coming years. While the proportion of men working part-time increased from 19% to 20%, the proportion of women working full-time decreased by 2% from 47% in 2021 to 45%, which was likely driven by the overall decrease of women's representation by 2%. These changes coincided with an overall decrease in the number of employees working part-time, who represented 13% of the workforce in 2021 and 11% of the workforce in 2023.
Gender composition of governing bodies | No | The gender composition of DTF's governing body, the DTF Board, changed from 43% women in 2021 to 40% women in 2023.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Overall progress DTF achieved progress in its overall base and total remuneration pay gaps. While the results are generally similar between median and mean in the 2023 audit results, median has been used for the purposes of this analysis. DTF's median base salary pay gap decreased from 9.9% in 2021 to 6.1% or $7,908 in 2023, representing an improvement of 3.8%. The median total remuneration pay gap also decreased from 11% in 2021 to 6.4% or $9,265 in 2021. In other terms, according to median total remuneration paid, for each $100 paid to a man, $89 was paid to a woman in 2021, compared to $94 in 2023. DTF's progress has been supported by improvement of pay gaps across VPSG2-4 which are 0% in 2023, as well as a widening of pay gaps in bias toward women at VPSG5 from 0.7% in 2021 to -0.9% in 2023 and at STS and SES-1 from -1.7% to -2.3%. While widening pay gaps are not preferred, they have nonetheless contributed to DTF’s overall pay gap progress. Widening pay gaps The median total remuneration pay gap widened in bias toward men for VPSG6 (1.6% to 2.5%), SES-2 (-3.1% to 3.2%) and SES-3 (-1.6% to 4.8%). These three classifications have the highest median pay gaps for both base salary and total remuneration. The shift in the SES-2 pay gap arose due to departures, both voluntary and involuntary (e.g. Machinery of Government Change), of a number of highly paid women at the SES-2 level since 2021.
Sexual harassment in the workplace | No | In both 2021 and 2023 DTF received a low number of formal sexual harassment complaints, with two complaints recorded in 2021 and one complaint recorded in 2023. Formal sexual harassment complainants represent less than one per cent of the total workforce. Anonymous reports of sexual harassment are higher, with 2% of men and 5% of women in the 2023 PMS reporting they experienced sexual harassment behaviour in the workplace, compared to 2% of men and 4% of women in 2021. DTF's PMS results indicate improvement in some aspects of preventing sexual harassment in the workplace and a lack of progress in others. The percentage of respondents who agreed they feel safe to challenge inappropriate behaviour at work increased from 82% to 85% for men and from 74% to 82% for women. While this improvement was observed, the percentage of women who agreed that DTF encourages respectful workplace behaviour decreased from 92% in 2021 to 88% in 2023. The proportion of women who agreed that DTF takes steps to eliminate bullying, harassment and discrimination also decreased from 80% in 2021 to 71% in 2023. The proportion of men who agreed to these statements remained relatively unchanged between 2021 and 2023. The overall rate of men and women who indicated they did not experience any negative behaviours in the workplace remained relatively unchanged, with 98% of men in both years indicating they didn't experience negative behaviours in the workplace, compared to 96% of women in 2021 and 95% in 2023. In both 2021 and 2023, 95% of men and 90% of women indicated they did not witness bullying, discrimination, sexual harassment, violence, or aggression against a colleague. While these figures indicate most men and women did not experience or witness negative behaviours, the results differ between the genders, with women both experiencing and witnessing negative behaviours at a slighly higher rate than men.
Recruitment and promotion practices in the workplace | Yes | Recruitment In both 2021 and 2023, the gender composition of recruitment was relatively balanced at 52% women in 2021 and 49% women in 2023. 1% of recruitments in 2023 were also self-identifying. Just under half (42%) of recruitments were to senior VPS position (VPSG5-6). The proportion of women recruited into senior VPS roles improved from 2021 to 2023, with 51% women recruited into VPSG6 compared to 46% in 2021, and 49% women recruited into VPS5 roles in 2023 compared to 52% in 2021. The overall balance for VSPG5-6 recruitment was 50% men and women, a slight improvement from 49% women in 2021. The greatest imbalances in recruitment were at lower VPS classifications, which represents over half (54%) of all recruitment for the reporting period. The proportion of women recruited into VPSG2 and VPSG3-4 was 58% and 55% respectively in 2021. Less than half of recruitments were women across both levels in 2023, with women comprising 46% of VPSG2 and 47% of VPSG3-4 recruitments. These imbalances have however contributed to progress in rebalancing the gender composition at both levels, demonstrated by the decreasing overrepresentation of women in the VPSG2-4 classification range. Executive and STS recruitment represented 4% of all recruitment. At the SES-1 and STS level 71% of 2023 recruitments were women. 63% of SES-1 recruitments were women. Although this shows an imbalance of recruitment at this level, a higher proportion of women being appointment to SES-1 roles will be necessary to support the overall improvement of gender composition in the DTF Executive cohort. SES-2 recruitment was balanced at 50% between men and women, comprised of two appointments. Promotions DTF improved the gender balance of promotions, with women securing 42% of promotions in 2021 and 49% in 2023. PMS results support these results. Perceptions of equality in promotions improved and equalised between the genders; in 2021 45% of women and 53% of men agreed they have an equal chance at promotion in DTF and in 2023 67% of women and 68% of men agreed with this statement. This improvement was supported by a greater balance in promotions across the VPSG3-5 classifications, which represent 72% of promotions. 52% of VPSG3-4 promotions were secured by women in 2023, consistent with 2021 results. Half of VPSG5 promotions were women in 2023, representing an improvement of 10% from 2021 (40%). Although DTF improved the proportion of women recruited to senior VPS roles in 2023, the proportion of women promoted to VPSG6 roles decreased from 44% in 2021 to 32% in 2023. Within the VPS5 classification, 52% of higher duties assignees were women and 61% of VPSG5 employees who undertook career development training were also women. While VPSG5 women were overrepresented in higher duties opportunities and career developing training, they were underrepresented in permanent promotions to the VPSG6 classification. At the SES-1 and STS level, 38% of internal promotion in 2023 were women, which is an improvement from 25% in 2021. Excluding STS appointments, women were awarded 43% of promotions to SES-1. Women secured all three promotions (100%) to the SES-2 band over the reporting period. Overrepresentation of women in SES-2 promotions supports maintenance and eventual improvement in the gender composition within this classification and the overall Senior Executive cohort.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Family violence DTF does not collect family violence leave data. 81% of men and 89% of women in 2021 agreed that DTF would support them if they needed to take family violence leave, which improved to 90% of men and 91% of women in 2023. Flexible work In 2021, 9% of the department had a formal flexible work arrangement in place, 81% of whom were women. Total uptake of flexible work arrangements increased with 45% of the department having a plan in place in 2023, 55% of whom are women. However, excluding working remotely flexible work arrangements, which is the most common (59%) flexible work option used, women comprise 70% of flexible work agreements. This imbalance is driven by women comprising the majority of employees working part-time flexible (81%). PMS results indicate DTF employees have greater confidence their requests for flexible arrangements would be given due consideration; in 2021 86% of women and 88% of men agreed their requests would be given due consideration which has increased to 93% for women and 90% for men in 2023. Flexible work arrangements were taken up evenly between the genders among senior leaders in 2023. Similar to department wide results, women comprise 75% of flexible workers when remote working arrangements are excluded, driven by women comprising 90% of senior leaders working part-time flexibly. Parental and carers leave Six per cent of employees used paid or unpaid parental leave during the reporting period. Of those employees who used parental leave 48% were men and 52% were women. The average total absence for those men was 6.1 weeks compared to 27.5 weeks for women, which is lower for both men (8.9 weeks) and women (42.7 weeks) to 2021. Of the employees in 2023 who took carers leave, 49% were men and 51% were women. This represents an improvement from 2021 where women comprised 56% of employees who used carers leave.
Gendered segregation within the workplace | Yes | Gender composition across DTF’s three main occupational categories remained relatively unchanged since 2021, which includes professionals (75%), managers (15%) and clerical and administrative workers (10%). In 2023, women comprised 45% of managers, 48% of professionals and 64% of clerical and administration workers. Between 2021 and 2023 the proportion of women in manager roles did not change, while the proportion of women in professional roles and clerical and administrative roles increased by 1% and 2% respectively. DTF has allocated managerial occupation codes to STS and SES employees only, so the underrepresentation of women in managerial positions largely reflects the gender balance of Executives at DTF. Although the professionals occupation category is relatively balanced (48% women), women are underrepresented the economists occupation, comprising 41% of a cohort of 121 economist employees. Women are overrepresented in clerical and administrative workers due to women occupying all executive assistant and support roles in the department. Results for gender segregation in the PMS improved from 2021 to 2023 for both genders, with 90% of men and 88% of women feeling culturally safe in 2021 compared to 95% of men and 91% of women in 2023. Similar improvements were observed across other gender segregation related questions, such as perceptions of fairness in allocating work regardless of gender. Overall, while employee experience data indicates an improvement in gender segregation experience among DTF employees, actual occupational segregation requires continued efforts to achieve progress.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled