## Sheet1
Project | Sector | Total estimated investment | Entity | Budget year | Estimated completion date | Project status | Estimated expenditure to 30.06.2023 | Estimated remaining expenditure | Notes
85 by 2025 (Level Crossing Removal) (metropolitan various) | Transport | $8,747M | Department of Transport and Planning | 2024-25 | qtr 2 2025-26 | Existing | $7,352M | $1,395M | The TEI has decreased by $84.892 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
A Pathway to more acute mental health beds: Responding to the interim report of the Royal Commission into the Victoria's Mental Health System (statewide) | Health and human services | $492M | Department of Health | 2024-25 | qtr 3 2024-25 | Completed | $475M | $0M
Additional acute mental health beds in regional Victoria (various) | Health and human services | $196M | Department of Health | 2024-25 | qtr 4 2028-29 | Existing | $8M | $188M
Additional VLocity trains (regional various) | Transport | $332M | Victorian Rail Track | 2024-25 | qtr 4 2025-26 | Completed | $315M | $0M | The TEI has decreased by $8.000 million which has been reprioritised to ‘Train radio system upgrade (metropolitan)’.
Arden Precinct Redevelopment (metropolitan) | Transport | tbc | Department of Transport and Planning | 2024-25 | tbc | Existing | tbc | tbc | The TEI and estimated completion date for this initiative are not disclosed at this time to ensure negotiations with affected landholders are not prejudiced.
Austin Hospital Emergency Department Upgrade (Heidelberg) | Health and human services | $275M | Department of Health | 2024-25 | qtr 2 2028-29 | New | $4M | $271M | The TEI includes $45.247 million provided in the 2023-24 Budget in the ‘Hospital Infrastructure Delivery Fund (statewide)’ initiative. This initiative is part of Labor's Financial Statement 2022.
Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | Health and human services | $650M | Department of Health | 2024-25 | qtr 2 2027-28 | Existing | $129M | $522M | The TEI has increased by $54.600 million to reflect additional funding provided in the 2024-25 Budget due to the inclusion of additional scope including expanding and fitting-out the Women’s and Children’s Hub. The estimated completion date has been revised to quarter 2 2027-28 in line with a revised project schedule.
Barwon Heads Road Upgrade (Barwon Heads) | Transport | $359M | Department of Transport and Planning | 2024-25 | qtr 1 2025-26 | Completed | $343M | $0M | The TEI has decreased by $6.195 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $292.000 million of Commonwealth Government funding.
Barwon Women's and Children's Hospital (Geelong) | Health and human services | $514M | Department of Health | 2024-25 | qtr 2 2029-30 | Existing | $38M | $476M | The TEI was previously a range of $500.000 million to $525.000 million and has now been disclosed following the appointment of the builder to deliver the works. The TEI includes $50.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement.
Best Start, Best Life: Infrastructure 2023-24 (statewide) | Education and training | $2,221M | Department of Education | 2024-25 | tbc | Existing | $0M | $0M | The estimated completion date has been revised to ‘tbc’, with cashflows and an overall program completion date to be updated following further project development and a confirmed infrastructure delivery schedule. The Pre-Prep element of Best Start, Best Life has been revised to a 15-year infrastructure program with an overall program completion date of 2036-37.
Better aged care services for regional Victorians (regional various) | Health and human services | $162M | Department of Health | 2024-25 | qtr 1 2028-29 | Existing | $1M | $161M | This initiative is part of Labor’s Financial Statement 2022.
Big Housing Build (statewide) | Health and human services | $2,326M | Homes Victoria | 2024-25 | qtr 4 2027-28 | Existing | $1,482M | $844M | The TEI has decreased by $740.365 million as a result of transfers to grant-funded construction programs for the community housing sector and to Ground Lease Model Project 1 for the expanded scope of the project. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule.
Big Housing Build physical improvements (statewide) | Health and human services | $184M | Homes Victoria | 2024-25 | qtr 4 2023-24 | Completed | $184M | $0M | The TEI reflects four years of funding consistent with the 2020-21 Budget. Homes Victoria has been provided with ongoing capital funding for this initiative until quarter 4 2026-27.
Building a better hospital for Melbourne's inner west (Footscray) | Health and human services | $1,999M | Department of Health | 2024-25 | qtr 1 2025-26 | Existing | $1,454M | $545M | This project is a PPP where the upfront capital investment has resulted in additional scope and whole-of-life benefits while remaining within the project’s affordability benchmark. The TEI reflects the inclusion of the Victoria University project components which are to be reimbursed by Victoria University.
Building a bigger and better Latrobe Regional Hospital (Traralgon) | Health and human services | $224M | Department of Health | 2024-25 | qtr 2 2024-25 | Completed | $217M | $0M
Building a world class Geelong Performing Arts Centre (Geelong) | Culture, sport and community | $140M | Other PNFC | 2024-25 | qtr 1 2024-25 | Completed | $140M | $0M
Building a world class hospital for Frankston families (Frankston) | Health and human services | $1,120M | Department of Health | 2024-25 | qtr 3 2025-26 | Existing | $523M | $597M | This project is a PPP where the upfront capital investment has resulted in additional scope and whole-of-life benefits while remaining within the project’s affordability benchmark. The TEI has increased by $2.000 million due to funding being redirected from the ‘Providing additional bed capacity through modular facilities (metropolitan various)’ initiative to improve the existing emergency department reception and triage area at Frankston Hospital. The estimated completion date reflects the completion of main works by the end of 2025, with the remaining refurbishment and other works completed by 2027-28.
Building a World Class Hospital in Maryborough (Maryborough) | Health and human services | $115M | Department of Health | 2024-25 | qtr 4 2025-26 | Existing | $44M | $71M | The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule.
Building works stimulus (statewide) | Health and human services | $173M | Homes Victoria | 2024-25 | qtr 1 2024-25 | Existing | $172M | $1M | The TEI has decreased by $2.699 million due to budgeted amounts being reclassified as operating expenditure instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 1 2024-25 in line with a revised project schedule.
Car Parks for Commuters (statewide) | Transport | $591M | Victorian Rail Track | 2024-25 | qtr 2 2025-26 | Existing | $464M | $127M | The TEI has decreased by $27.606 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2025-26 to reflect expected environmental approval timelines. The TEI includes $121.999 million of Commonwealth Government funding, revised from the previous amount of $132.899 million in Commonwealth Government funding due to the Commonwealth Infrastructure Investment Program review.
Caulfield Rationalisation Works (metropolitan various) | Transport | $234M | Victorian Rail Track | 2024-25 | qtr 4 2025-26 | Existing | $188M | $46M | The TEI has decreased by $2.525 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | Transport | $465M | Victorian Rail Track | 2024-25 | qtr 2 2025-26 | Completed | $446M | $0M | The TEI has decreased by $0.013 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Clyde Road Upgrade (metropolitan southeast) | Transport | $244M | Department of Transport and Planning | 2024-25 | qtr 1 2027-28 | Existing | $37M | $207M | The TEI is funded by $243.679 million of Commonwealth Government funding.
Community hospitals to give patients the best care (statewide) | Health and human services | $870M | Department of Health | 2024-25 | qtr 4 2025-26 | Existing | $402M | $468M | The TEI has increased by $194.986 million due to $192.066 million in additional funding provided in the 2024-25 Budget and $2.920 million from Growth Areas Infrastructure Contributions funding to deliver additional dialysis chairs at the Sunbury Community Hospital. The scope of the project has changed to progress with a number of sites in delivery and some other sites subject to further service planning. The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule.
Community Safety Statement (statewide) | Justice and emergency services | $315M | Department of Justice and Community Services | 2024-25 | various | Completed | $257M | $0M
Cooling our public housing towers (metropolitan) | Health and human services | $127M | Homes Victoria | 2024-25 | qtr 4 2026-27 | Existing | $4M | $123M | The TEI has decreased by $8.928 million due to a reallocation to the ‘Public Housing Revitalisation (metropolitan)’ initiative to align to the first tranche of the program. This initiative is part of Labor's Financial Statement 2022.
COVID catch-up plan (statewide) | Health and human services | $208M | Department of Health | 2024-25 | qtr 4 2028-29 | Existing | $118M | $89M | The TEI has increased by $7.900 million due to repurposed funds from the ‘Surgery Recovery and Reform Program’ to fund rapid access hubs and Surgical Equipment Innovation Fund expansion projects.
Dandenong Corridor Readiness Works (metropolitan various) | Transport | $275M | Victorian Rail Track | 2024-25 | qtr 2 2025-26 | Existing | $245M | $30M | The TEI has decreased by $0.695 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Delivering the Road Safety Action Plan (statewide) | Transport | $230M | Department of Transport and Planning | 2024-25 | tbc | Existing | $114M | $116M | The TEI has decreased by $15.317 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $142.484 million of Commonwealth Government funding. The estimated completion date is being negotiated with the Commonwealth Government.
Eastern Freeway Upgrade (Springvale to Hoddle) | Transport | $5,709M | Department of Transport and Planning | 2024-25 | qtr 2 2028-29 | Existing | tbc | tbc | This project was previously published as part of ‘North East Link (State and Freeway Packages)’ in the 2023-24 Budget. The funding reflects a combination of existing and additional funding, as reported in the 2023-24 Budget Update. The project includes a share of $1.750 billion of Commonwealth Government funding. The estimated expenditure will be reported when the procurement processes and commercial arrangements are finalised.
E-Class Tram Infrastructure Program (metropolitan various) | Transport | $789M | Victorian Rail Track | 2024-25 | qtr 4 2027-28 | Existing | $567M | $222M
Emergency Departments Expansion Program – Casey Hospital and Werribee Mercy Hospital (Casey) (Werribee) | Health and human services | $280M | Department of Health | 2024-25 | qtr 4 2026-27 | Existing | $18M | $262M | The TEI has increased by $43.521 million to reflect $35.521 million additional funding provided in the 2024-25 Budget for the Casey Hospital Emergency Department Expansion Project and $8.000 million additional funding for the Werribee Mercy Hospital due to funding being redirected from the ‘Providing additional bed capacity through modular facilities (metropolitan various)’ initiative.
Emergency Services High-priority infrastructure (statewide) | Justice and emergency services | $128M | Department of Justice and Community Services | 2024-25 | qtr 4 2026-27 | Existing | $107M | $21M | The TEI has increased by $2.209 million due to additional funding to support delivery of Tranche 2 projects. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Essential maintenance and compliance (statewide) | Education and training | $110M | Department of Education | 2024-25 | qtr 4 2026-27 | New | $0M | $110M
Essential maintenance and compliance 2022-23 (statewide) | Education and training | $120M | Department of Education | 2024-25 | qtr 4 2025-26 | Existing | $58M | $62M
Essential maintenance and compliance 2023-24 (statewide) | Education and training | $104M | Department of Education | 2024-25 | qtr 4 2025-26 | Existing | $2M | $102M
Expanding mental health treatment facilities for Victoria's youth (statewide) | Health and human services | $141M | Department of Health | 2024-25 | qtr 4 2024-25 | Existing | $35M | $106M
Fishermans Bend Innovation Precinct at the former General Motors Holden Site – Stage 1 (Melbourne) | Culture, sport and community | $179M | Department of Transport and Planning | 2024-25 | qtr 2 2025-26 | Existing | $93M | $86M | The TEI has increased by $171.943 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2025-26 in line with a revised project schedule.
Forensic Mental Health Expansion Project Stage 1 and 2 (Fairfield) | Health and human services | $462M | Department of Health | 2024-25 | qtr 4 2024-25 | Existing | $160M | $303M
FRV Capital Upgrades Program (statewide) | Justice and emergency services | $112M | Fire Rescue Victoria | 2024-25 | qtr 4 2027-28 | Existing | $44M | $67M | The TEI has increased by $4.448 million in line with a revised project scope.
Geelong City Deal (Geelong) | Culture, sport and community | $111M | Department of Jobs, Skills, Industry and Regions | 2024-25 | qtr 4 2025-26 | Existing | $27M | $84M | The TEI has reduced by $295.454 million due to funding now being separately reported as the ‘Nyaal Banyul Geelong Convention and Event Centre (regional)’, budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards and additional funding approved for the project. The TEI includes $106.347 million of Commonwealth Government funding.
Geelong Fast Rail (regional various) | Transport | tbc | Victorian Rail Track | 2024-25 | tbc | Discontinued | tbc | $0M | As part of the Commonwealth’s Infrastructure Investment Review, the Commonwealth has withdrawn it's funding for the project. The Victorian Government is working to conclude the project in light of this decision.
Goulburn Valley Health redevelopment - planning and development (Shepparton) | Health and human services | $229M | Department of Health | 2024-25 | qtr 4 2023-24 | Completed | $229M | $0M
Great Ocean Road Renewal (Barwon South West) | Transport | $255M | Department of Transport and Planning | 2024-25 | qtr 1 2025-26 | Existing | $116M | $139M | The estimated completion date has been revised to quarter 1 2025-26 in line with a revised project schedule.
Hall Road Upgrade (Skye) | Transport | $282M | Department of Transport and Planning | 2024-25 | qtr 3 2025-26 | Completed | $276M | $0M | The TEI has decreased by $0.329 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $141.252 million of Commonwealth Government funding.
High Capacity Metro Trains (metropolitan various) | Transport | $2,265M | Victorian Rail Track | 2024-25 | qtr 4 2024-25 | Existing | $2,219M | $46M | The estimated completion date has been revised to quarter 4 2024-25 in line with a revised project schedule. The TEI includes financing costs.
Homes Victoria Ground Lease Model Project 1 (metropolitan) | Health and human services | $517M | Homes Victoria | 2024-25 | qtr 2 2026-27 | Existing | $398M | $120M | This project is being delivered as an availability PPP under a Ground Lease Model. The TEI has been revised following the outcome of commercial negotiations to deliver an additional 286 social and affordable homes at the Flemington site. The updated TEI includes project development, demolition, procurement costs, capital contribution, and construction costs being funded by Building Communities. The estimated completion date has been revised to quarter 2 2026‑27 in line with the additional scope of works.
Homes Victoria Ground Lease Model Project 2 (metropolitan) | Health and human services | $687M | Homes Victoria | 2024-25 | qtr 2 2026-27 | Existing | $182M | $504M | This project is being delivered as an availability PPP under a Ground Lease Model. The TEI has been revised following financial close of the project in November 2023. The updated TEI includes project development, demolition, procurement costs, capital contribution, and construction costs being funded by Building Communities. The estimated completion date has been revised to quarter 2 2026‑27 in line with the contract outcome.
Hospital Infrastructure Delivery Fund (statewide) – A new hospital for West Gippsland to put patients first – A new Queen Elizabeth II Hospital in Melbourne’s East – A Hospital Plan for the South-East – Dandenong Hospital – Wonthaggi hospital redevelopment | Health and human services | $116M | Department of Health | 2024-25 | qtr 2 2026-27 | Existing | $7M | $108M | The TEI has decreased by $204.447 million due to separate reporting of ‘Austin Hospital Emergency Department Upgrade (Heidelberg)’, ‘Monash Medical Centre Redevelopment (Clayton)’ and ‘Northern Hospital Redevelopment (Epping)’ in the 2024-25 Budget as these initiatives are now funded for construction. This initiative is part of Labor’s Financial Statement 2022.
Improving the Calder Freeway (Calder Park) | Transport | tbc | Department of Transport and Planning | 2024-25 | tbc | Discontinued | $13M | $87M | The TEI includes $50.000 million of Commonwealth Government funding. As part of the Commonwealth's Infrastructure Investment Review, the Commonwealth has withdrawn funding for the project. The Victorian Government has paused the project and is working with the Commonwealth to understand the impact of this decision.
Ison Road Rail Overpass (Werribee) | Transport | $111M | Department of Transport and Planning | 2024-25 | qtr 2 2025-26 | Existing | $47M | $63M | The TEI has decreased by $2.994 million due to budgeted amounts being reclassified as operating instead of capital, in line with accounting standards. The TEI includes $56.900 million of Commonwealth Government funding and early works funding.
Kananook Train Maintenance Facility Stage 2 (metropolitan) | Transport | $365M | Victorian Rail Track | 2024-25 | qtr 1 2025-26 | Existing | $183M | $182M | The TEI has decreased by $0.402 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 1 2025-26 to reflect a more accurate forecast following contract award.
Kardinia Park Stadium Stage 5 Redevelopment (Geelong) | Culture, sport and community | $142M | Other PNFC | 2024-25 | qtr 4 2024-25 | Completed | $142M | $0M
Keeping Victorians moving (metropolitan) | Transport | $173M | Department of Transport and Planning | 2024-25 | qtr 4 2024-25 | Existing | $169M | $4M | The estimated completion date has been revised to quarter 4 2024-25 due to delays in software upgrades to align with the latest hardware implemented.
Land acquisition 2021-22 (various) | Education and training | $297M | Department of Education | 2024-25 | qtr 4 2024-25 | Existing | $211M | $86M | The estimated completion date has been revised to quarter 4 2024-25 due to land acquisition timelines.
Land acquisition 2022-23 (various) | Education and training | $251M | Department of Education | 2024-25 | qtr 4 2024-25 | Existing | $128M | $122M | The TEI has increased by $16.700 million due to additional funding from the Growth Areas Infrastructure Contribution.
M80 Ring Road Upgrade (Greensborough) | Transport | $3,824M | Department of Transport and Planning | 2024-25 | qtr 2 2028-29 | Existing | $720M | $3,104M | This project was previously published as part of ‘North East Link (State and Freeway Packages)’ in the 2023-24 Budget. The funding reflects a combination of existing and additional funding, as reported in the 2023-24 Budget Update. The project includes a share of $1.750 billion of Commonwealth Government funding.
M80 Ring Road upgrade (metropolitan north and west) | Transport | $657M | Department of Transport and Planning | 2024-25 | qtr 3 2024-25 | Existing | $500M | $157M | The TEI includes $349.130 million of Commonwealth Government funding.
Maintaining Victoria's road network (statewide) | Transport | $146M | Department of Transport and Planning | 2024-25 | qtr 4 2024-25 | Existing | $133M | $13M | The TEI has increased by $26.637 million due to project funding that was previously withheld and is now fully released. The estimated completion date has been revised to quarter 4 2024-25 due to the rescheduling of road works at Spout Creek.
Meeting ambulance response times (statewide) | Health and human services | $177M | Department of Health | 2024-25 | qtr 2 2025-26 | Existing | $144M | $34M | The TEI has increased by $7.961 million to deliver a new ambulance station at Wyndham Vale and is funded from additional Growth Areas Infrastructure Contributions funding. The estimated completion date for the final remaining sites has been revised to quarter 2 2025-26 in line with a revised project schedule.
Melbourne Arts Precinct transformation Phase One (Melbourne) | Culture, sport and community | $1,574M | Other PNFC | 2024-25 | qtr 2 2028-29 | Existing | $221M | $1,353M
Melton Line upgrade (statewide) | Transport | $641M | Victorian Rail Track | 2024-25 | qtr 4 2028-29 | Existing | $1M | $640M | This initiative is part of Labor's Financial Statement 2022.
Men's prison system capacity (statewide) | Justice and emergency services | $754M | Department of Justice and Community Services | 2024-25 | qtr 3 2024-25 | Existing | $612M | $142M | The TEI has decreased by $4.095 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 3 2024-25 in line with a revised project schedule.
Metro Tunnel (metropolitan various) | Transport | $12,642M | Victorian Rail Track | 2024-25 | qtr 2 2025-26 | Existing | $11,835M | $808M | The TEI excludes financing costs.
Metro Tunnel readiness (statewide) | Transport | $151M | Victorian Rail Track | 2024-25 | qtr 2 2025-26 | New | $0M | $151M
Metro Tunnel Readiness 2023-24 (metropolitan) | Transport | $241M | Victorian Rail Track | 2024-25 | qtr 2 2025-26 | Existing | $155M | $0M | The TEI has increased by $2.784 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Metropolitan Health Infrastructure Fund (metropolitan various) | Health and human services | $187M | Department of Health | 2024-25 | qtr 4 2024-25 | Existing | $135M | $52M
Metropolitan rail infrastructure renewal program (metropolitan various) | Transport | $942M | Victorian Rail Track | 2024-25 | qtr 4 2028-29 | Existing | $220M | $721M | As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2023-24 to 2028-29.
Metropolitan Road and Intersection Upgrades (metropolitan various) | Transport | $121M | Department of Transport and Planning | 2024-25 | qtr 3 2025-26 | Existing | $43M | $78M | The TEI has increased by $4.420 million due to further service relocation charges and higher land acquisition costs. The estimated completion date has been revised to quarter 3 2025-26 in line with a revised project schedule.
Metropolitan road upgrades 2022-23 (metropolitan) | Transport | $100M | Department of Transport and Planning | 2024-25 | qtr 4 2025-26 | Existing | $38M | $62M | The TEI has decreased by $0.612 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Mickleham Road Upgrade – Stage 1 (Greenvale) | Transport | $207M | Department of Transport and Planning | 2024-25 | qtr 4 2025-26 | Existing | $157M | $50M | The TEI has decreased by $0.110 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $109.540 million of Commonwealth Government funding.
Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project (Cheltenham) | Health and human services | $140M | Department of Health | 2024-25 | qtr 4 2025-26 | Existing | $45M | $95M | The TEI has increased by $5.000 million due to funding being redirected from the ‘Wantirna aged care redevelopment (Wantirna)’ initiative completed in the 2023-24 Budget.
Modernise the Digital Train Radio System (metropolitan) | Transport | $180M | Victorian Rail Track | 2024-25 | qtr 2 2030-31 | New | $0M | $180M
Monash Medical Centre Redevelopment (Clayton) | Health and human services | $535M | Department of Health | 2024-25 | qtr 4 2028-29 | New | $2M | $533M | The TEI includes $36.700 million provided in the 2023-24 Budget in the ‘Hospital Infrastructure Delivery Fund (statewide)’ initiative. This initiative is part of Labor's Financial Statement 2022.
More help for Victorian mums and dads (statewide) | Health and human services | $123M | Department of Health | 2024-25 | qtr 2 2025-26 | Existing | $112M | $11M | The estimated completion date for the final remaining sites has been revised to quarter 2 2025-26 in line with a revised project schedule.
More hospital and aged care beds for Melbourne’s East (Angliss Hospital Expansion Stage 2) (Upper Ferntree Gully) | Health and human services | $112M | Department of Health | 2024-25 | qtr 4 2026-27 | Existing | $7M | $105M
More VLocity trains 2022-23 (regional) | Transport | $250M | Victorian Rail Track | 2024-25 | qtr 4 2026-27 | Existing | $199M | $51M
More VLocity trains 2023-24 (regional) | Transport | $601M | Victorian Rail Track | 2024-25 | qtr 4 2027-28 | Existing | $297M | $304M | This initiative is part of Labor's Financial Statement 2022.
Murray Basin Rail Project (regional various) | Transport | $807M | Victorian Rail Track | 2024-25 | tbc | Existing | $787M | $21M | The TEI has increased by $18.500 million due to reprioritisation from Ballarat Line Upgrade and has decreased by $5.643 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date is subject to significant signalling design work and co-ordination with the pipeline of projects underway across the program and will be updated when these arrangements have been settled. The TEI includes $470.400 million of Commonwealth Government funding.
National Water Infrastructure Development Fund - National Partnership Agreement (regional various) | Water | $169M | Department of Energy, Environment and Climate Action | 2024-25 | qtr 4 2025-26 | Existing | $143M | $26M | The TEI includes $168.893 million of Commonwealth Government funding.
New Melton Hospital (Cobblebank) | Health and human services | $900M-$1,000M | Department of Health | 2024-25 | qtr 4 2028-29 | Existing | $47M | $0M | The TEI for this initiative will be reported as commercial arrangements are finalised.
New metropolitan trains (statewide) | Transport | $986M | Victorian Rail Track | 2024-25 | qtr 3 2027-28 | Existing | $267M | $719M | The estimated completion date has been revised to quarter 3 2027-28 in line with a revised project schedule.
New School Construction 2021-22 (statewide) | Education and training | $488M | Department of Education | 2024-25 | qtr 1 2025-26 | Completed | $487M | $0M | The TEI has decreased by $0.281 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $0.499 million in co-contributions from the school.
New Schools construction (statewide) | Education and training | $948M | Department of Education | 2024-25 | qtr 3 2025-26 | New | $12M | $936M | The TEI includes $35.472 million from the Growth Areas Infrastructure Contribution, and $11.000 million reprioritised from the ‘New Schools Planning Fund’ initiative funded in the 2023-24 Budget. To open in 2026: - Ballarto Road Primary School (interim name) - Casey Central Primary School (interim name) - Clyde Creek North Primary School (interim name) - Clyde Creek North Secondary School (interim name) - Cobblebank Secondary School (interim name) - Horseshoe Bend Primary School (interim name) - Leneva (Frederic Street Road) Primary School (interim name) - Lockerbie Specialist School (interim name) - Mickleham South Primary School (interim name) - Plumpton Primary School (interim name) - Point Cook South Specialist School (interim name) - Tarneit Plains Primary School (interim name) - Toolern Waters Primary School (interim name) - Wallan East Primary School (interim name) - Warralily Park Primary School (interim name) - Wollert Andrews Road Primary School (interim name) Additional stages of new schools: - Mickleham Secondary College - Wollert Secondary School
New schools construction 2022-23 (statewide) | Education and training | $723M | Department of Education | 2024-25 | qtr 1 2025-26 | Existing | $688M | $34M | The TEI has increased by $0.637 million to extend scope for additional school requirements, funded by co-contributions from schools. This is offset by a TEI decrease of $6.291 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
New schools construction 2023-24 (statewide) | Education and training | $672M | Department of Education | 2024-25 | qtr 3 2025-26 | Existing | $128M | $544M | The TEI has increased by $98.584 million due to market escalation in the construction sector.
New Tarneit railway station (Tarneit) | Transport | $124M | Victorian Rail Track | 2024-25 | qtr 4 2025-26 | Existing | $4M | $120M
New trains for Sunbury (metropolitan various) | Transport | $1,763M | Victorian Rail Track | 2024-25 | qtr 2 2024-25 | Existing | $1,199M | $563M | The TEI has decreased by $26.194 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
New Wyndham Law Court Development (Werribee) | Justice and emergency services | $275M | Court Services Victoria | 2024-25 | qtr 3 2024-25 | Existing | $193M | $82M | The TEI has increased by $3.800 million due to funds being redirected from the ‘Bendigo Law Courts Redevelopment (Bendigo)’ project for additional road and car parking works.
Next generation computer aided dispatch system for Triple Zero (statewide) | Justice and emergency services | tbc | Department of Justice and Community Services | 2024-25 | tbc | Existing | tbc | tbc | The TEI, estimated expenditure, and estimated completion date are not reported at this time as commercial arrangements are still to be finalised.
Next Generation Trams (metropolitan various) | Transport | $1,440M | Victorian Rail Track | 2024-25 | qtr 4 2028-29 | Existing | $251M | $1,189M | The TEI has increased by $35.601 million due to additional scope for the Automatic Vehicle Monitoring System and decreased by $3.000 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
North East Link – Primary Package (Tunnels) and State Toll Co (Greensborough) | Transport | $14,034M | State Tolling Corporation | 2024-25 | qtr 2 2028-29 | Existing | $4,556M | $9,478M | The TEI includes the $11.100 billion contract with the Spark consortium to deliver the Primary Package and other costs associated with the operations of the State Tolling Corporation. The project includes a share of $1.750 billion of Commonwealth Government funding. The TEI excludes financing costs associated with the Primary Package. The State Tolling Corporation is responsible for providing funding contributions to the ‘North East Link – Primary Package (Tunnels)’ initiative.
North East Link Connections (Bulleen/Watsonia) | Transport | $2,642M | Department of Transport and Planning | 2024-25 | qtr 2 2028-29 | Existing | $858M | $1,784M | This project was previously published as part of ‘North East Link (State and Freeway Packages)’ in the 2023-24 Budget. The funding reflects a combination of existing and additional funding, as reported in the 2023-24 Budget Update. The project includes a share of $1.750 billion of Commonwealth Government funding.
Northern Hospital Redevelopment (Epping) | Health and human services | $813M | Department of Health | 2024-25 | qtr 2 2029-30 | New | $3M | $809M | The TEI includes $122.500 million provided in the 2023-24 Budget in the ‘Hospital Infrastructure Delivery Fund (statewide)’ initiative and $17.000 million from ‘Building emergency departments kids and families can count on’. This initiative is part of Labor’s Financial Statement 2022.
Nyaal Banyul Geelong Convention and Event Centre (regional) | Culture, sport and community | $449M | Department of Jobs, Skills, Industry and Regions | 2024-25 | qtr 4 2025-26 | Existing | $144M | $305M | This project is being delivered as a precinct partnership under an availability PPP. The TEI reflects the outcome of financial close of the project in December 2023. This initiative was previously reported under the ‘Geelong City Deal (Geelong)’ in the 2023-24 Budget. The TEI includes $30.000 million of Commonwealth Government funding and $3.000 million of City of Greater Geelong funding. The estimated completion date of quarter 4 2025-26 reflects the completion of the convention and event centre. The TEI excludes financing, land acquisition and ongoing operating costs.
Off-farm Efficiency Program (statewide) | Environment | $124M | Department of Energy, Environment and Climate Action | 2024-25 | qtr 4 2023-24 | Completed | $124M | $0M | The project name has changed from ‘Goulburn Murray Water - Water Efficiency Project (statewide)’ when it was published in the 2023‑24 Budget. The TEI has decreased by $7.385 million to align with the allocation of Commonwealth funding. The TEI includes $124.050 million of Commonwealth Government funding.
Pakenham Roads Upgrade (Pakenham) | Transport | $391M | Department of Transport and Planning | 2024-25 | qtr 3 2026-27 | Existing | $161M | $231M | The TEI is funded by $391.495 million of Commonwealth Government funding.
Princes Highway East Duplication Stage 3 (regional various) | Transport | $245M | Department of Transport and Planning | 2024-25 | qtr 4 2025-26 | Completed | $244M | $0M | The TEI includes $202.600 million of Commonwealth Government funding.
Public Housing Renewal Program (statewide) | Health and human services | $185M | Homes Victoria | 2024-25 | qtr 1 2025-26 | Existing | $174M | $11M | The estimated completion date has been revised to quarter 1 2025-26 to align with the revised project schedule.
Public Housing Revitalisation Program (metropolitan) | Health and human services | $436M | Homes Victoria | 2024-25 | various | New | $15M | $422M | The TEI includes $8.928 million due to a reallocation from the ‘Cooling our public housing towers (metropolitan)’ initiative to align to the first tranche of redevelopment of public housing towers.
Public Transport Ticketing Asset Renewal (statewide) | Transport | $544M | Victorian Rail Track | 2024-25 | qtr 4 2026-27 | Existing | $118M | $426M
Ready for school: Kinder for every three-year-old 2019-20 (statewide) | Education and training | $282M | Department of Education | 2024-25 | qtr 4 2025-26 | Existing | $205M | $77M | The TEI has increased by $1.580 million to extend its scope for additional school requirements, funded by co-contributions from local councils. The TEI includes $0.576 million in co-contributions from schools and a total of $2.146 million in co-contributions from local councils. The estimated completion date has been revised to quarter 4 2025-26 to align with updated demand modelling.
Ready for school: kinder for every three-year-old 2023-24 (statewide) | Education and training | $208M | Department of Education | 2024-25 | qtr 3 2027-28 | Existing | $5M | $203M | The project name has changed from ‘Kinder for every three-year-old’ when it was published in the 2023-24 Budget.
Redevelopment of Royal Melbourne Hospital and Royal Women's Hospital (Arden/Parkville) | Health and human services | $2,338M | Department of Health | 2024-25 | tbc | Existing | $65M | $2,273M | The estimated completion date is being re-evaluated due to the project now progressing at a single site in Parkville.
Regional Health Infrastructure Fund (regional various) | Health and human services | $250M | Department of Health | 2024-25 | qtr 4 2025-26 | Existing | $240M | $10M | The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule.
Regional Health Infrastructure Fund 2019-20 (regional various) | Health and human services | $100M | Department of Health | 2024-25 | qtr 4 2025-26 | Existing | $78M | $22M | The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule.
Regional Health Infrastructure Fund 2020-21 (regional various) | Health and human services | $120M | Department of Health | 2024-25 | qtr 4 2025-26 | Existing | $82M | $38M | The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule.
Regional Health Infrastructure Fund 2022-23 (regional various) | Health and human services | $300M | Department of Health | 2024-25 | qtr 4 2026-27 | Existing | $67M | $233M | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
Regional Housing Fund (regional) | Health and human services | $701M | Homes Victoria | 2024-25 | qtr 4 2027-28 | New | $55M | $646M | The Regional Housing Fund also includes $299 million in output funding.
Regional Rail Revival - Bendigo/Echuca Line Upgrade (regional various) | Transport | $184M | Victorian Rail Track | 2024-25 | qtr 4 2024-25 | Completed | $151M | $0M | The TEI has increased by $10.000 million due to reprioritisation from Avon River Bridge Upgrade for the extended development timeframe required as a result of V/line's new track standard and has decreased by $1.158 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $159.108 million of Commonwealth Government funding.
Regional Rail Revival - Gippsland Line Upgrade Stage 1 (regional various) | Transport | $563M | Victorian Rail Track | 2024-25 | tbc | Existing | $563M | $0M | The TEI has increased by $37.500 million due to reprioritisation from other projects and has decreased by $6.200 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date is subject to signalling design work and co-ordination with the pipeline of projects underway across the program and will be updated when these arrangements have been settled. The TEI includes $449.400 million of Commonwealth Government funding.
Regional Rail Revival - Shepparton Line Upgrade - Stage 3 (Shepparton) | Transport | $399M | Victorian Rail Track | 2024-25 | tbc | Existing | $289M | $110M | The TEI has decreased by $0.630 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date is subject to signalling design work and co-ordination with the pipeline of projects underway across the program and will be updated when these arrangements have been settled. The TEI includes $320.000 million of Commonwealth Government funding.
Regional Rail Revival - Warrnambool Line Upgrade - Stage 2 (regional various) | Transport | $251M | Victorian Rail Track | 2024-25 | tbc | Existing | $149M | $102M | The TEI has decreased by $9.392 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date will be advised when the relevant commercial arrangements have been finalised. The TEI includes $208.000 million of Commonwealth Government funding.
Regional Rail Revival - Waurn Ponds Track Duplication - Stage 2 (regional various) | Transport | $827M | Victorian Rail Track | 2024-25 | qtr 2 2024-25 | Existing | $666M | $161M | The TEI has decreased by $32.900 million due to reprioritisation to Warrnambool Line Upgrade Stage 1 and has decreased by $39.621 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been confirmed as quarter 2 2024-25 following settlement of commissioning events being resolved for this project. The TEI includes $754.000 million of Commonwealth Government funding.
Regional rail sustainability 2021-22 (statewide) | Transport | $465M | Victorian Rail Track | 2024-25 | qtr 4 2024-25 | Existing | $351M | $113M
Regional rail sustainability 2022-23 (statewide) | Transport | $205M | Victorian Rail Track | 2024-25 | qtr 4 2025-26 | Existing | $173M | $32M
Relocatable Buildings Program - providing relocatable buildings to meet growing demand (statewide) | Education and training | $152M | Department of Education | 2024-25 | qtr 4 2024-25 | New | $0M | $152M
Relocatable Buildings Program 2023-24 (statewide) | Education and training | $152M | Department of Education | 2024-25 | qtr 4 2024-25 | Completed | $152M | $0M | The TEI has increased by $4.388 million due to budget amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Road Blitz to Get Families Home Sooner and Safer (statewide) | Transport | $674M | Department of Transport and Planning | 2024-25 | qtr 4 2028-29 | Existing | $32M | $642M | The TEI has decreased by $0.200 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $170.000 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022.
Road Maintenance (statewide) | Transport | $105M | Department of Transport and Planning | 2024-25 | qtr 4 2024-25 | New | $0M | $105M
Road Maintenance and Renewal (statewide) | Transport | $1,091M | Department of Transport and Planning | 2024-25 | qtr 4 2032-33 | Existing | $16M | $1,075M | The TEI has decreased by $158.710 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Road Safety Strategy (statewide) | Transport | $277M | Department of Transport and Planning | 2024-25 | qtr 4 2024-25 | Existing | $216M | $62M | The TEI has decreased by $42.800 million due to the budget transfer to the Department of Justice and Community Safety for additional intersection speed and highway network cameras. The TEI includes $183.300 million of Commonwealth Government funding and funding from the Transport Accident Commission.
Rolling stock maintenance and disposal programs (statewide) | Transport | $117M | Victorian Rail Track | 2024-25 | qtr 1 2025-26 | Existing | $64M | $54M | The TEI has decreased by $5.500 million which has been reprioritised to ‘Next Generation Trams (metropolitan various)’.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Health and human services | $320M | Department of Health | 2024-25 | qtr 4 2023-24 | Completed | $320M | $0M | The TEI has increased by $2.000 million in line with a revised project schedule, funded from savings from the Victorian Heart Hospital initiative which was completed in the 2023-24 Budget. The Royal Victorian Eye and Ear Hospital project was published as completed in the 2023-24 Budget.
Rural and Regional PSRACS Revitalisation Strategy Stage 1 (2022-23) (regional various) | Health and human services | $143M | Department of Health | 2024-25 | qtr 4 2027-28 | Existing | $10M | $133M
Rural and Regional Roads Package - Rutherglen alternative truck route (Rutherglen) | Transport | tbc | Department of Transport and Planning | 2024-25 | tbc | Discontinued | $1M | tbc | As part of the Commonwealth's Infrastructure Investment Review, the Commonwealth has withdrawn funding for this project. The Victorian Government has paused this project and is working with the Commonwealth to understand the impact of this decision.
School upgrades - growth for 2022 (metropolitan various) | Education and training | $131M | Department of Education | 2024-25 | qtr 1 2024-25 | Completed | $130M | $0M | The TEI includes $0.246 million in total co-contributions from the schools and $0.551 million is funded from a third party for necessary re-tendering.
Social Housing Accelerator Program (statewide) | Health and human services | $463M | Homes Victoria | 2024-25 | qtr 4 2027-28 | New | $3M | $460M | The TEI is funded by $463.343 million of Commonwealth Government funding.
South Dynon Train Maintenance Facility Stage 1 (statewide) | Transport | $122M | Victorian Rail Track | 2024-25 | qtr 4 2025-26 | Completed | $120M | $0M
South Dynon Train Maintenance Facility Stage 2 (statewide) | Transport | $297M | Victorian Rail Track | 2024-25 | qtr 1 2026-27 | Existing | $64M | $233M | The estimated completion date has been revised to quarter 1 2026-27 following a more precise forecast obtained after contract award.
Special school upgrades 2022-23 (statewide) | Education and training | $326M | Department of Education | 2024-25 | qtr 2 2025-26 | Existing | $96M | $231M | The TEI has increased by $0.450 million to extend scope for additional school requirements, funded by co-contributions from schools.
State Basketball Centre redevelopment (Knox) | Culture, sport and community | $129M | Other PNFC | 2024-25 | qtr 1 2024-25 | Existing | $128M | $0M | The TEI has increased by $0.250 million due to additional funds to enable mechanical systems and amenity upgrades of the ‘Mini Show Court' into the project's scope. The TEI also includes a $27.000 million contribution from the Knox City Council.
Suburban Parks Program (Creating a Ring of New Parkland) (metropolitan) | Culture, sport and community | $211M | Department of Energy, Environment and Climate Action | 2024-25 | qtr 4 2023-24 | Completed | $211M | $0M | The TEI has increased by $18.841 million to reflect revised project costings.
Suburban Rail Loop - Airport (metropolitan various) | Transport | tbc | Victorian Rail Track | 2024-25 | tbc | Existing | $1,015M | tbc | The State and Commonwealth governments have committed $5.000 billion each to the project. The TEI and estimated completion date are not reported at this time as the Commonwealth Government has only recently appointed a mediator. With Australia Pacific Airports (Melbourne) Pty Ltd continuing to demand compensation and an underground station, the completion date is likely to be at least four years delayed.
Suburban Rail Loop East – Development, Initial and Early Works (metropolitan various) | Transport | $2,372M | Victorian Rail Track | 2024-25 | qtr 3 2025-26 | Existing | $1,161M | $1,211M | The estimated completion date has been revised to quarter 3 2025-26 to reflect a revised schedule of works relating to the completion of initial and early works for the project.
Suburban Rail Loop East – Main Works (metropolitan various) | Transport | tbc | Victorian Rail Track | 2024-25 | tbc | Existing | tbc | tbc | The Suburban Rail Loop East is expected to cost between $30.000–$34.500 billion and is targeting delivery by 2035. This expected cost includes $3.610 billion (GST exclusive) for the Suburban Rail Loop East tunnel south contract from Cheltenham to Glen Waverley, which was awarded in December 2023. The TEI, remaining expenditure and estimated completion date will be disclosed following the procurement of the main works packages. The TEI includes $2.200 billion of Commonwealth Government funding.
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | Transport | $2,523M | Department of Transport and Planning | 2024-25 | qtr 2 2025-26 | Existing | $2,318M | $205M | The TEI has increased by $10.204 million due to additional funding from developer contributions for the design and construction of the intersection works as part of the Narre Warren Cranbourne Road Upgrade Project and the Bridge Inn Road Upgrade Project. The TEI includes $1,140.000 million of Commonwealth Government funding.
Sunshine Station Masterplan (Sunshine) | Transport | tbc | Victorian Rail Track | 2024-25 | tbc | Existing | tbc | tbc | The TEI, estimated expenditure and estimated completion date will be disclosed following the completion of the procurement process.
Sustaining statewide health service delivery at The Alfred (Prahran) | Health and human services | $118M | Department of Health | 2024-25 | qtr 4 2027-28 | New | $0M | $118M
Targeted Road Safety Works (statewide) | Transport | $106M | Department of Transport and Planning | 2024-25 | qtr 2 2024-25 | Existing | $72M | $34M
Technology and resources to support Victoria's fines system (statewide) | Justice and emergency services | $180M | Department of Justice and Community Services | 2024-25 | qtr 4 2025-26 | Existing | $114M | $66M | The TEI has increased by $38.346 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2025-26 reflecting the updated system build and migration approach taken to minimise transition risks.
The Alfred Hospital urgent infrastructure (Prahran) | Health and human services | $175M | Department of Health | 2024-25 | qtr 4 2029-30 | Existing | $13M | $161M | The TEI has increased by $105.000 million due to a revised strategy to deliver fire safety compliance works. The estimated completion date has been revised to quarter 4 2029-30 in line with the revised strategy to deliver fire safety compliance works.
Train radio system upgrade (metropolitan) | Transport | $205M | Victorian Rail Track | 2024-25 | qtr 4 2027-28 | Existing | $54M | $151M | The TEI has increased by $32.284 million, funded from reprioritisations from various rolling stock projects.
Tram infrastructure upgrades (metropolitan various) | Transport | $428M | Victorian Rail Track | 2024-25 | qtr 1 2025-26 | Existing | $222M | $207M | The TEI has decreased by $0.308 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 1 2025-26 to reflect a more accurate forecast obtained after contract award.
Twenty-five more level crossing removals by 2030 (Level Crossing Removal) (metropolitan various) | Transport | $6,510M | Department of Transport and Planning | 2024-25 | qtr 4 2029-30 | Existing | $303M | $6,207M | The TEI has decreased by $12.535 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Warrnambool Base Hospital redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | Health and human services | $384M | Department of Health | 2024-25 | qtr 4 2026-27 | Existing | $88M | $296M
West Gate Tunnel (metropolitan various) | Transport | $10,159M | Department of Transport and Planning | 2024-25 | qtr 2 2025-26 | Existing | $9,130M | $1,029M | The TEI has increased by $5.112 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Western Highway duplication - Ballarat to Stawell (regional various) | Transport | $656M | Department of Transport and Planning | 2024-25 | tbc | Existing | $603M | $53M | The estimated completion date is to be confirmed once planning activities are completed. The TEI includes $499.380 million of Commonwealth Government funding.