# Community Support Fund

Final Outcomes Summary for the Projects Completed 2021-22

Contents

St Kilda Gatehouse  The Young Women’s Project	2

HE Parker Reserve Fit Out Project	3

Mitcham Cricket Club clubrooms fit out project	3

Rebuild of the La Mama Theatre	4

2015-16 Community Facilities Funding Program	4

Cobram Cricket Club Scoreboard	5

Queenscliff Cultural Hub	6

East Ballarat Cricket Club Community Cricket Nets Project	7

Hurstbridge Football and Cricket Pavilion Changeroom Upgrade	8

Heathmont Bowls Club Synthetic Bowling Rink Replacement	9

McIntyre Wildlife Shelter	10

Peter Macallum Cancer Centre Mobile Exhibition Program	11

Avoca Silo Project	11

Training and match Lighting for the second footy/cricket oval at Le Page Park	12

Euroa and District Community Sports Centre Upgrade	12

Community Splash Park/Water Playground - Water Play at Livvi’s Place	12

Upgrade Sandfield Reserve Skatepark: An Awesome Park for Local Youth	12

Little River Play and Fitness Circuit	14

Integrating Technology & Refurbishing Lyrebird Community Centre	14

New Score Shed and Storage garage for Wyndham BMX	15

Geelong Inclusive Art Project	15

Princes Highway Reserve Electronic Scoreboard	16

Solar Panels for a leading Banyule Disability Provider - IDV	17

Walter St Reserve Net Redevelopment - Redevelopment of the cricket nets at Walter St Reserve	17

Wyndham Community Arts Project - Water Tower Mural	18

Wyndham Community Arts Project - Water Tower Mural	19

Gold Street All Abilities Playground	19

Dalton Street Reserve - Activation Project: Sunshine West parkland community investment	20

# St Kilda Gatehouse – The Young Women’s Project

The Young Women’s Program has been ongoing since its launch in 2015, developing a way of supporting young people affected by or at risk of child sexual exploitation. This program has succeeded in providing a model of specialised support to assist young people build resilience, develop personal strengths, understand boundaries and increase their general safety and wellbeing.

In 2021, the program provided intensive outreach support for 31 high risk young women with complex needs, as well as 26 group work sessions that provided support to 15 young women.

The Project prides itself in adapting and learning from the young women and key networks that it supports. The grant enabled St Kilda Gatehouse to continue to build partnerships with community organisations, as well as work closely with Child Protection and SOCIT.

COVID-19 restrictions meant that outreach workers needed to learn how to support the young women virtually and noted that the difference in meeting face to face outdoors had better opportunities to connect than over the phone. St Kilda Gatehouse adapted their programs to focus on smaller group programs, meeting more regularly and moving outdoors or to lower risk environments.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# HE Parker Reserve Fit Out Project

The fit out of the new pavilion at HE Parker Reserve was delivered by Maroondah Council and completes the package of offerings at the reserve. The fit out of the new built pavilion including the kitchen, canteen, cool room, and upgraded equipment including audio visual and speaker upgrades. The project will attract new players and members to the new facilities with the aim to increase participation and new opportunities of social use and hire of the pavilion.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# Mitcham Cricket Club clubrooms fit out project

The fit out of the pavilion at Walker Park Reserve was delivered by the Mitcham Cricket Club and completes the package of offerings at the reserve including recently upgraded cricket training nets and new reserve lighting.

The fit out of the new built pavilion included upgrades to the existing change rooms to become female

friendly change rooms, upgrades to bathrooms, the social room and development of an additional wing to the existing facility complete with bar, viewing area and decking.

The project aims to attract new female players and members to the upgraded facilities with the aim to increase participation and new opportunities of social use and hire of the pavilion.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# Rebuild of the La Mama Theatre

The La Mama Theatre rebuild project has been successfully completed. The delay in completion was because of the restrictions on building due to the COVID-19 pandemic which affected the rebuild construction timeline in both 2020 and in 2021.

As well as reinstating the original building, a second building was built to house the office and rehearsal hub. As well as installing improved technical infrastructure, the building is now fully accessible with sustainable features (water tanks, insulation, solar panels.).

The impact is that La Mama Theatre will continue as a space that supports thousands of Victorian artists each year.  With improved facilities, it can support the next generations to develop and present work in the model that has been utilised and valued by artists for more than fifty years.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Resources.

# 2015-16 Community Facilities Funding Program

From outcomes reporting and evaluation, the program has provided:

• increased sport and recreation participation – 89% of projects showed a significant increase in

participation from 25 – 50%, whilst 10% of the projects maintained showed a slight to medium increase in participation (0-24%).

• increased female and junior participation – female participation in both sport and active recreation

almost doubled with dedicated or additional facilities. Junior sport participation gained the most with

junior boys as major beneficiaries.

• increased access to sport and recreation opportunities – a large majority of projects benefited two or

more clubs and/or organisations.

• better planning of sport and recreation facilities – four planning projects developed a sustainable and

community focused infrastructure investment direction and pipeline.

• innovative sport and recreation facilities – a large range of facility types were invested in to increase

diversity of participation opportunities. Examples include park exercise equipment, reclaimed tennis

court as a kids’ play space and community centre fitness circuits.

• environmentally sustainable facilities – over a quarter of the facilities installed included one or more ESD elements.

These ranged from solar panels, water reclamation/harvesting to efficient lighting which led to reduced

power consumption and cost and minimal impact on the environment.

• universally designed facilities - on average one to three universal design principals were applied to each facility. Equitable use and flexibility of use were the most common to be applied.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# Cobram Cricket Club Scoreboard

The new electronic scoreboard plays videos and music and has added value to the Cobram

Showgrounds, benefitting the Club and the broader community during various community events, such as the Cobram Agricultural Show, Rotary Show and Shine, the Australian Primary Schools Carnival, Masters Cricket, Moira Arts and Cultural Festival, Relay for Life and the Australian Sheep Dog Trials.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# Queenscliff Cultural Hub

The project has fulfilled four of nine contracted milestones and is on track for completion by 30 December 2022. An evaluation and outcomes summary will be provided post completion.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# East Ballarat Cricket Club Community Cricket Nets Project

Ballarat City Council have completed upgrades to the East Ballarat Cricket Club Community cricket nets that addressed the safety issues for the Club’s players during their sessions. The project has enabled the East Ballarat Cricket Club to meet the growing needs of local sports clubs through the provision of a safer and more welcoming community sport infrastructure.

Disclaimer: The above information was provided by the Department of Jobs, Projects and Regions.

# Hurstbridge Football & Cricket Pavilion Changeroom Upgrade

Nillumbik Shire Council have completed upgrades to the Hurstbridge Football Netball Club change rooms to encourage female participation and involvement. This project saw the construction of two additional female friendly changerooms and updates to the umpires’ rooms, and increased accessibility to all amenities and pathways surrounding the existing pavilion.

These upgrades have allowed for increased safety, participation, accessibility through improved universal designs and female-friendly facilities.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# Heathmont Bowls Club Synthetic Bowling Rink Replacement

This project saw the removal of current synthetic material, which included removing sand and then relevelling the surface and installing a new synthetic bowling material. The new surface provides a safer facility, savings on maintenance costs and promotes greater participation and events at the Heathmont Bowls Club.

Disclaimer: The above information was provided by the Department of Jobs, Precincts and Regions.

# McIntyre Wildlife Shelter

Funding enabled the extension of existing facilities and construction of a new macropod enclosure (see below photos). The area is larger, meaning more kangaroos can be cared for and they will have more space to exercise. This is particularly important as several other shelters in the area have closed or downsized, while there has been increased demand due to storms and floods in late 2022. The containers will provide a sturdy, sheltered area to treat injured wildlife.

The funding also contributed towards additional consumables including formula and feed and thus helped alleviate the rising costs of rescuing and caring for wildlife.

Disclaimer: The above information was provided by the Department of Energy, Environment and Climate Action.

# Peter Macallum Cancer Centre Mobile Exhibition Program

The unforeseen Covid 19 pandemic 2020/21 and the ensuing restrictions and various lockdowns have impacted the original timing of this project and affected the final stage of implementation. The hospital remains a high risk setting as we enter 2022 and restrictions have not yet been eased, with the result that the final exhibition component of the project remains on hold as it entails the involvement of non-essential external contractors, artists and installation staff who are unable to come onsite under the current circumstances.

However, the central and most important component of the project, for which $15,000 of funding was sought and allocated, was the fabrication of the plinths, pedestal units with Perspex covers and the mobile display cases. This was successfully managed and achieved in stages between the various lockdowns and has now been completed with all funds expended.

The significant acquisition of this display equipment will have far reaching benefits for the hospital’s art program. It will enable the safe, secure and flexible display of three dimensional artworks on a smaller and more intimate scale for the benefit of our less mobile patients, as a regular and ongoing part of the art program for years to come.

The first planned exhibition featuring contemporary Australian glass is presently on hold until restrictions within the hospital ease.

Disclaimer: The above information was provided by the Department of Health and Human Services.

# Avoca Silo Project

The major outcome of this project has been the establishment of a dedicated night and daytime outdoor entertainment venue with particular emphasis on supporting arts and cultural activities across a whole range of creative endeavours.

In relation to the large silo mural with its world ground- breaking ‘glow-in-the-dark feature a significant economic improvement has been enjoyed across local hospitality businesses because of greater visitor numbers stopping at the town.

As more and more of the proposed events occur at the site, even greater economic outcomes will follow.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Training and match Lighting for the second footy/cricket oval at Le Page Park

An infrastructure project to deliver better lighting for Oval 2 to provide more training opportunities/options seven days a week, as well as match lighting for night games of junior football.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Euroa & District Community Sports Centre Upgrade

Upgrade, improvement to facilities in Sports Stadium, used by the community, at Euroa Secondary

College.

The facility was built in 1989/90 and has had no improvements for over 30 years.

Air-conditioning units have been provided and basketball backboards have been replaced, wall padding was installed to meet OHS requirements, a third netball court was added, and a dividing curtain installed to create two separate teaching/ playing areas, when required.

Electronic scoreboards catering for various sports were also purchased and installed.

A Karcher Floor scrubber was also purchased to assists with ongoing maintenance and cleaning.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Community Splash Park/Water Playground - Water Play at Livvi’s Place

A free accessible outdoor water play experience has been provided to further enhance an inclusive play space that is well loved by the community.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Upgrade Sandfield Reserve Skatepark: An Awesome Park for Local Youth

The primary activity delivered was infrastructure, through the construction of a skatepark upgrade. This included an expanded concrete skate area with elements and features such as moguls, volcanoes, mini bowls and transition areas.

The upgrade has created a great new park that caters for different ages, experience levels and types of users including skateboarders, BMX and scooter riders.

Media Release:

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Little River Play and Fitness Circuit

To enhance the access to fitness equipment for the 150 pupils of Little River Primary School and the wider community. The students have enjoyed the new turf on the school oval and have been running around and engaging in games of cricket, football and soccer. The appearance of the school grounds has improved significantly which in turn has impacted school morale.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Integrating Technology & Refurbishing Lyrebird Community Centre

The primary activity delivered is that the Centre has been updated with current audio-visual equipment and new furniture, that is used on a daily.

The completion of the project allows Lyrebird to engage with more community members and ensure that participation at the Centre is a positive and valuable experience. The new technology and equipment have enhanced flexible learning and meeting spaces.

The upgraded facilities encourage more community members to participate, therefore providing opportunities for lifelong learning, prevent isolation and provide opportunities for disadvantaged community members.

The ‘English for Everyday Life’ tutor has commented that the new technologies have opened learning opportunities to students through different online mediums.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# New Score Shed and Storage garage for Wyndham BMX

This money provided infrastructure for the club to run events, store equipment and provide rest areas for members. Improved the standard of presentation to the community when presenting the club to them.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Geelong Inclusive Art Project

The primary activity was the creation of a public artwork celebrating people in our community with a lived experience of disability. This work took the form of a large concrete sculpture forming the words “I AM” and is intended to be interactive whereby the viewer puts themselves in the picture to create a sentence “I AM (person)”. Viewers are then encouraged via a QR code on the work to upload to social media with the tag #IAMGeelong.

Through the shortlisting process, the stakeholders and community participants expressed a desire to see artworks and stories from members of the disability community as an audio-visual experience in the public space, in addition to the static sculptural work. This has led to the commission of video documentation and projection work to be shown across a range of platforms in the future.

Finally, the artist creating the work engaged with 91 community participants to produce data for the inlay detail on the sculptural work, and through these workshops gathered a huge amount of text, video responses and drawings from the community. To honour these contributions and to give all works involved a public outlet, an artist’s book was commissioned to document the contributions. This will be available in print and online in December 2021.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Princes Highway Reserve Electronic Scoreboard

The installation of a new electronic scoreboard with Wi-Fi capabilities - video board dimensions - 5760mm x 2880mm with 10mm pitch on a steel structure 6 metres height. This scoreboard replaced the limited and outdated asset and will be the primary scoreboard in operation at Princes Highway Reserve West for the use by Council and co-tenants who utilise the west oval at Princes Highway Reserve.

The project will benefit the local community by providing year-round accessible information for both Oakleigh District Football and Netball Clubs and the wider community and increase ability for clubs to promote participation opportunities to spectators.

The scoreboard will allow the club to enhance their game day experience with electronic scoring, and sponsorship promotions.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Solar Panels for a leading Banyule Disability Provider - IDV

The project delivered a 40 kWp Solar PV Array for the IDV Disability Services Head Office in Macleod and two further Solar PV installations at IDV Houses for Disabled Residents in Briar Hill and Montmorency totalling 16.45 kWp.

The project has been a huge success after significant early engagement with IDV stakeholders. After initially being unsure about the project we worked with them to explain both the environmental and financial benefits of the project, as well as addressing safety concerns via a structural survey of their roof spaces. Through analysis of their energy data, we were also able to advise of changes in their energy usage to shift consumption into daylight hours and benefit from their Solar PV arrays.

Prior to this project IDV had spiralling energy bills of $25k+ per annum. Since project completion they have realised a 50% reduction in energy bills at their Head Office since 2019 because of their first Solar PV installation, as well as a further reduction in energy bills at their two residential houses.

IDV is now very engaged with energy efficiency and plan future projects to improve their thermal building envelope and reduce energy usage.

They plan to use the savings from the Solar PV project to expand their services and help more disabled residents in the community.

Since the beginning of this project the Banyule Clean Energy Group has also delivered over 100 kWp of Solar PV installations to residents and local businesses. We credit this in large part to the success and publicity of this project.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Walter St Reserve Net Redevelopment - Redevelopment of the cricket nets at Walter St Reserve

New infrastructure for the tenant cricket club and the wider community.

The project has resulted in increased use of the cricket nets as the nets are now safe for play and can cater for more usage as there are now four lanes instead of three. Council has received many phone calls from residents complimenting the new nets and thanking Council for the upgraded infrastructure.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Wyndham Community Arts Project - Water Tower Mural

Funding was used to design and install a mural on the surface of a disused 18-metre-high water tower, located at 1 Tower Road, Werribee. The installation of the mural was successfully completed in July 2020.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.

# Gold Street All Abilities Playground

This project was to provide an all abilities play space to cater for a diverse range of children including children with special needs. The space has diversity, flexibility and simplicity threaded through the design. The play space has replaced an area that was unused by children and now there is a play space that includes a contoured, sensory space with wheelchair access.

This play space is accessible to the broader community as the school gates are open and the school grounds are accessible after school and on weekends. This play space will benefit many children in the local area.

Disclaimer: This information was provided by the Department of Families, Fairness and Housing.

# Dalton Street Reserve - Activation Project: Sunshine West parkland community investment

This project included an upgrade to a circuit path, comprising of seats, a nature play area with artwork depicting local fauna and planting of local flora, including the installation of a fitness station and a basketball court.

The facilities constructed and installed provide opportunities for physical, social and emotional wellbeing of the community.

Disclaimer: The above information was provided by the Department of Families, Fairness and Housing.